## Re-host-Dashboard
[18 empty] | Check-101 (AWS Migration team) |  |  | Disk Size | [22 empty] | EC2-Tagging -(AWS Migration/Carrier team) | [15 empty] | Pre-Migration |  |  |  |  | Build |  |  | Validate |  |  | Boot-up Testing |  |  |  |  | Cutover Validation | [6 empty] | Post Cutover activities/validation (App Owner)
Release | Wave | Wave Start Date | Wave End Date | Exxplicit Cutover Window (ET) | App | Server_Name | Migration Status | FQDN | On-prem IP | AD Migration Status | DC/Site | No of CPU | Total Memory (GB) | Operating System | OS Version | Server Type | App Owner | AWS Migration Team RDP access validation | Outbound TCP 443,1500 through Proxy | Interview Answer Cross check | C: | D: | E: | F: | G: | R: | X: | Target AWS account | Target AWS Account Name | Target EC2 Instance Type | EBS volume Type (Std, SSD, Provisioned) | EBS IOPS | EBS Encryption (Yes/No) | Target Subnet | Target Security Group | securitygroup_IDs_test | Target Private IP | Target Public IP or EIP | IAM Role | cloudendure project name | server_tier | server_environment | tenancy | ApplicationName | Server Name | Application ID | ApplicationOwner | BusinessUnit | Department | CostCenter | ServerType | ComplianceRequirement | Entity | Environment | Region | UsagePattern | MaxLifeTime | backup | AppCat | Confirm Wave Plan with App Owner (AWS, Carrier) | Submit BPAR [status-date] (Carrier) | Submit RFC and Schedule Change window (Carrier) | Complete migration factory intake form (AWS) | Import intake form in to Migration Factory (AWS) | Verify Source Server Pre-requisite (AWS) | Install CloudEndure agent (AWS) | (Optional) Push post-launch script (AWS, Carrier) | Verify CloudEndure replication status (AWS) | (Optional) Troubleshoot CloudEndure issues (AWS) | Validate local admin/sudo user on source machines (AWS, Carrier) | Launch server from migration factory and CloudEndure (AWS, Carrier) | Verify instance boot up status (AWS) | (Optional) Resolve instance boot up issues (AWS) | Validate cutover blueprint for Target instance type, disk IOPS, IP, SG,Subnet (AWS) | Terminate test instances (AWS) | Verify CloudEndure replication status (AWS)4 | Stop Service or shutdown source server for cutover (Carrier) | Launch instances for cutover (AWS) | Verify instance boot up status (AWS)5 | Test RDP/SSH access (AWS, Carrier) | (Optional) Clean up local admin/sudo after cutover (AWS) | Change DNS or other network settings for the application (Carrier) | Application Configuration Change/Network change (Carrier) | Post Cutover activities/ Application validation (App Owner) | Notes | Issues
Pilot | thisweek | 5/27/2020 | 07/15/2020 |  | NWDI-STAGE | CUSNWK0V | Ready to Test | CUSNWK0V.carcgl.com | 159.82.100.14 | COMPLETE | Newington | 2 | 8 | windows | Windows 2008 R2 | Rehost | Sarah Strominger | Yes | Yes | [8 empty] | 260780007980 | HVAC_Com_Preprod | t2.medium | SSD | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | sg-0cfa6a707d1ff7fe5 | 10.233.9.140 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Preprod_260780007980 | app | stage | Shared | NWDI-STAGE | CUSNWK0V | NA | Sarah Strominger | HVAC_Com_Preprod | 4732 | 104742 | Application | NA | NA | STG | us-east-1 | Weekdays | Indefinitely | y | Bronze | complete -26th May 2020 |  | Optional | complete - 27th May 2020 | complete - 27th May 2020 | In-Progress - 28th May 2020 | complete | Yet to Start - 1st June 2020 | complete | complete | complete | complete | complete | complete | complete | complete | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020
Pilot | thisweek | 5/27/2020 | 07/15/2020 |  | JONAS - STAGE | CUSNWA74 | Ready to Test | cusnwa74.carcgl.com | 10.177.6.127 | COMPLETE | Newington | 2 | 4 | windows | Windows 2012 R2 | Rehost | Randy Durocher | Yes | Yes | [8 empty] | 260780007980 | HVAC_Com_Preprod | t2.large | SSD | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | sg-0cfa6a707d1ff7fe5 | 10.233.9.141 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Preprod_260780007980 | app | stage | Shared | JONAS - STAGE | CUSNWA74 | 6316 | Randy Durocher | HVAC_Com_Preprod | 3899 | 104742 | Application | NA | NA | STG | us-east-1 | Weekdays | Indefinitely | y | Bronze | complete -26th May 2020 |  | Optional | complete - 27th May 2020 | complete - 27th May 2020 | In-Progress - 28th May 2020 | complete | Yet to Start - 1st June 2020 | complete | complete | complete | complete | complete | complete | complete | complete | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020
Pilot | thisweek | 5/27/2020 | 07/15/2020 |  | MYEDDIE-TEST | KUSMND19 | Ready to Test | kusmnd19.carcgl.com | 159.82.226.170 | COMPLETE | Meriden | 2 | 4 | windows | Microsoft Windows Server 2008 R2 Enterprise | Rehost | Jeff Turner/Timothy Kennedy | Yes | Yes | [8 empty] | 917128996017 | Fire_And_Security_PreProd | t2.large | SSD | N/A | YES | subnet-0dd905d5c0776f8ac | sg-0a08dc8c96199a489 | sg-0a08dc8c96199a489 | 10.233.153.140 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_PreProd_917128996017 | db | test | Shared | MYEDDIE-TEST | KUSMND19 | 1856 | Jeff Turner/Timothy Kennedy | Fire_And_Security_PreProd | CASS-EDWRD | IC990447 | Database | NA | NA | TST | us-east-1 | Weekdays | Indefinitely | y | Bronze | complete -26th May 2020 |  | Optional | complete - 27th May 2020 | complete - 27th May 2020 | In-Progress - 28th May 2020 | complete | Yet to Start - 1st June 2020 | complete | complete | complete | complete | complete | complete | complete | complete | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020
R02 | R02W01 | 6/04/2020 | 06/18/2020 |  | Carrier DEBTS - NonProd | cusmna07 | Complete | cusmna07.carcgl.com | 159.82.227.236 | COMPLETE | Meriden | 8 | 64 | windows | Microsoft Windows Server 2016 Standard | Rehost | Tracy Jones and Jon Ascher | Yes | TBV | [8 empty] | 890585303181 | Fire_And_Security_Dev | r5.2xlarge | SSD | N/A | YES | subnet-0c6533ebaf5f1b1a2 | sg-05d2d8a7449289f9e | sg-09876514db5a00fb8 | 10.233.193.140 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Dev_890585303181 | app | dev | Shared | Carrier DEBTS - NonProd | cusmna07 | 5932 | Tracy Jones and Jon Ascher | Fire_And_Security_Dev | 0 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze | complete | complete | complete | complete | complete | complete | complete | complete | 6/10/2020 | 6/10/2020 | 6/10/2020 | 6/11/2020 | 6/11/2020 | 6/11/2020 | 6/11/2020 | 6/13/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | Yet to Start - 18th June 2020 | Yet to Start - 18th June 2020
Pilot | Pilot | 5/27/2020 | 06/11/2020 |  | Kidde Safety Meriden (9888), TEST | CUSMNK0P | Ready to Test | cusmnk0p.carcgl.com | 159.82.226.99 | COMPLETE | Meriden | 2 | 4 | windows | Windows Server 2008 R2 Standard | Rehost | Chris Marshall | Yes | Yes | [8 empty] | 260780007980 | Fire_And_Security_PreProd | t2.medium | SSD | N/A | YES | subnet-0dd905d5c0776f8ac | sg-0a08dc8c96199a489 | sg-0104099b41897670f | 10.233.153.141 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_PreProd_917128996017 | app | test | Shared | Kidde Safety Meriden (9888), TEST | CUSMNK0P | NA | Chris Marshall | Fire_And_Security_PreProd | FS-00100 | IC990447 | Application | NA | NA | TST | us-east-1 | Weekdays | Indefinitely | y | Bronze | complete -26th May 2020 |  | Optional | complete - 27th May 2020 | complete - 27th May 2020 | In-Progress - 28th May 2020 | complete | Yet to Start - 1st June 2020 | complete | complete | complete | complete | complete | complete | complete | complete | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020
R01 | R01W01 | 07/02/2020 | 07/29/2020 |  | General Test | CUSH1AV8 | Pending Agent Install | cush1av8.utccgl.com | 10.223.24.7 | COMPLETE - 5/21/20 | HP MPC - Alpharetta,GA | 2 | 8 | windows | Windows Server 2012 R2 Datacenter | Rehost | Jordan King | Yes | Yes |  | 79.51 | 200 | [5 empty] | 260780007980 | HVAC_Com_Preprod | m5.large | SSD | N/A | YES | subnet-0dd905d5c0776f8ac | sg-0a08dc8c96199a489 | sg-0a08dc8c96199a489 | 10.233.153.142 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_PreProd_917128996017 | app | test | Shared | General Test | CUSH1AV8 | NA | Jordan King | HVAC_Com_Preprod | CCS-HPEMPC-15736948-00A?DevCodeCollab (Offering: Archived - UTC Prod Windows Virtual- Comm) | IC990447 | Application | NA | NA | TST | us-east-1 | Weekdays | Indefinitely | y | Bronze | complete -26th May 2020 |  | 43969 | complete - 27th May 2020 | complete - 27th May 2020 | In-Progress - 28th May 2020 | Yet to start -27th May 2020 | Yet to Start - 1st June 2020 | Yet to Start - 2nd June 2020 | Yet to Start - 2nd June 2020 | Yet to Start - 3nd June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020
R01 | R01W01 | 07/02/2020 | 07/29/2020 |  | Klocworks | cush1ax3 | Pending Agent Install | cush1ax3.utccgl.com | 10.223.72.20 10.223.24.20 | COMPLETE | HP MPC - Alpharetta,GA | 8 | 16 | windows | Microsoft Windows Server 2016 Datacenter | Rehost | Jordan King | Yes |  |  | 75.29 | 1000 | [5 empty] | 808538705328 | Fire_And_Security_Prod | c5.2xlarge | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.160 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | Klocworks | cush1ax3 | 7047 | Jordan King | Fire_And_Security_Prod | CCS-HPEMPC-16939911-00A?EngineeringDevelopment (Offering: Archived - UTC Prod Windows Virtual - Comm) | IC990447 | Application | NA | NA | PROD | us-east-1 | Weekdays | Indefinitely | y | Bronze | 43972 |  | 43973 | 43973 | 43976 | 43977 | 43977 | 43977 | 43979 | 43979 | 43979 | 43990 | 43990 | 43990 | 43990 | 43990 | 43993 | 43993 | 43993 | 43993 | 43993 | 43993 | 43993 | 43993
R01 | R01W01 | 07/02/2020 | 07/29/2020 | TBD by Sarah S. | LiveCompare | CUSH1AY3 | Boot-up Test Complete | cush1ay3.utccgl.com | 10.223.24.29 10.223.72.29 | COMPLETE | HP MPC - Alpharetta,GA | 8 | 32 | windows | Microsoft Windows Server 2016 Datacenter | Rehost | Sarah Strominger | Yes | No |  | 79 | 1000 | [5 empty] | 913828333602 | HVAC_Com_Prod | m5.2xlarge | SSD | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.17.143 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | LiveCompare | CUSH1AY3 | NA | Sarah Strominger | HVAC_Com_Prod | CCS-HPEMPC-17778726-00A-LIVECOMPARE (Offering: Archived - UTC Prod Windows Virtual - Comm) | 104742 | Application | NA | NA | PROD | us-east-1 | Weekdays | Indefinitely | y | Bronze
R01 | R01W02 | 07/02/2020 | 08/04/2020 | TBD by Sarah S. | Approva 10.1.6.0007 | CUSH1AT3 | Boot-up Test Complete | cush1at3.utccgl.com | 10.223.72.4 10.223.24.2 | COMPLETE - 5/21/20 | HP MPC - Alpharetta,GA | 4 | 8 | windows | Microsoft Windows Server 2012 R2 Datacenter | Rehost | Sarah Strominger - rambabu.katta2@carrier.comm (tester) - need Wintel DXC team | Yes | No |  | 79.51 | 100 | [5 empty] | 913828333602 | HVAC_Com_Prod | c5.xlarge | SSD | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.17.144 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | Approva 10.1.6.0007 | CUSH1AT3 | 7047 | Sarah Strominger - rambabu.katta2@carrier.comm (tester) - need Wintel DXC team | HVAC_Com_Prod | CCS-HPEMPC-15071868-00A-Approva (Offering: Archived - UTC Prod Windows Virtual- Comm) | 104742 | Application | NA | NA | PROD | us-east-1 | Weekdays | Indefinitely | y | Bronze
R01 | R01W02 | 07/02/2020 | 08/04/2020 | TBD by Sarah S. | Approva 10.1.6.0007 | CUSH1D06 | Boot-up Test Complete | cush1d06.utccgl.com | 10.223.72.5 10.223.24.3 | COMPLETE - 5/21/20 | HP MPC - Alpharetta,GA | 8 | 16 | windows | Microsoft Windows Server 2012 R2 Datacenter | Rehost | Sarah Strominger - cheryl.a.mmantel@dxc.com (tester) - need Wintel DXC team | Yes | No |  | 79.51 | 250 | [5 empty] | 913828333602 | HVAC_Com_Prod | c5.2xlarge | SSD | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.17.145 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | Approva 10.1.6.0007 | CUSH1D06 | 8899 | Sarah Strominger - cheryl.a.mmantel@dxc.com (tester) - need Wintel DXC team | HVAC_Com_Prod | CCS-HPEMPC-15071868-01A-ApprovaDB (Offering: Archived - UTC Prod Windows Virtual- Comm) | 104742 | Application | NA | NA | PROD | us-east-1 | Weekdays | Indefinitely | y | Bronze
R01 | R01W01 | 07/02/2020 | 07/29/2020 |  | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | cush0a03 | Ready to Test | cush0a03.utccgl.com | 10.223.207.251 10.223.159.251 | COMPLETE - 5/13/20 | HP MPC - Tulsa,OK | 32 | 128 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger | Yes | No |  | 79.29 | 99.87 | [5 empty] | 913828333602 | HVAC_Com_Prod | r5.8xlarge | SSD | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.17.146 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | cush0a03 | 5984 | Sarah Strominger | HVAC_Com_Prod | CCS | 104742 | Application | NA | NA | PROD | us-east-1 | monthly (Monday after 3rd Sunday) 6 to 9PM (EST) | Indefinitely | y | Bronze
R01 | R01W01 | 07/02/2020 | 07/29/2020 |  | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | cush0a07 | Ready to Test | cush0a07.utccgl.com | 10.223.207.245 10.223.159.245 | COMPLETE - 5/13/20 | HP MPC - Tulsa,OK | 32 | 128 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger | Yes | No |  | 79.29 | 99.87 | [5 empty] | 913828333602 | HVAC_Com_Prod | r5.8xlarge | SSD | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.17.147 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | cush0a07 | 5984 | Sarah Strominger | HVAC_Com_Prod | CCS | 104742 | Application | NA | NA | PROD | us-east-1 | monthly (Monday after 3rd Sunday) 6 to 9PM (EST) | Indefinitely | y | Bronze
R01 | R01W01 | 07/02/2020 | 07/29/2020 |  | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | CUSH0D02 | Ready to Test | cush0d02.utccgl.com | 10.223.207.250 10.223.159.250 | COMPLETE - 5/13/20 | HP MPC - Tulsa,OK | 16 | 32 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger | Yes | No |  | 119.29 | 99.87 |  | 49.87 | 49.87 |  |  | 913828333602 | HVAC_Com_Prod | c5.4xlarge | SSD | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.17.148 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | CUSH0D02 | 6335 | Sarah Strominger | HVAC_Com_Prod | CCS | 104742 | Application | NA | NA | PROD | us-east-1 | monthly (Monday after 3rd Sunday) 6 to 9PM (EST) | Indefinitely | y | Bronze
R01 | R01W01 | 07/02/2020 | 07/29/2020 |  | HVACNA-TIDALQSA-IT-US-HVAC 6.2.1.848 - QA1 | CUSH0A01 | Pending Agent Install | cush0a01.utccgl.com | 10.223.159.254 | COMPLETE | HP MPC - Tulsa,OK | 32 | 128 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger |  |  |  | 79.29 | 99.87 | [5 empty] | 260780007980 | HVAC_Com_Preprod | r5.8xlarge | SSD | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | sg-0cfa6a707d1ff7fe5 | 10.233.9.154 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Preprod_260780007980 | app | QA | shared | HVACNA-TIDALQSA-IT-US-HVAC 6.2.1.848 - QA1 | CUSH0A01 | 6335 | Sarah Strominger | HVAC_Com_Preprod | CCS | 104742 | Application | NA | NA | TST | us-east-1 | NA | Indefinitely | y | Bronze
R01 | R01W01 | 07/02/2020 | 07/29/2020 |  | HVACNA-TIDALQSA-IT-US-HVAC 6.2.1.848 - QA1 | cush0a02 | Pending Agent Install | cush0a02.utccgl.com | 10.223.159.252 | COMPLETE | HP MPC - Tulsa,OK | 16 | 32 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger |  |  |  | 79.29 | 99.87 | [5 empty] | 260780007980 | HVAC_Com_Preprod | c5.4xlarge | SSD | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | sg-0cfa6a707d1ff7fe5 | 10.233.9.155 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Preprod_260780007980 | app | QA | shared | HVACNA-TIDALQSA-IT-US-HVAC 6.2.1.848 - QA1 | cush0a02 | 6335 | Sarah Strominger | HVAC_Com_Preprod | CCS | 104742 | Application | NA | NA | TST | us-east-1 | NA | Indefinitely | y | Bronze
R01 | R01W01 | 07/02/2020 | 07/29/2020 |  | HVACNA-TIDALQSA-IT-US-HVAC 6.2.1.848 - QA1 | CUSH0A06 | Pending Agent Install | cush0a06.utccgl.com | 10.223.159.246 | COMPLETE | HP MPC - Tulsa,OK | 48 | 256 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger |  |  |  | 79.29 | 99.87 | [5 empty] | 260780007980 | HVAC_Com_Preprod | r5.12xlarge | SSD | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | sg-0cfa6a707d1ff7fe5 | 10.233.9.156 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Preprod_260780007980 | app | QA | shared | HVACNA-TIDALQSA-IT-US-HVAC 6.2.1.848 - QA1 | CUSH0A06 | NA | Sarah Strominger | HVAC_Com_Preprod | CCS | 104742 | Application | NA | NA | TST | us-east-2 | NA | Indefinitely | y | Bronze
R01 | R01W01 | 07/02/2020 | 07/29/2020 |  | HVACNA-TIDALQSA-IT-US-HVAC 6.2.1.848 - QA1 | CUSH0D01 | Pending Agent Install | cush0d01.utccgl.com | 10.223.159.253 | COMPLETE | HP MPC - Tulsa,OK | 16 | 32 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger |  |  |  | 119.29 | 49.87 |  | 49.87 | 49.87 |  |  | 260780007980 | HVAC_Com_Preprod | c5.4xlarge | SSD | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | sg-0cfa6a707d1ff7fe5 | 10.233.9.157 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Preprod_260780007980 | app | QA | shared | HVACNA-TIDALQSA-IT-US-HVAC 6.2.1.848 - QA1 | CUSH0D01 | NA | Sarah Strominger | HVAC_Com_Preprod | CCS | 104742 | Application | NA | NA | TST | us-east-1 | NA | Indefinitely | y | Bronze
R01 | R01W03 | 07/09/2020 | 08/16/2020 |  | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | CUSH0A05 | Pending Agent Install | CUSH0A05.utccgl.com | 10.223.159.247 | 0 | HP MPC - Tulsa,OK | 16 | 32 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger | YES | No |  | 79.29 | 99.87 | [5 empty] | 913828333602 | HVAC_Com_Prod | c5.4xlarge | SSD | N/A | YES | subnet-02d0b3ed0b3132028 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.94.10 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | CUSH0A05 | NA | Sarah Strominger | HVAC_Com_Prod | CCS | 104742 | Application | NA | NA | PROD | us-east-2 | weekdays | Indefinitely | y | Bronze
R01 | R01W01 | 07/09/2020 | 07/29/2020 | TBD by Sarah S. | GTS 8.08-Non Production | CUSH0A70 | Boot-up Test Complete | cush0a70.utccgl.com | 10.223.152.10 | COMPLETE | HP MPC - Tulsa,OK | 8 | 16 | windows | Microsoft Windows Server 2012 R2 Datacenter | Rehost | Sarah Strominger | YES | No |  | 79.51 | 50 | [5 empty] | 260780007980 | HVAC_Com_Preprod | c5.2xlarge | SSD | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | sg-0cfa6a707d1ff7fe5 | 10.233.9.143 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Preprod_260780007980 | app | Stage | Shared | GTS 8.08-Non Production | CUSH0A70 | NA | Sarah Strominger | HVAC_Com_Preprod | CCS-HPEMPC-15622800-00A-GTSNonProd (Offering: Archived - UTC Prod Windows Virtual- Comm) | 104742 | Application | NA | NA | STG | Us-east-1 | 24 Hous | Indefinitely | y | Bronze
R01 | R01W03 | 07/09/2020 | 08/16/2020 |  | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | CUSH1A01 | Pending Agent Install | cush1a01.utccgl.com | 10.223.31.254 | 0 | HP MPC - Alpharetta,GA | 32 | 128 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger | YES | No |  | 79.29 | 99.87 | [5 empty] | 913828333602 | HVAC_Com_Prod | r5.8xlarge | SSD | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.17.149 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | CUSH1A01 | 7047 | Sarah Strominger | HVAC_Com_Prod | CCS | 104742 | Application | NA | NA | PROD | us-east-1 | NA | Indefinitely | y | Bronze
R01 | R01W03 | 07/09/2020 | 08/16/2020 |  | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | CUSH1A02 | Pending Agent Install | CUSH1A02.utccgl.com | 10.223.31.252 | 0 | HP MPC - Alpharetta,GA | 48 | 256 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger | YES | No |  | 79.29 | 99.87 | [5 empty] | 913828333602 | HVAC_Com_Prod | r5.12xlarge | SSD | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.17.150 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | CUSH1A02 | NA | Sarah Strominger | HVAC_Com_Prod | CCS | 104742 | Application | NA | NA | PROD | us-east-1 | NA | Indefinitely | y | Bronze
R01 | R01W03 | 07/09/2020 | 08/16/2020 |  | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | CUSH1AY4 | Pending Agent Install | cush1ay4.utccgl.com | 10.223.24.30 | 0 | HP MPC - Alpharetta,GA | 8 | 128 | windows | Microsoft Windows Server 2012 R2 Datacenter | Rehost | Sarah Strominger | YES | No |  | 79.51 | 100 | [5 empty] | 913828333602 | HVAC_Com_Prod | r5.4xlarge | SSD | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.17.151 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | CUSH1AY4 | 6335 | Sarah Strominger | HVAC_Com_Prod | CCS-HPEMPC-17839207-00A-TIDALJUMP (Offering: Archived - UTC Prod Windows Virtual - Comm) | 104742 | Application | NA | NA | PROD | us-east-1 | NA | Indefinitely | y | Bronze
R01 | R01W03 | 07/09/2020 | 08/16/2020 |  | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | cush1d01 | Pending Agent Install | cush1d01.utccgl.com | 10.223.31.253 | 0 | HP MPC - Alpharetta,GA | 16 | 32 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger | YES | No |  | 119 | 99.87 |  | 199.87 | 199.87 |  |  | 913828333602 | HVAC_Com_Prod | r5.xlarge | SSD | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.17.152 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | cush1d01 | 6335 | Sarah Strominger | HVAC_Com_Prod | CCS | 104742 | Application | NA | NA | PROD | us-east-1 | NA | Indefinitely | y | Bronze
R01 | R01W03 | 07/09/2020 | 08/16/2020 |  | HVACNA-TIDALQSA-IT-US-HVAC 6.2.1.848 - HA/DR | CUSH0A04 | Pending Agent Install | CUSH0A04.utccgl.com |  | 0 | HP MPC - Alpharetta,GA | 32 | 128 | Windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger |  |  |  | 79.29 | 99.87 | [5 empty] | 913828333602 | HVAC_Com_Prod | r5.8xlarge |  | N/A | YES | subnet-0634ce85e89e184bf | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.19.10 |  | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | HVACNA-TIDALQSA-IT-US-HVAC 6.2.1.848 - HA/DR | CUSH0A04 | NA | Sarah Strominger | HVAC_Com_Prod | NA | #REF! | Application | NA | NA |  | us-east-2 | NA | Indefinitely | y | Bronze
R01 | R01W03 | 07/09/2020 | 08/16/2020 |  | HVACNA-TIDALQSA-IT-US-HVAC 6.2.1.848 - HA/DR | CUSH0A08 | Pending Agent Install | CUSH0A08.utccgl.com |  | 0 | HP MPC - Alpharetta,GA | 48 | 254 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger |  |  |  | 79.29 | 99.87 | [5 empty] | 913828333602 | HVAC_Com_Prod | r5.12xlarge |  | N/A | YES | subnet-0634ce85e89e184bf | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.19.11 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | HVACNA-TIDALQSA-IT-US-HVAC 6.2.1.848 - HA/DR | CUSH0A08 | NA | Sarah Strominger | HVAC_Com_Prod | NA | #REF! | Application | NA | NA | PROD | us-east-2 | NA | Indefinitely | y | Bronze
R01 | R01W03 | 07/09/2020 | 08/16/2020 |  | HVACNA-TIDALQSA-IT-US-HVAC 6.2.1.848 - HA/DR | CUSH0D03 | Pending Agent Install | CUSH0D03.utccgl.com |  | 0 | HP MPC - Alpharetta,GA | 16 | 32 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger |  |  |  | 119.29 | 99.87 |  | 99.87 | 99.87 |  |  | 913828333602 | HVAC_Com_Prod | c5.4xlarge |  | N/A | YES | subnet-0634ce85e89e184bf | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.19.12 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | HVACNA-TIDALQSA-IT-US-HVAC 6.2.1.848 - HA/DR | CUSH0D03 | NA | Sarah Strominger | HVAC_Com_Prod | NA | #REF! | Application | NA | NA | PROD | us-east-2 | NA | Indefinitely | y | Bronze
R01 | R01W01 | 07/09/2020 | 07/29/2020 | TBD by Sarah S. | Uperform 5.20.9 | cush1ay5 | Boot-up Test Complete | cush1ay5.utccgl.com | 10.223.24.32 | COMPLETE - 5/21/20 | HP MPC - Alpharetta,GA | 8 | 16 | windows | Microsoft Windows Server 2016 Datacenter | Rehost | Sarah Strominger | YES | No |  | 79 |  | 50 |  |  |  |  | 913828333602 | HVAC_Com_Prod | c5.2xlarge | SSD | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.17.155 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | Uperform 5.20.9 | cush1ay5 | NA | Sarah Strominger | HVAC_Com_Prod | CCS-DXCMPC-17929643-00A-UPERFORM (Offering: Archived - UTC Prod Windows Virtual - Comm) | 104742 | Application | NA | NA | PROD | us-east-1 | NA | Indefinitely | y | Bronze
R01 | R01W01 | 07/09/2020 | 07/29/2020 | TBD by Sarah S. | Uperform 5.20.9 | cush1d17 | Boot-up Test Complete | cush1d17.utccgl.com | 10.223.24.31 | COMPLETE - 5/21/20 | HP MPC - Alpharetta,GA | 8 | 16 | windows | Microsoft Windows Server 2016 Datacenter | Rehost | Sarah Strominger | YES | No |  | 79 |  | 150 | 50 | 150 |  |  | 913828333602 | HVAC_Com_Prod | c5.2xlarge | SSD | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.17.156 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | Uperform 5.20.9 | cush1d17 | NA | Sarah Strominger | HVAC_Com_Prod | CCS-HPEMPC-17929680-00A-UPERFORM (Offering: Archived - UTC Prod Windows Virtual - Comm) | 104742 | Application | NA | NA | PROD | us-east-1 | NA | Indefinitely | y | Bronze
R01 | R01W01 | 07/09/2020 | 07/29/2020 | TBD by Sarah S. | Uperform 5.20.9 | cush1w04 | Boot-up Test Complete | cush1w04.utccgl.com | 10.223.24.27 | COMPLETE - 5/21/20 | HP MPC - Alpharetta,GA | 8 | 16 | windows | Microsoft Windows Server 2016 Datacenter | Rehost | Sarah Strominger | YES | No |  | 79 |  | 100 |  |  |  |  | 913828333602 | HVAC_Com_Prod | c5.2xlarge | SSD | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.17.157 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | Uperform 5.20.9 | cush1w04 | NA | Sarah Strominger | HVAC_Com_Prod | CCS-HPEMPC-17929750-00A-UPERFORM (Offering: Archived - UTC Prod Windows Virtual - Comm) | 104742 | Application | NA | NA | PROD | us-east-1 | NA | Indefinitely | y | Bronze
R01 | R01W04 | 07/09/2020 | 09/20/2020 |  | GTS 8.08-Production Secondary | CUSH0A76 | Pending Agent Install | cush0a76.carcgl.com | 10.223.152.16 | COMPLETE | HP MPC - Tulsa,OK | 8 | 16 | windows | Microsoft Windows Server 2012 R2 Datacenter | Rehost | Sarah Strominger | Yes | No |  | 79.51 | 50 | [5 empty] | 913828333602 | HVAC_Com_Prod | c5.2xlarge | SSD | N/A | YES | subnet-0634ce85e89e184bf | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.19.13 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | GTS 8.08-Production Secondary | CUSH0A76 | NA | Sarah Strominger | HVAC_Com_Prod | CCS-HPEMPC-15622784-00A-GTSRFSecondary (Offering: UTC Prod Windows Virtual - Comm) | 104742 | Application | NA | NA | PROD | us-east-2 | 24 Hous | Indefinitely | y | Bronze
R01 | R01W04 | 07/09/2020 | 09/20/2020 |  | GTS 8.08-Production Primary | cush1aw5 | Pending Agent Install | CUSH1AW5.carcgl.com | 10.223.24.16 | COMPLETE | HP MPC - Alpharetta,GA | 8 | 16 | windows | Microsoft Windows Server 2012 R2 Datacenter | Rehost | Sarah Strominger | Yes | No |  | 79.51 | 50 | [5 empty] | 913828333602 | HVAC_Com_Prod | c5.2xlarge | SSD | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.17.154 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | GTS 8.08-Production Primary | cush1aw5 | NA | Sarah Strominger | HVAC_Com_Prod | CCS-HPEMPC-15622746-00A-GTSRFPrimary (Offering: UTC Prod Windows Virtual - Comm) | 104742 | Application | NA | NA | PROD | us-east-1 | 24 Hous | Indefinitely | y | Bronze
R01 | R01W04 | 07/09/2020 | 09/20/2020 |  | Production printer server | CUSH1P01 | Pending Agent Install | cush1p01.utccgl.com | 10.223.24.18 | 0 | HP MPC - Alpharetta,GA | 8 | 16 | windows | Windows Server 2012 R2 Datacenter | Rehost | Sarah Strominger |  |  |  | 79.51 | 50 | [5 empty] | 913828333602 | HVAC_Com_Prod | c5.2xlarge | SSD | N/A | YES | subnet-023516f902c3d8757 | sg-06b51bf12deaa479a | sg-0c55b9769612daba9 | 10.233.137.142 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Dev_436524867280 | app | Production | Shared | Production printer server | CUSH1P01 | NA | Sarah Strominger | HVAC_Com_Prod | CCS-DXCMPC-19356397-00A-SAP_PRINTPrimary (Offering: UTC Prod Windows Virtual - Comm) | 104742 | Application | NA | NA | Production | us-east-1 | NA | Indefinitely | y | Bronze
R01 | R01W01 | 07/09/2020 | 07/29/2020 |  | Development printer server | CUSH0A71 | Pending Agent Install | cush0a71.utccgl.com | 10.223.152.11 | 0 | HP MPC - Tulsa,OK | 8 | 16 | windows | Windows Server 2012 R2 Datacenter | Rehost | Sarah Strominger |  |  |  | 79.51 | 50 | [5 empty] | 913828333602 | HVAC_Com_Preprod | c5.2xlarge | SSD | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.17.158 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | Development printer server | CUSH0A71 | NA | Sarah Strominger | HVAC_Com_Preprod | CCS-HPEMPC-16104274-00A-SAPPRINTNONPROD (Offering: Archived - UTC Prod Windows Virtual- Comm) | 104742 | Application | NA | NA | PROD | us-east-1 | NA | Indefinitely | y | Bronze
R01 | R01W04 | 07/09/2020 | 09/20/2020 |  | Production printer server | CUSH0P01 | Pending Agent Install | cush0p01.utccgl.com | 10.223.152.5 | 0 | HP MPC - Tulsa,OK | 8 | 16 | windows | Windows Server 2012 R2 Datacenter | Rehost | Sarah Strominger |  |  |  | 79.51 | 50 | [5 empty] | 913828333602 | HVAC_Com_Prod | c5.2xlarge | SSD | N/A | YES | subnet-0634ce85e89e184bf | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.19.14 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | Production printer server | CUSH0P01 | NA | Sarah Strominger | HVAC_Com_Prod | CCS-DXCMPC-19357990-00A-SAP_PRINTSecondary (Offering: UTC Prod Windows Virtual - Comm) | 104742 | Application | NA | NA | PROD | us-east-2 |  | Indefinitely | y | Bronze
R02 | R02W01 | 6/04/2020 | 06/18/2020 |  | Carrier PayCzar - NonProd | cusmna07 | Complete | cusmna07.carcgl.com | 159.82.227.236 | COMPLETE | Meriden | 8 | 64 | windows | Microsoft Windows Server 2016 Standard | Rehost | Tracy Jones and Jon Ascher | Yes | TBV | [8 empty] | 890585303181 | Fire_And_Security_Dev | r5.2xlarge | SSD | N/A | YES | subnet-0c6533ebaf5f1b1a2 | sg-05d2d8a7449289f9e | sg-09876514db5a00fb8 | 10.233.193.140 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Dev_890585303181 | app | dev | Shared | Carrier PayCzar - NonProd | cusmna07 | NA | Tracy Jones and Jon Ascher | Fire_And_Security_Dev | 0 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze | complete | complete | complete | complete | complete | complete | complete | complete | 6/10/2020 | 6/10/2020 | 6/10/2020 | 6/11/2020 | 6/11/2020 | 6/11/2020 | 6/11/2020 | 6/13/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | Yet to Start - 18th June 2020 | Yet to Start - 18th June 2020
R02 | R02W02 | 6/04/2020 | 06/25/2020 |  | Production planning system | CUSMND0L | Complete | cusmnd0l.carcgl.com | 159.82.226.140 | COMPLETE | Meriden | 2 | 8 | windows | Windows Server 2008 R2 Standard | Rehost | Alejandro Martinez, Zamora Armando | TBV | TBV | [8 empty] | 808538705328 | Fire_And_Security_Prod | m5.large | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.147 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | Production planning system | CUSMND0L | NA | Alejandro Martinez, Zamora Armando | Fire_And_Security_Prod | 3899 | 104742 | Application | n/a | n/a | Production | us-east-1 | NA | indefinitely | y | Bronze
R02 | R02W02 | 6/04/2020 | 06/25/2020 |  | Production planning system | CUSMNA12 | Complete | cusmna12.carcgl.com | 159.82.226.141 | COMPLETE | Meriden | 2 | 8 | windows | Windows Server 2008 R2 Standard | Rehost | Alejandro Martinez, Arora Prateek | TBV | TBV | [8 empty] | 808538705328 | Fire_And_Security_Prod | m5.large | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.146 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | Production planning system | CUSMNA12 | n/a | Alejandro Martinez, Arora Prateek | Fire_And_Security_Prod | 3899 | 104742 | Application | n/a | n/a | Production | us-east-1 | NA | indefinitely | y | Bronze
R02 | R02W02 | 6/04/2020 | 06/25/2020 |  | Canon Printer Server | CUSMNA12 | Complete | cusmna12.carcgl.com | 159.82.226.141 | COMPLETE | Meriden | 2 | 8 | windows | Windows Server 2008 R2 Standard | Rehost | Alejandro Martinez, Arora Prateek | TBV | TBV | [8 empty] | 808538705328 | Fire_And_Security_Prod | m5.large | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.146 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | Canon Printer Server | CUSMNA12 | n/a | Alejandro Martinez, Arora Prateek | Fire_And_Security_Prod | 3899 | 104742 | Application | n/a | n/a | Production | us-east-1 | NA | indefinitely | y | Bronze
R02 | R02W01-DMZ | 6/18/2020 |  |  | CCS GSP Supra ADFS for SSO-STAGE | xmnt253 |  | xmnt253.utc.com | 167.17.243.50 | N/A | Meriden |  |  | windows | Microsoft Windows Server 2012 Standard R2 | Rehost | Kyle Shields, Jan Phillips | No | TBV | [8 empty] | 917128996017 | Fire_And_Security_PreProd |  | SSD | N/A | YES |  |  |  |  | N/A | AWSCloudWatchAgentRole | Fire_And_Security_PreProd_917128996017 | app | Stage | Shared | CCS GSP Supra ADFS for SSO-STAGE | xmnt253 | 1958 | Kyle Shields, Jan Phillips | Fire_And_Security_PreProd | CASS-SUPRA | IC990447 | Application | NA | NA | Stage | Us-east-1 | NA | indefinitely | y | Bronze
R02 | R02W01-DMZ | 6/18/2020 |  |  | CCS GSP Supra ADFS for SSO-STAGE | XMNT254 |  | xmnt254.carrier.utc.com |  | N/A | Meriden |  |  | windows | Microsoft Windows Server 2012 Standard R2 | Rehost | Kyle Shields, Jan Phillips | No | TBV | [8 empty] | 917128996017 | Fire_And_Security_PreProd |  | SSD | N/A | YES |  |  |  |  | N/A | AWSCloudWatchAgentRole | Fire_And_Security_PreProd_917128996017 | app | Stage | Shared | CCS GSP Supra ADFS for SSO-STAGE | XMNT254 | 1958 | Kyle Shields, Jan Phillips | Fire_And_Security_PreProd | CASS-SUPRA | IC990447 | Application | NA | NA | Stage | Us-east-1 | NA | indefinitely | y | Bronze
R02 | R02W02 | 6/04/2020 | 06/18/2020 |  | Mgmt Tools | CUSMNA1I | Complete | CUSMNA1I.carcgl.com | 159.82.227.3 | COMPLETE | Meriden | 8 | 32 | windows | Microsoft Windows Server 2016 Standard | Rehost | Guy Julian, Ed Amelchenko, Chintan Khambholja, Devon Varner | Yes | TBV | [8 empty] | 913828333602 | HVAC_Com_Prod | m5.2xlarge | SSD | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.17.141 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | Mgmt Tools | CUSMNA1I | 4615 | Guy Julian, Ed Amelchenko, Chintan Khambholja, Devon Varner | HVAC_Com_Prod | 9712 | 109712 | Application | NA | NA | PROD | Us-east-1 | NA | indefinitely | y | Bronze | complete | complete | complete | complete | complete | complete | complete | complete | 6/10/2020 | 6/10/2020 | 6/10/2020 | 6/11/2020 | 6/11/2020 | 6/11/2020 | 6/11/2020 | 6/13/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | Yet to Start - 18th June 2020 | Yet to Start - 18th June 2020
R02 | R02W01 | 6/04/2020 | 06/18/2020 |  | So99 | CUSMND01 | Complete | cusmnd01.carcgl.com | 159.82.226.23 | COMPLETE | Meriden | 8 | 32 | windows | Microsoft Windows Server 2016 Standard | Rehost | Jeff Turner | Yes | Yes | [8 empty] | 808538705328 | Fire_And_Security_Prod | m5.2xlarge | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.140 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | So99 | CUSMND01 | 5932 | Jeff Turner | Fire_And_Security_Prod | FS-00100 | IC990447 | Application | NA | NA | Production | us-east-1 | NA | indefinitely | y | Bronze | complete | complete | complete | complete | complete | complete | complete | complete | 6/10/2020 | 6/10/2020 | 6/10/2020 | 6/11/2020 | 6/11/2020 | 6/11/2020 | 6/11/2020 | 6/13/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | Yet to Start - 18th June 2020 | Yet to Start - 18th June 2020
R02 | R02W01 | 6/04/2020 | 06/18/2020 |  | KF - Dynamics CRM / FireEye | CUSMNA0W | Complete | CUSMNA0W.carcgl.com | 159.82.226.28 | COMPLETE | Meriden | 2 | 8 | windows | Microsoft Windows Server 2008 R2 Standard | Rehost | Scot Sanborn | Yes | Yes | [8 empty] | 808538705328 | Fire_And_Security_Prod | m5.large | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.141 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | KF - Dynamics CRM / FireEye | CUSMNA0W | 6167 | Scot Sanborn | Fire_And_Security_Prod | KFEN-14 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze | complete | complete | complete | complete | complete | complete | complete | complete | 6/10/2020 | 6/10/2020 | 6/10/2020 | 6/11/2020 | 6/11/2020 | 6/11/2020 | 6/11/2020 | 6/13/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | Yet to Start - 18th June 2020 | Yet to Start - 18th June 2020
R02 | R02W01-DMZ |  |  |  | ComfortChoice (MyTStat) | XMNT214 |  | XMNT214.utc.com | 167.17.243.14 | N/A | Meriden |  |  | windows | Microsoft Windows Server 2012 Standard R2 | Rehost | Syed, Mehmood Kozlowski, John E | No | TBV | [8 empty] | 890585303181 | Fire_And_Security_Dev |  | SSD | N/A | YES |  |  |  |  | N/A | AWSCloudWatchAgentRole | #ERROR! | app | dev | Shared | ComfortChoice (MyTStat) | XMNT214 | NA | Syed, Mehmood Kozlowski, John E | Fire_And_Security_Dev | 3525 | IC990447 | Application | NA | NA | Dev | us-east-1 | NA | indefinitely | y | Bronze
R02 | R02W01-DMZ |  |  |  | ComfortChoice (manager) | XMNT215 |  | XMNT215.utc.com | 167.17.243.53 | N/A | Meriden |  |  | windows | Microsoft Windows Server 2012 Standard R2 | Rehost | Syed, Mehmood Kozlowski, John E | No | TBV | [8 empty] | 890585303181 | Fire_And_Security_Dev |  | SSD | N/A | YES |  |  |  |  | N/A | AWSCloudWatchAgentRole | #ERROR! | app | dev | Shared | ComfortChoice (manager) | XMNT215 | NA | Syed, Mehmood Kozlowski, John E | Fire_And_Security_Dev | 3525 | IC990447 | Application | NA | NA | Dev | Us-east-1 | NA | indefinitely | y | Bronze
R02 | R02W01-DMZ |  |  |  | WHQ Engineering Newington (PTC InService) | XMNT245 |  | XMNT245.carrier.utc.com |  | N/A | Meriden |  |  | windows | Microsoft Windows Server 2012 Standard R2 | Rehost | John Macpherson, Sandra Trainer | No | TBV | [8 empty] | 823570924226 | HVAC_Res_Preprod |  | SSD | N/A | YES |  |  |  |  | N/A | AWSCloudWatchAgentRole | HVAC_Res_PreProd_823570924226 | app | Stage | Shared | WHQ Engineering Newington (PTC InService) | XMNT245 | NA | John Macpherson, Sandra Trainer | HVAC_Res_Preprod | 9230 | 109230 | Application | NA | NA | Stage | Us-east-1 | NA | indefinitely | y | Bronze
R02 | R02W03 | 6/04/2020 | 07/09/2020 |  | KF - DoubleTake | CUSMND0E | Migrating to VMC7222PA088 and will be decommissioed. Was Cutover and rolled back | CUSMND0E.carcgl.com | 159.82.226.87 | COMPLETE | Meriden | 2 | 16 | windows | Microsoft Windows Server 2008 R2 Standard | Rehost | Mauro Ciccarelli | Yes | Yes | [8 empty] | 808538705328 | Fire_And_Security_Prod | r5.large | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.143 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | KF - DoubleTake | CUSMND0E | 6157 | Mauro Ciccarelli | Fire_And_Security_Prod | FS-00103 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze | complete | complete | complete | complete | complete | complete | complete | complete | 6/10/2020 | 6/10/2020 | 6/10/2020 | 6/11/2020 | 6/11/2020 | 6/11/2020 | 6/11/2020 | 6/13/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | Yet to Start - 18th June 2020 | Yet to Start - 18th June 2020
R02 | add | 6/04/2020 | 07/15/2020 |  | Subversion Kidde/Edwards/GFP Subversion | CUSMNA0V | Boot-up Test Complete | cusmna0v.carcgl.com | 159.82.226.13 | COMPLETE | Meriden | 4 | 16 | windows | Microsoft Windows Server 2008 R2 Standard | Rehost | Jordan King | Yes | Yes | [8 empty] | 808538705328 | Fire_And_Security_Prod | m5.xlarge | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.142 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | Subversion Kidde/Edwards/GFP Subversion | CUSMNA0V | 7048. 1940 | Jordan King | Fire_And_Security_Prod | CASS-INTLX | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze | complete | complete | complete | complete | complete | complete | complete | complete | 6/10/2020 | 6/10/2020 | 6/10/2020 | 6/11/2020 | 6/11/2020 | 6/11/2020 | 6/11/2020 | 6/13/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | Yet to Start - 18th June 2020 | Yet to Start - 18th June 2020
R02 | thisweek | 6/04/2020 | 07/15/2020 |  | Automated Data ETL (SSIS & Other) | CUSMND0M | Replication in-progress | cusmnd0m.carcgl.com | 159.82.226.77 | COMPLETE | Meriden | 4 | 16 | windows | Windows Server 2008 R2 Enterprise | Rehost | Jeff Turner | TBV | TBV | [8 empty] | 808538705328 | Fire_And_Security_Prod | m5.xlarge | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.145 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | db | Production | Shared | Automated Data ETL (SSIS & Other) | CUSMND0M | 7018 | Jeff Turner | Fire_And_Security_Prod | IC990260 | IC990447 | DB | n/a | n/a | Production | us-east-1 | NA | indefinitely | y | Bronze
R02 | thisweek | 6/04/2020 | 07/15/2020 |  | Case Manager Web Application | CUSMND0M | Replication in-progress | cusmnd0m.carcgl.com | 159.82.226.77 | COMPLETE | Meriden | 4 | 16 | windows | Windows Server 2008 R2 Enterprise | Rehost | Jeff Turner | TBV | TBV | [8 empty] | 808538705328 | Fire_And_Security_Prod | m5.xlarge | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.145 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | db | Production | Shared | Case Manager Web Application | CUSMND0M | 7020 | Jeff Turner | Fire_And_Security_Prod | IC990260 | IC990447 | DB | n/a | n/a | Production | us-east-1 | NA | indefinitely | y | Bronze
R02 | R02W03 | 6/04/2020 | 07/22/2020 |  | JONAS - DR (AD validation issue) | CUSMNA1B | Boot-up Test Complete | cusmna12.carcgl.com | 159.82.226.66 | 0 | Meriden | 4 | 8 | windows | Windows Server 2008 R2 Standard | Rehost | Randy Durocher | TBV | TBV | [8 empty] | 913828333602 | HVAC_Com_Prod | c5.xlarge | SSD | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.17.142 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | JONAS - DR (AD validation issue) | CUSMNA1B | 6316 | Randy Durocher | HVAC_Com_Prod | 3899 | 104742 | DR | n/a | n/a | PROD | us-east-1 | NA | indefinitely | y | n/a
R02 | add | 6/04/2020 | 07/15/2020 |  | ComfortChoice | CUSMNW0E | Boot-up Test Complete | cusmnw0e.utccgl.com | 159.82.226.245 | COMPLETE | Meriden | 2 | 4 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Mehmood Syed and John Kozlowski | Yes | TBV | [8 empty] | 436524867280 | HVAC_Com_Dev | c5.large | SSD | N/A | YES | subnet-00a9966005a386acb | sg-0765e3df2626173e2 | sg-0c55b9769612daba9 | 10.233.137.140 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Dev_436524867280 | app | dev | Shared | ComfortChoice | CUSMNW0E | 7033 | Mehmood Syed and John Kozlowski | HVAC_Com_Dev | 3525 | IC990447 | Application | NA | NA | DEV | Us-east-1 | NA | indefinitely | y | Bronze | complete | complete | complete | complete | complete | complete | complete | complete | 6/10/2020 | 6/10/2020 | 6/10/2020 | 6/11/2020 | 6/11/2020 | 6/11/2020 | 6/11/2020 | 6/13/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | 6/18/2020 | Yet to Start - 18th June 2020 | Yet to Start - 18th June 2020
R02 | thisweek | 6/04/2020 | 07/15/2020 |  | EDI Support Site | CUSMND0M | Replication in-progress | cusmnd0m.carcgl.com | 159.82.226.77 | COMPLETE | Meriden | 4 | 16 | windows | Windows Server 2008 R2 Enterprise | Rehost | Jeff Turner | TBV | TBV | [8 empty] | 808538705328 | Fire_And_Security_Prod | m5.xlarge | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.145 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | db | Production | Shared | EDI Support Site | CUSMND0M | 7015 | Jeff Turner | Fire_And_Security_Prod | IC990260 | IC990447 | DB | n/a | n/a | Production | us-east-1 | NA | indefinitely | y | Bronze
R02 | thisweek | 6/04/2020 | 07/15/2020 |  | Kidde/Edwards Data Warehouse Reporting | CUSMND0M | Replication in-progress | cusmnd0m.carcgl.com | 159.82.226.77 | COMPLETE | Meriden | 4 | 16 | windows | Windows Server 2008 R2 Enterprise | Rehost | Jeff Turner | TBV | TBV | [8 empty] | 808538705328 | Fire_And_Security_Prod | m5.xlarge | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.145 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | db | Production | Shared | Kidde/Edwards Data Warehouse Reporting | CUSMND0M | 7034 | Jeff Turner | Fire_And_Security_Prod | IC990260 | IC990447 | DB | n/a | n/a | Production | us-east-1 | NA | indefinitely | y | Bronze
R02 | R02W02 | 6/04/2020 | 06/25/2020 |  | Case Manager Web Application | CUSMNK0O | Complete | cusmnd0l.carcgl.com | 159.82.226.112 | COMPLETE | Meriden | 1 | 8 | windows | Windows Server 2008 R2 Standard | Rehost | Jeff Turner | TBV | TBV | [8 empty] | 890585303181 | Fire_And_Security_Dev | m5.large | SSD | N/A | YES | subnet-0c6533ebaf5f1b1a2 | sg-05d2d8a7449289f9e | sg-09876514db5a00fb8 | 10.233.193.141 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Dev_890585303181 | db | Non Prod | Shared | Case Manager Web Application | CUSMNK0O | 7020 | Jeff Turner | Fire_And_Security_Dev | FS-00100 | IC990447 | DB | n/a | n/a | Production | us-east-1 | NA | indefinitely | y | Bronze
R02 | R02W02 | 6/04/2020 | 06/25/2020 |  | EDI Support Site | CUSMNK0O | Complete | cusmnd0l.carcgl.com | 159.82.226.112 | COMPLETE | Meriden | 1 | 8 | windows | Windows Server 2008 R2 Standard | Rehost | Jeff Turner | TBV | TBV | [8 empty] | 890585303181 | Fire_And_Security_Dev | m5.large | SSD | N/A | YES | subnet-0c6533ebaf5f1b1a2 | sg-05d2d8a7449289f9e | sg-09876514db5a00fb8 | 10.233.193.141 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Dev_890585303181 | db | Non Prod | Shared | EDI Support Site | CUSMNK0O | 7015 | Jeff Turner | Fire_And_Security_Dev | FS-00100 | IC990447 | DB | n/a | n/a | Production | us-east-1 | NA | indefinitely | y | Bronze
R02 | R02Plat |  |  |  | RCS Newington (BI 4) - QA | cusmnk17 |  | cusmnk17.carrier.utc.com | 159.82.226.238 | N/A | Meriden |  |  | linux | Linux - OEL 6.x | Replatform | Phillip Pascoe | No | TBV | [8 empty] | 823570924226 | HVAC_Res_Preprod |  | SSD | N/A | YES | subnet-034c5b1f10a32deaf | sg-0eb6d6c9b2ca6e16c | sg-044e1966a2ef361df | 10.233.145.140 | N/A | AWSCloudWatchAgentRole | HVAC_Res_PreProd_823570924226 | app | pre-prod | Shared | RCS Newington (BI 4) - QA | cusmnk17 |  | Phillip Pascoe | HVAC_Res_Preprod | CASS-INTLX | IC990447 | Application | NA | NA | pre-prod | Us-east-1 | NA | indefinitely | y | Bronze
R02 | R02Plat |  |  |  | RCS Newington (SAP DW) - QA | cusmnk17 |  | cusmnk17.carrier.utc.com | 159.82.226.238 | N/A | Meriden |  |  | linux | Linux - OEL 6.x | Replatform | Phillip Pascoe | No | TBV | [8 empty] | 823570924226 | HVAC_Res_Preprod |  | SSD | N/A | YES | subnet-034c5b1f10a32deaf | sg-0eb6d6c9b2ca6e16c | sg-044e1966a2ef361df | 10.233.145.141 | N/A | AWSCloudWatchAgentRole | HVAC_Res_PreProd_823570924226 | app | pre-prod | Shared | RCS Newington (SAP DW) - QA | cusmnk17 |  | Phillip Pascoe | HVAC_Res_Preprod | CASS-INTLX | IC990447 | Application | NA | NA | pre-prod | Us-east-1 | NA | indefinitely | y | Bronze
R02 | add | 5/27/2020 | 07/15/2020 |  | HVACNA-NPC-US-NAFS-TEST | CUSNWT0M | Boot-up Test Complete | cusnwt0m.carcgl.com | 159.82.100.145 | COMPLETE | Newington | 2 | 4 | windows | Microsoft Windows Server 2008 R2 Standard | Rehost | Tom Greco and Venu Reddy | Yes | Yes | [8 empty] | 260780007980 | HVAC_Com_Preprod | t2.large | SSD | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | sg-0cfa6a707d1ff7fe5 | 10.233.9.142 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Preprod_260780007980 | app | test | Shared | HVACNA-NPC-US-NAFS-TEST | CUSNWT0M | 6321 | Tom Greco and Venu Reddy | HVAC_Com_Preprod | 3899 | 104742 | Application | NA | NA | TST | us-east-1 | Weekdays | Indefinitely | y | Bronze | complete -26th May 2020 |  | Optional | complete - 27th May 2020 | complete - 27th May 2020 | In-Progress - 28th May 2020 | complete | Yet to Start - 1st June 2020 | complete | complete | complete | complete | complete | complete | complete | complete | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020 | Yet to Start - 11th June 2020
R02 | R02-DMZ |  |  |  | CCS GSP Supra ADFS for SSO | XMNP175 |  |  |  | N/A | Meriden |  |  |  | Microsoft Windows Server 2012 Standard R2 | Rehost | Kyle Shields, Jan Phillips | [13 empty] | SSD |  | YES |  |  |  |  | N/A | AWSCloudWatchAgentRole |  |  |  |  | CCS GSP Supra ADFS for SSO | XMNP175 |  | Kyle Shields, Jan Phillips | 0 | CASS-SUPRA | IC990447 | [7 empty] | y
R02 | R02-DMZ |  |  |  | WHQ (iListen - MFA) - Staging | XMNT232 |  |  |  | N/A | Meriden |  |  |  | Microsoft Windows Server 2012 Standard R2 | Rehost | Sunny Sangha / Ainsworth, Andrew | [13 empty] | SSD |  | YES |  |  |  |  | N/A | AWSCloudWatchAgentRole |  |  |  |  | WHQ (iListen - MFA) - Staging | XMNT232 |  | Sunny Sangha / Ainsworth, Andrew | 0 | IC990269 | IC990269-Int | [7 empty] | y
R02 | thisweek | 06/11/2020 | 07/15/2020 |  | MS Dynamics SL - TEST | CUSMNK0R | Boot-up Test Complete | CUSMNK0R.carcgl.com | 159.82.226.120 | COMPLETE | Meriden | 4 | 16 | windows | Windows ServerÂ® 2008 Enterprise | Replatform | Renee Brewer |  |  |  | 60 | 100 | 1 |  |  |  |  | 260780007980 | HVAC_Com_Preprod | m5.xlarge | SSD | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | sg-0cfa6a707d1ff7fe5 | 10.233.9.144 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Preprod_260780007980 | app | test | Shared | MS Dynamics SL - TEST | CUSMNK0R | NA | Renee Brewer | HVAC_Com_Preprod | 3899 | 104742 | Application | NA | NA | TST | us-east-1 | Weekdays | Indefinitely | y | Bronze
R02 | thisweek | 06/11/2020 | 07/15/2020 |  | MS Dynamics SL - TEST | CUSMNK0S | Boot-up Test Complete | CUSMNK0S.carcgl.com | 159.82.226.122 | COMPLETE | Meriden | 8 | 32 | windows | Windows Server 2008 R2 Standard | Rehost | Renee Brewer |  |  |  | 120 | 900 | 900 |  |  |  |  | 260780007980 | HVAC_Com_Preprod | m5.2xlarge | SSD | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | sg-0cfa6a707d1ff7fe5 | 10.233.9.145 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Preprod_260780007980 | app | test | Shared | MS Dynamics SL - TEST | CUSMNK0S | NA | Renee Brewer | HVAC_Com_Preprod | 3899 | 104742 | Application | NA | NA | TST | us-east-1 | Weekdays | Indefinitely | y | Bronze
R02 | thisweek | 06/11/2020 | 07/15/2020 |  | MS Dynamics SL - TEST | CUSMNK0T | Boot-up Test Complete | CUSMNK0T.carcgl.com | 159.82.226.121 | COMPLETE | Meriden | 4 | 16 | windows | Windows Server 2008 R2 Standard | Rehost | Renee Brewer |  |  |  | 60 | 100 | [5 empty] | 260780007980 | HVAC_Com_Preprod | m5.xlarge | SSD | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | sg-0cfa6a707d1ff7fe5 | 10.233.9.146 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Preprod_260780007980 | app | test | Shared | MS Dynamics SL - TEST | CUSMNK0T | NA | Renee Brewer | HVAC_Com_Preprod | 3899 | 104742 | Application | NA | NA | TST | us-east-1 | Weekdays | Indefinitely | y | Bronze
R02 | thisweek | 06/11/2020 | 07/15/2020 |  | MS Dynamics SL - TEST | CUSMNK0U | Boot-up Test Complete | CUSMNK0U.carcgl.com | 159.82.226.119 | COMPLETE | Meriden | 4 | 32 | windows | Windows Server 2008 R2 Standard | Rehost | Renee Brewer |  |  |  | 120 | 100 | [5 empty] | 260780007980 | HVAC_Com_Preprod | r5.xlarge | SSD | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | sg-0cfa6a707d1ff7fe5 | 10.233.9.147 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Preprod_260780007980 | app | test | Shared | MS Dynamics SL - TEST | CUSMNK0U | NA | Renee Brewer | HVAC_Com_Preprod | 3899 | 104742 | Application | NA | NA | TST | us-east-1 | Weekdays | Indefinitely | y | Bronze
R02 | thisweek | 06/11/2020 | 07/15/2020 |  | MS Dynamics SL - TEST | CUSMNK0V | Boot-up Test Complete | CUSMNK0V.carcgl.com | 159.82.226.123 | COMPLETE | Meriden | 4 | 16 | windows | Windows Server 2008 R2 Standard | Rehost | Renee Brewer |  |  |  | 60 | 100 | 250 |  |  |  |  | 260780007980 | HVAC_Com_Preprod | m5.xlarge | SSD | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | sg-0cfa6a707d1ff7fe5 | 10.233.9.148 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Preprod_260780007980 | app | test | Shared | MS Dynamics SL - TEST | CUSMNK0V | NA | Renee Brewer | HVAC_Com_Preprod | 3899 | 104742 | Application | NA | NA | TST | us-east-1 | Weekdays | Indefinitely | y | Bronze
R02 | thisweek | 06/11/2020 | 07/15/2020 |  | MS Dynamics SL - TEST | CUSMNK0W | Boot-up Test Complete | CUSMNK0W.carcgl.com | 159.82.226.124 | COMPLETE | Meriden | 4 | 4 | windows | Windows ServerÂ® 2008 Standard | Replatform | Renee Brewer |  |  |  | 60 | 100 | [5 empty] | 260780007980 | HVAC_Com_Preprod | c5.xlarge | SSD | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | sg-0cfa6a707d1ff7fe5 | 10.233.9.149 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Preprod_260780007980 | app | test | Shared | MS Dynamics SL - TEST | CUSMNK0W | NA | Renee Brewer | HVAC_Com_Preprod | 3899 | 104742 | Application | NA | NA | TST | us-east-1 | Weekdays | Indefinitely | y | Bronze
R02 | thisweek | 06/11/2020 | 07/15/2020 |  | MS Dynamics SL - TEST | CUSMNK19 | Boot-up Test Complete | CUSMNK19.carcgl.com | 159.82.226.65 | COMPLETE | Meriden | 4 | 16 | windows | Windows Server 2008 R2 Standard | Rehost | Renee Brewer |  |  |  | 72 | 900 | [5 empty] | 260780007980 | HVAC_Com_Preprod | m5.xlarge | SSD | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | sg-0cfa6a707d1ff7fe5 | 10.233.9.150 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Preprod_260780007980 | app | test | Shared | MS Dynamics SL - TEST | CUSMNK19 | NA | Renee Brewer | HVAC_Com_Preprod | ALC9-01-31 | 104742 | Application | NA | NA | TST | us-east-1 | Weekdays | Indefinitely | y | Bronze
R03 | R03W01 | 06/11/2020 | 07/09/2020 |  | HVACNA-WORKSOFT-IT-US-HVACRCS 10.0.0.995 | CUSNWD2T | Moving to Azure as of 5/21 | cusnwd2t.carcgl.com | 10.177.6.141 | 0 | Newington | 2 | 16 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Judy Zeman | Yes | No |  | 60.00 GB | 35.00 GB | 250.00 GB | 150.00 GB |  |  |  | 913828333602 | HVAC_Com_Prod | r5.large | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.10 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | HVACNA-WORKSOFT-IT-US-HVACRCS 10.0.0.995 | CUSNWD2T | 6346 | Judy Zeman | HVAC_Com_Prod | 4731 | 104742 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W04 | 06/11/2020 | 07/29/2020 |  | CCS GFP DOORs, DOORs Kidde/Edwards | CUSNWA6R | Boot-up Test Complete | cusnwa6r.carcgl.com | 10.177.6.113 | 0 | Newington | 2 | 6 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Jordan King | Yes | No |  | 48.00 GB | 200.00 GB | [5 empty] | 808538705328 | Fire_And_Security_Prod | m5.large | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.148 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | CCS GFP DOORs, DOORs Kidde/Edwards | CUSNWA6R | 7044. 1894 | Jordan King | Fire_And_Security_Prod | 0 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W04 | 06/11/2020 | 07/29/2020 |  | TRESS - Navojoa | KUSNWD17 | Boot-up Test Complete | kusnwd17.na.1utcfs.com | 159.82.103.193 | 0 | Newington | 2 | 2 | windows | Microsoft Windows Server 2008 R2 Standard | Rehost | Ismael Villarreal, Shreyes Bhatnagar, Rohit Malpekar, Alejandro Martinez, Oscar Aguilar | Yes | No |  | 92.00 GB |  | 130.00 GB |  |  |  |  | 913828333602 | HVAC_Com_Prod | c5.large | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.11 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | TRESS - Navojoa | KUSNWD17 | 6805 | Ismael Villarreal, Shreyes Bhatnagar, Rohit Malpekar, Alejandro Martinez, Oscar Aguilar | HVAC_Com_Prod | 9713 | 109713 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W04 | 06/11/2020 | 07/29/2020 |  | Subversion Kidde/Edwards | CUSNWA6Q | Boot-up Test Complete | CUSNWA6Q.carcgl.com | 10.177.6.112 | 0 | Newington | 4 | 16 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Jordan King | Yes | No |  | 60.00 GB | 1,994.00 GB | [5 empty] | 808538705328 | Fire_And_Security_Prod | m5.xlarge | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.149 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | Subversion Kidde/Edwards | CUSNWA6Q | 7048 | Jordan King | Fire_And_Security_Prod | CASS-INTLX | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | thisweek | 06/11/2020 | 07/15/2020 |  | MOODLE - Test | KUSNWD1I | Boot-up Test Complete | KUSNWD1I.carcgl.com | 159.82.94.41 | COMPLETE | Newington | 16 | 64 | windows | Microsoft Windows Server 2008 R2 Enterprise | Rehost | Timothy Kennedy | Yes | No |  | 68.33 GB | 68.33 GB | 25.00 GB | 250.00 GB | 75.00 GB |  |  | 808538705328 | Fire_And_Security_Prod | r5.2xlarge | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.150 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | MOODLE - Test | KUSNWD1I | 1856 | Timothy Kennedy | Fire_And_Security_Prod | CASS-EDWRD | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W01 | 06/11/2020 | 07/09/2020 |  | HPQC ALM12 F&S - Stag | CUSNWK1L | Complete | CUSNWK1L.utccgl.com | 10.177.6.199 | COMPLETE | Newington | 4 | 16 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Vinay Chandra | Yes | No |  | 72.00 GB | 400.00 GB | 400.00 GB |  |  |  |  | 260780007980 | HVAC_Com_PreProd | m5.xlarge | SSD | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | sg-0cfa6a707d1ff7fe5 | 10.233.9.151 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Preprod_260780007980 | app | Stage | Shared | HPQC ALM12 F&S - Stag | CUSNWK1L | NA | Vinay Chandra | HVAC_Com_PreProd | 9230 | 109230 | Application | NA | NA | Stage | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W01 | 06/11/2020 | 07/09/2020 |  | HPQC ALM12 F&S - Stag | CUSNWK1M | Complete | CUSNWK1M.chubbfsad.com | 10.177.6.202 | COMPLETE | Newington | 4 | 16 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Vinay Chandra | Yes | No |  | 72.00 GB | 900.00 GB | 400.00 GB |  |  |  |  | 260780007980 | HVAC_Com_PreProd | m5.xlarge | SSD | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | sg-0cfa6a707d1ff7fe5 | 10.233.9.152 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Preprod_260780007980 | app | Stage | Shared | HPQC ALM12 F&S - Stag | CUSNWK1M | NA | Vinay Chandra | HVAC_Com_PreProd | 9230 | 109230 | Application | NA | NA | Stage | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W01 | 06/11/2020 | 07/09/2020 |  | HPQC ALM12 F&S - Stag | CUSNWK1N | Complete | CUSNWK1N.chubbfsad.com | 10.177.6.200 | COMPLETE | Newington | 4 | 32 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Vinay Chandra | Yes | No |  | 72.00 GB | 1,300.00 GB | [5 empty] | 260780007980 | HVAC_Com_PreProd | r5.xlarge | SSD | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | sg-0cfa6a707d1ff7fe5 | 10.233.9.153 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Preprod_260780007980 | app | Stage | Shared | HPQC ALM12 F&S - Stag | CUSNWK1N | NA | Vinay Chandra | HVAC_Com_PreProd | 9230 | 109230 | Application | NA | NA | Stage | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W04 | 06/11/2020 | 07/29/2020 |  | HVACNA-DOCUSHARE-DOCH-US-NAFS 6 | CUSNWA33 | Replication in-progress | CUSNWA33.carcgl.com | 159.82.100.160 | 0 | Newington | 16 | 8 | windows | Microsoft Windows Server 2008 R2 Standard | Rehost | Tom Greco | Yes | No |  | 68.33 GB | 500.00 GB |  |  |  |  | 1,500.00 GB | 913828333602 | HVAC_Com_Prod | c5.4xlarge | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.12 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | HVACNA-DOCUSHARE-DOCH-US-NAFS 6 | CUSNWA33 | 6307 | Tom Greco | HVAC_Com_Prod | 3899 | 104742 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W04 | 06/11/2020 | 07/29/2020 |  | HVACNA-DOCUSHARE-DOCH-US-NAFS 6 | CUSNWA34 | Replication in-progress | CUSNWA34.carcgl.com | 159.82.100.159 | 0 | Newington | 16 | 16 | windows | Microsoft Windows Server 2008 R2 Standard | Rehost | Tom Greco | Yes | No |  | 68.33 GB | 999.87 GB | 1,000.00 GB |  |  |  |  | 913828333602 | HVAC_Com_Prod | c5.4xlarge | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.13 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | HVACNA-DOCUSHARE-DOCH-US-NAFS 6 | CUSNWA34 | 6307 | Tom Greco | HVAC_Com_Prod | 3899 | 104742 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W04 | 06/11/2020 | 07/29/2020 |  | HVACNA-DOCUSHARE-DOCH-US-NAFS 6 | CUSNWD13 | Replication in-progress | CUSNWD13.carcgl.com | 159.82.100.94 | 0 | Newington | 16 | 20 | windows | Microsoft Windows Server 2008 R2 Enterprise | Rehost | Tom Greco | Yes | No |  | 68 GB | 200 GB | 164 GB | 830 GB |  |  |  | 913828333602 | HVAC_Com_Prod | c5.4xlarge | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.14 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | HVACNA-DOCUSHARE-DOCH-US-NAFS 6 | CUSNWD13 | 6307 | Tom Greco | HVAC_Com_Prod | 3899 | 104742 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W04 | 06/11/2020 | 07/29/2020 |  | Confluence | CUSNWA51 | Boot-up Test Complete | cusnwa51.fs.utc.com | 159.82.94.179 | 0 | Newington | 4 | 16 | windows | Microsoft Windows Server 2008 R2 Standard | Rehost | Jordan King | Yes | No |  | 60.00 GB | 1,024.00 GB | [5 empty] | 808538705328 | Fire_And_Security_Prod | m5.xlarge | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.151 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | Confluence | CUSNWA51 | 7043 | Jordan King | Fire_And_Security_Prod | FS-00100 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W04 | 06/11/2020 | 07/29/2020 |  | AutoCAD Edwards | CUSNWA5Z | Boot-up Test Complete | cusnwa5z.fs.utc.com | 10.177.6.114 | 0 | Newington | 1 | 12 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Jordan King | Yes | No |  | 60.00 GB | 136.00 GB | [5 empty] | 808538705328 | Fire_And_Security_Prod | r5.large | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.152 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | AutoCAD Edwards | CUSNWA5Z | 7040 | Jordan King | Fire_And_Security_Prod | IC990260 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W04 | 06/11/2020 | 07/29/2020 |  | Code Collaborator | CUSNWA5Z | Boot-up Test Complete | cusnwa5z.fs.utc.com | 10.177.6.114 | 0 | Newington | 1 | 12 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Jordan King | Yes | No |  | 60.00 GB | 136.00 GB | [5 empty] | 808538705328 | Fire_And_Security_Prod | r5.large | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.152 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | Code Collaborator | CUSNWA5Z | 7049 | Jordan King | Fire_And_Security_Prod | IC990260 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W04 | 06/11/2020 | 07/29/2020 |  | indysoft Kidde/Edwards | CUSNWA5Z | Boot-up Test Complete | cusnwa5z.fs.utc.com | 10.177.6.114 | 0 | Newington | 1 | 12 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Jordan King, Chris Marshall | Yes | No |  | 60.00 GB | 136.00 GB | [5 empty] | 808538705328 | Fire_And_Security_Prod | r5.large | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.152 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | indysoft Kidde/Edwards | CUSNWA5Z | 7045 | Jordan King, Chris Marshall | Fire_And_Security_Prod | IC990260 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W04 | 06/11/2020 | 07/29/2020 |  | Mentor Graphics Kidde/Edwards | CUSNWA5Z | Boot-up Test Complete | cusnwa5z.fs.utc.com | 10.177.6.114 | 0 | Newington | 1 | 12 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Jordan King | Yes | No |  | 60.00 GB | 136.00 GB | [5 empty] | 808538705328 | Fire_And_Security_Prod | r5.large | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.152 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | Mentor Graphics Kidde/Edwards | CUSNWA5Z | 7046 | Jordan King | Fire_And_Security_Prod | IC990260 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W03 | 06/25/2020 | 07/22/2020 |  | Carrier Transicold Athens - IQR - PROD | CUSNWA70 | Ready to Test | CUSNWA70.carcgl.com | 10.177.6.225 | COMPLETE | Newington | 4 | 16 | windows | Windows Server 2016 Standard | Rehost | Mike Brunson | Yes | No |  | 70.67 GB | 300.00 GB | [5 empty] | 707766415800 | Refrigeration_Prod | m5.large | SSD | N/A | YES | subnet-077b7aa26f206e5d1 | sg-0281524ca4012fafb | sg-025b3ec92d0987576 | 10.233.25.141 | N/A | AWSCloudWatchAgentRole | Refrigeration_Prod_707766415800 | app | Production | Shared | Carrier Transicold Athens - IQR - PROD | CUSNWA70 | NA | Mike Brunson | Refrigeration_Prod | NA | NA | Application | NA | NA | Production | Us-east-1 | NA | N/A | y | Bronze
R03 | R03W03 | 06/25/2020 | 07/22/2020 |  | Carrier Transicold Athens - TMS - PROD | CUSNWA70 | Ready to Test | CUSNWA70.carcgl.com | 10.177.6.225 | COMPLETE | Newington | 4 | 16 | windows | Windows Server 2016 Standard | Rehost | Mike Brunson | Yes | No | [8 empty] | 707766415800 | Refrigeration_Prod | r5.large | SSD | N/A | YES | subnet-077b7aa26f206e5d1 | sg-0281524ca4012fafb | sg-025b3ec92d0987576 | 10.233.25.141 | N/A | AWSCloudWatchAgentRole | Refrigeration_Prod_707766415800 | app | Production | Shared | Carrier Transicold Athens - TMS - PROD | CUSNWA70 | NA | Mike Brunson | Refrigeration_Prod | NA | NA | Application | NA | NA | Production | Us-east-1 | NA | N/A | y | Bronze
R03 | R03W03 | 06/25/2020 | 07/22/2020 |  | CTDA - SOTI MobiControl | CUSNWA70 | Ready to Test | CUSNWA70.carcgl.com | 10.177.6.225 | COMPLETE | Newington | 4 | 16 | windows | Windows Server 2016 Standard | Rehost | Mike Brunson | Yes | No | [8 empty] | 707766415800 | Refrigeration_Prod | r5.large | SSD | N/A | YES | subnet-077b7aa26f206e5d1 | sg-0281524ca4012fafb | sg-025b3ec92d0987576 | 10.233.25.141 | N/A | AWSCloudWatchAgentRole | Refrigeration_Prod_707766415800 | app | Production | Shared | CTDA - SOTI MobiControl | CUSNWA70 | NA | Mike Brunson | Refrigeration_Prod | NA | NA | Application | NA | NA | Production | Us-east-1 | NA | N/A | y | Bronze
R03 | R03W03 | 06/25/2020 | 07/22/2020 |  | OMS - PROD | CUSNWA70 | Ready to Test | CUSNWA70.carcgl.com | 10.177.6.225 | COMPLETE | Newington | 4 | 16 | windows | Windows Server 2016 Standard | Rehost | Mike Brunson | Yes | [9 empty] | 707766415800 | Refrigeration_Prod | m5.xlarge | SSD | N/A | YES | subnet-077b7aa26f206e5d1 | sg-0281524ca4012fafb | sg-025b3ec92d0987576 | 10.233.25.141 | N/A | AWSCloudWatchAgentRole | Refrigeration_Prod_707766415800 | app | Production | Shared | OMS - PROD | CUSNWA70 | NA | Mike Brunson | Refrigeration_Prod | NA | NA | Application | NA | NA | Production | Us-east-1 | NA | N/A | y | Bronze
R03 | R03W03 | 06/25/2020 | 07/22/2020 |  | PC Scheduler | CUSNWA70 | Ready to Test | CUSNWA70.carcgl.com | 10.177.6.225 | COMPLETE | Newington | 4 | 16 | windows | Windows Server 2016 Standard | Rehost | Mike Brunson | Yes | [9 empty] | 707766415800 | Refrigeration_Prod | m5.xlarge | SSD | N/A | YES | subnet-077b7aa26f206e5d1 | sg-0281524ca4012fafb | sg-025b3ec92d0987576 | 10.233.25.141 | N/A | AWSCloudWatchAgentRole | Refrigeration_Prod_707766415800 | app | Production | Shared | PC Scheduler | CUSNWA70 | NA | Mike Brunson | Refrigeration_Prod | NA | NA | Application | NA | NA | Production | Us-east-1 | NA | N/A | y | Bronze
R03 | R03W03 | 06/11/2020 | 07/22/2020 |  | Doubletake PY | CUSMND0O | Boot-up Test Complete | cusmnd0o.carcgl.com | 159.82.227.128 | COMPLETE | Newington | 1 | 16 | windows | Microsoft Windows Server 2016 | Rehost | Jeff Turner, Chris Marshall | Yes | No |  | 70.67 GB | 1,000.00 GB | [5 empty] | 917128996017 | Fire_And_Security_PreProd | r5.large | SSD | N/A | YES | subnet-0dd905d5c0776f8ac | sg-0a08dc8c96199a489 | sg-0a08dc8c96199a489 | 10.233.153.143 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_PreProd_917128996017 | app | pre-prod | Shared | Doubletake PY | CUSMND0O | NA | Jeff Turner, Chris Marshall | Fire_And_Security_PreProd | FS-00100 | IC990447 | Application | NA | NA | Test | Us-east-1 | NA | indefinitely | y | Bronze
R03 | thisweek | 06/11/2020 | 07/15/2020 |  | Infrastructure servers | CUSNWW0U | Boot-up Test Complete | cusnww0u.carcgl.com | 159.82.91.85 | COMPLETE | Newington | 4 | 8 | windows | Windows Server 2008 R2 Standard | Rehost | RICH JOHNSTON | Yes | No |  | 36.00 GB | 50.00 GB | [5 empty] | 913828333602 | HVAC_Com_Prod | c5.xlarge | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.15 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | Infrastructure servers | CUSNWW0U | 9713 | RICH JOHNSTON | HVAC_Com_Prod | 9713 | 109713 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | thisweek | 06/11/2020 | 07/15/2020 |  | Infrastructure servers | CUSNWW1C | Boot-up Test Complete | CUSNWW1C.carcgl.com | 159.82.94.99 | COMPLETE | Newington | 2 | 2 | windows | Windows Server 2008 R2 Standard | Rehost | RICH JOHNSTON | Yes | No |  | 60.00 GB |  |  | 76.00 GB |  |  |  | 913828333602 | HVAC_Com_Prod | c5.xlarge | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.16 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | Infrastructure servers | CUSNWW1C | 9713 | RICH JOHNSTON | HVAC_Com_Prod | 9713 | 109713 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W01 | 06/11/2020 | 07/09/2020 |  | Kronos 7.x | CUSNWK0A | Complete | CUSNWK0A.carcgl.com | 159.82.61.136 | COMPLETE | Newington | 2 | 16 | windows | Windows Server 2008 R2 Standard | Rehost | Mike Brunson | Yes | No |  | 72.00 GB | 40.00 GB | 50.00 GB |  |  |  |  | 15623844436 | Refrigeration_PreProd | r5.large | SSD | N/A | YES | subnet-0688f427d6de70fe9 | sg-0947ed90c16e965c3 | sg-025b3ec92d0987576 | 10.233.149.140 | N/A | AWSCloudWatchAgentRole | Refrigeration_PreProd_15623844436 | app | pre-prod | Shared | Kronos 7.x | CUSNWK0A | NA | Mike Brunson | Refrigeration_PreProd | NA | IC990236 | Application | NA | NA | Pre-prod | Us-east-1 | NA | indefinitely | y | Bronze
R03 | thisweek | 06/18/2020 | 07/15/2020 |  | Webtime and HRIS - Prod | CUSNWA2A | Boot-up Test Complete | CUSNWA2A.carcgl.com | 10.177.6.165 | COMPLETE | Newington | 2 | 4 | windows | Microsoft Windows Server 2016 Standard | Rehost | Venkatagopi Somaraju, James D McGill | Yes |  |  | 58.79 GB | 250.00 GB | [5 empty] | 913828333602 | HVAC_Com_Prod | c5.large | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.18 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | Webtime and HRIS - Prod | CUSNWA2A | 6868 | Venkatagopi Somaraju, James D McGill | HVAC_Com_Prod | 9755 | 109755 | Application | NA | NA | NA | Us-east-1 | NA | NA | y | Bronze
R03 | R03W04 | 06/18/2020 | 07/29/2020 |  | CCS Windchill Product Analytics - Prod | CUSNWA7Z | Boot-up Test Complete | cusnwa7z.utccgl.com | 10.177.6.125 | 0 | Newington | 8 | 16 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | John Macpherson | Yes |  |  | 72.00 GB | 150.00 GB | [5 empty] | 808538705328 | Fire_And_Security_Prod | c5.2xlarge | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.154 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | CCS Windchill Product Analytics - Prod | CUSNWA7Z | 4637 | John Macpherson | Fire_And_Security_Prod | 9230 | 109230 | Application | NA | NA | Production | Us-east-1 | NA | NA | y | Bronze
R03 | R03W04 | 06/18/2020 | 07/29/2020 |  | CCS Windchill Product Analytics - Prod | CUSNWA80 | Boot-up Test Complete | CUSNWA80.utccgl.com | 159.82.61.146 | 0 | Newington | 8 | 16 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | John Macpherson | Yes |  |  | 72.00 GB | 500.00 GB | 18.00 GB | 50.00 GB |  | 4.00 GB |  | 808538705328 | Fire_And_Security_Prod | c5.2xlarge | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.155 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | CCS Windchill Product Analytics - Prod | CUSNWA80 | 4637 | John Macpherson | Fire_And_Security_Prod | 9230 | 109230 | Application | NA | NA | Production | Us-east-1 | NA | NA | y | Bronze
R03 | R03W04 | 06/18/2020 | 07/29/2020 |  | IBM Jazz Continuous Integration Server adapters for PIC software development projects | CUSNWA35 | Boot-up Test Complete | CUSNWA35.carcgl.com | 10.177.6.143 | 0 | Newington | 2 | 16 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | McGaughey, Peter Chopra, Puja Victor Yevtukh | Yes | No |  | 72.00 GB | 200.00 GB | [5 empty] | 913828333602 | HVAC_Com_Prod | r5.large | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.17 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | IBM Jazz Continuous Integration Server adapters for PIC software development projects | CUSNWA35 | NA | McGaughey, Peter Chopra, Puja Victor Yevtukh | HVAC_Com_Prod | 9230 | 109230 | Application | NA | NA | Production | Us-east-1 | NA | NA | y | Bronze
R03 | thisweek | 06/18/2020 | 07/15/2020 |  | ICP Lewisburg - SQL 2012 - Application: SAS | CUSNWD2G | Boot-up Test Complete | cusnwd2g.carrier.utc.com | 10.177.6.103 | COMPLETE | Newington | 4 | 16 | windows | Windows Server 2012 R2 Standard | Rehost | Oran Wray | Yes |  |  | 60.00 GB | 1,000.00 GB | [5 empty] | 501143608669 | HVAC_Res_Prod | m5.xlarge | SSD | N/A | YES | subnet-0d2c10f3c6ae2fece | sg-0d09f9d12ffec86b1 | sg-04fe3038a54e44e4d | 10.233.21.140 | N/A | AWSCloudWatchAgentRole | HVAC_Res_Prod_501143608669 | app | Production | Shared | ICP Lewisburg - SQL 2012 - Application: SAS | CUSNWD2G | NA | Oran Wray | HVAC_Res_Prod | 1351 | 105675 | Application | NA | NA | Production | Us-east-1 | NA | NA | y | Bronze
R03 | thisweek | 06/18/2020 | 07/15/2020 |  | NOR Newforma (dev) | CUSNWK0N | Boot-up Test Complete | CUSNWK0N.carcgl.com | 10.177.6.159 | COMPLETE | Newington | 2 | 8 | windows | Windows Server 2012 R2 Standard | Rehost | Ferdinand Schmid | Yes | TBV |  | 48.00 GB | 20.00 GB | [5 empty] | 424277870443 | HVAC_Res_Dev | m5.large | SSD | N/A | YES | subnet-01be3d7f1fda2f9eb | sg-07b8b2aabbd558bee | sg-0ecaaa208c3e967d4 | 10.233.141.140 | N/A | AWSCloudWatchAgentRole | HVAC_Res_Dev_424277870443 | app | Production | Shared | NOR Newforma (dev) | CUSNWK0N | NA | Ferdinand Schmid | HVAC_Res_Dev | 150015900 | 104742 | Application | NA | NA | Pre-prod | Us-east-1 | NA | NA | y | Bronze
R03 | R03W04 | 06/18/2020 | 07/29/2020 |  | WHQ Engineering Newington (0001) - ARBORTEXT | CUSNWA3Z | Boot-up Test Complete | CUSNWA3Z.carcgl.com | 10.177.6.177 | 0 | Newington | 8 | 24 | windows | Windows Server 2012 R2 Standard | Rehost | John Macpherson | Yes | No |  | 72.00 GB | 100.00 GB | [5 empty] | 917128996017 | Fire_And_Security_PreProd | m5.2xlarge | SSD | N/A | YES | subnet-0dd905d5c0776f8ac | sg-0a08dc8c96199a489 | sg-0104099b41897670f | 10.233.153.144 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_PreProd_917128996017 | app | Production | Shared | WHQ Engineering Newington (0001) - ARBORTEXT | CUSNWA3Z | N/A | John Macpherson | Fire_And_Security_PreProd | NA | NA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | y | N/A
R03 | R03W04 | 06/18/2020 | 07/29/2020 |  | WHQ Engineering Newington (0001) - CORE LICENSING MANAGER | CUSNWA3K | Boot-up Test Complete | CUSNWA3K.carcgl.com | 159.82.100.16 | 0 | Newington | 2 | 2 | windows | Windows Server 2008 R2 Standard | Rehost | John Macpherson | Yes | No |  | 36.00 GB | 50.00 GB | [5 empty] | 913828333602 | HVAC_Com_Prod | c5.large | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.19 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | WHQ Engineering Newington (0001) - CORE LICENSING MANAGER | CUSNWA3K | N/A | John Macpherson | HVAC_Com_Prod | NA | NA | N/A | N/A | N/A | Production | Us-east-1 | N/A | N/A | y | N/A
R03 | R03W04 | 06/18/2020 | 07/29/2020 |  | WHQ Engineering Newington (0001) - ESR | CUSNWA6F | Boot-up Test Complete | CUSNWA6F.carcgl.com | 10.177.6.23 | 0 | Newington | 4 | 16 | windows | Windows Server 2012 R2 Standard | Rehost | John Macpherson | Yes | No |  | 72.00 GB | 300.00 GB | [5 empty] | 913828333602 | HVAC_Com_Prod | m5.xlarge | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.20 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | WHQ Engineering Newington (0001) - ESR | CUSNWA6F | N/A | John Macpherson | HVAC_Com_Prod | NA | NA | N/A | N/A | N/A | Production | Us-east-1 | N/A | N/A | y | N/A
R03 | R03W04 | 06/18/2020 | 07/29/2020 |  | WHQ Engineering Newington (0001) - GRANTA | CUSNWA42 | Boot-up Test Complete | CUSNWA42.carcgl.com | 159.82.100.212 | 0 | Newington | 16 | 20 | windows | Windows Server 2008 R2 Standard | Rehost | John Macpherson | Yes | No |  | 68.33 GB | 558.73 GB | [5 empty] | 913828333602 | HVAC_Com_Prod | c5.4xlarge | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.21 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | WHQ Engineering Newington (0001) - GRANTA | CUSNWA42 | N/A | John Macpherson | HVAC_Com_Prod | NA | NA | N/A | N/A | N/A | Production | Us-east-1 | N/A | N/A | y | N/A
R03 | thisweek | 06/18/2020 | 07/15/2020 |  | WHQ Engineering Newington (0001) - IN SERVICE | CUSNWK1I | Boot-up Test Complete | CUSNWK1I.carcgl.com | 10.177.6.175 | COMPLETE | Newington | 8 | 32 | windows | Windows Server 2012 R2 Standard | Rehost | John Macpherson | Yes | No |  | 72.00 GB | 100.00 GB | 500.00 GB |  |  |  |  | 917128996017 | Fire_And_Security_PreProd | m5.2xlarge | SSD | N/A | YES | subnet-0dd905d5c0776f8ac | sg-0a08dc8c96199a489 | sg-0104099b41897670f | 10.233.153.145 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_PreProd_917128996017 | app | Production | Shared | WHQ Engineering Newington (0001) - IN SERVICE | CUSNWK1I | NA | John Macpherson | Fire_And_Security_PreProd | 9230 | 109230 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | y | N/A
R03 | thisweek | 06/18/2020 | 07/15/2020 |  | WHQ Engineering Newington (0001) - IN SERVICE | CUSNWK1J | Boot-up Test Complete | CUSNWK1J.carcgl.com | 10.177.6.176 | COMPLETE | Newington | 8 | 32 | windows | Windows Server 2012 R2 Standard | Rehost | John Macpherson | Yes | No |  | 72.00 GB | 100.00 GB | 200.00 GB |  |  |  |  | 917128996017 | Fire_And_Security_PreProd | r5.2xlarge | SSD | N/A | YES | subnet-0dd905d5c0776f8ac | sg-0a08dc8c96199a489 | sg-0104099b41897670f | 10.233.153.146 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_PreProd_917128996017 | app | Production | Shared | WHQ Engineering Newington (0001) - IN SERVICE | CUSNWK1J | NA | John Macpherson | Fire_And_Security_PreProd | 9230 | 109230 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | y | N/A
R03 | thisweek | 06/18/2020 | 07/15/2020 |  | WHQ Engineering Newington (0001) - NAVIGATE | CUSNWA7S | Boot-up Test Complete | CUSNWA7S.carcgl.com | 10.177.6.179 | COMPLETE | Newington | 8 | 32 | windows | Windows Server 2012 R2 Standard | Rehost | John Macpherson | Yes | No |  | 72.00 GB | 100.00 GB | 200.00 GB |  |  |  |  | 913828333602 | HVAC_Com_Prod | r5.2xlarge | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.22 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | WHQ Engineering Newington (0001) - NAVIGATE | CUSNWA7S | NA | John Macpherson | HVAC_Com_Prod | 9230 | 109230 | N/A | N/A | N/A | Production | Us-east-1 | N/A | N/A | y | N/A
R03 | R03W04 | 06/18/2020 | 07/29/2020 |  | WHQ Engineering Newington (0001) - PART LISTER | CUSNWA79 | Pending Agent Install | cusnwa79.carrier.utc.com | 10.177.6.116 | 0 | Newington | 2 | 32 | linux | Linux - Red Hat 6.x | Rehost | John Macpherson | No | No | [8 empty] | 913828333602 | HVAC_Com_Prod | r5.xlarge | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.23 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | WHQ Engineering Newington (0001) - PART LISTER | CUSNWA79 | N/A | John Macpherson | HVAC_Com_Prod | 9230 | 109230 | N/A | N/A | N/A | Production | Us-east-1 | N/A | N/A | y | N/A
R03 | R03W04 | 06/18/2020 | 07/29/2020 |  | WHQ Engineering Newington (0001) - SVN | CUSNWA5D | Boot-up Test Complete | CUSNWA5D.carcgl.com | 159.82.100.65 | 0 | Newington | 4 | 8 | windows | Windows Server 2008 R2 Standard | Rehost | John Macpherson | Yes | No |  | 48.00 GB | 500.00 GB | [5 empty] | 913828333602 | HVAC_Com_Prod | r5.large | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.24 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | WHQ Engineering Newington (0001) - SVN | CUSNWA5D | N/A | John Macpherson | HVAC_Com_Prod | NA | NA | N/A | N/A | N/A | Production | Us-east-1 | N/A | N/A | y | N/A
R03 | R03W04 | 06/18/2020 | 07/29/2020 |  | WHQ Engineering Newington (0001) - TESTS / TEAMS | CUSNWA42 | Boot-up Test Complete | CUSNWA42.carcgl.com | 159.82.100.212 | 0 | Newington | 16 | 20 | windows | Windows Server 2008 R2 Standard | Rehost | John Macpherson | Yes | No |  | 68.33 GB | 558.73 GB | [5 empty] | 913828333602 | HVAC_Com_Prod | c5.4xlarge | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.21 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | WHQ Engineering Newington (0001) - TESTS / TEAMS | CUSNWA42 | N/A | John Macpherson | HVAC_Com_Prod | NA | NA | N/A | N/A | N/A | Production | Us-east-1 | N/A | N/A | y | N/A
R03 | R03W04 | 06/18/2020 | 07/29/2020 |  | WHQ Engineering Newington (0001) - WQS | CUSNWA6D | Boot-up Test Complete | CUSNWA6D.carcgl.com | 10.177.6.97 | 0 | Newington | 2 | 4 | windows | Windows Server 2012 R2 Standard | Rehost | John Macpherson | Yes | No |  | 48.00 GB | 150.00 GB | [5 empty] | 808538705328 | Fire_And_Security_Prod | c5.large | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.156 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | WHQ Engineering Newington (0001) - WQS | CUSNWA6D | N/A | John Macpherson | Fire_And_Security_Prod | NA | NA | N/A | N/A | N/A | Production | N/A | N/A | N/A | y | N/A
R03 | R03W04 | 06/18/2020 | 07/29/2020 |  | HVACNA-STARTRAC-US-NAFS | CUSNWA4Y | Boot-up Test Complete | cusnwa4y.carrier.utc.com | 159.82.100.93 | 0 | Newington | 4 | 8 | windows | Microsoft Windows Server 2008 R2 Standard | Rehost | Tom Greco, Kathy Remillard | Yes |  |  | 111.00 GB | 200.00 GB | [5 empty] | 913828333602 | HVAC_Com_Prod | r5.large | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.27 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | HVACNA-STARTRAC-US-NAFS | CUSNWA4Y | N/A | Tom Greco, Kathy Remillard | HVAC_Com_Prod | 3899 | 104742 | Application | N/A | N/A | Production | Us-east-1 | N/A | N/A | y | Bronze
R03 | R03W04 | 06/18/2020 | 07/29/2020 |  | HVACNA-STARTRAC-US-NAFS | CUSNWD1Q | Boot-up Test Complete | cusnwd1q.carrier.utc.com | 159.82.100.28 | 0 | Newington | 4 | 8 | windows | Microsoft Windows Server 2008 R2 Standard | Rehost | Tom Greco, Kathy Remillard | Yes |  |  | 300 GB | 350 GB | 310 GB | 50 GB |  |  |  | 913828333602 | HVAC_Com_Prod | c5.large | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.28 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | db | Production | Shared | HVACNA-STARTRAC-US-NAFS | CUSNWD1Q | N/A | Tom Greco, Kathy Remillard | HVAC_Com_Prod | 3899 | 104742 | Database | N/A | N/A | Production | Us-east-1 | N/A | N/A | y | Bronze
R03 | R03W04 | 06/18/2020 | 07/29/2020 |  | HVACNA-STARTRAC-US-NAFS | CUSNWD1W | Boot-up Test Complete | cusnwd1w.carrier.utc.com | 159.82.100.100 | 0 | Newington | 4 | 8 | windows | Microsoft Windows Server 2008 R2 Standard | Rehost | Tom Greco, Kathy Remillard | Yes |  |  | 105.00 GB | 200.00 GB | [5 empty] | 913828333602 | HVAC_Com_Prod | r5.large | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.29 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | db | Production | Shared | HVACNA-STARTRAC-US-NAFS | CUSNWD1W | N/A | Tom Greco, Kathy Remillard | HVAC_Com_Prod | 3899 | 104742 | Database | N/A | N/A | Production | Us-east-1 | N/A | N/A | y | Bronze
R03 | R03W04 | 06/11/2020 | 07/29/2020 |  | Code Collaborator | CUSNWA7E | Boot-up Test Complete | CUSNWA7E.utccgl.com | 10.177.6.163 | 0 | Newington | 4 | 16 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Jordan King | Yes | No |  | 72.00 GB | 500.00 GB | [5 empty] | 808538705328 | Fire_And_Security_Prod | m5.xlarge | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.153 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | Code Collaborator | CUSNWA7E | 7049 | Jordan King | Fire_And_Security_Prod | FS-00100 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W04 | 06/11/2020 | 07/29/2020 |  | Confluence | CUSNWA7E | Boot-up Test Complete | CUSNWA7E.utccgl.com | 10.177.6.163 | 0 | Newington | 4 | 16 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Jordan King | Yes | No |  | 72.00 GB | 500.00 GB | [5 empty] | 808538705328 | Fire_And_Security_Prod | m5.xlarge | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.153 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | Confluence | CUSNWA7E | 7043 | Jordan King | Fire_And_Security_Prod | FS-00100 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W03 | 06/25/2020 | 07/22/2020 |  | aPriori - Prod | CUSNWD0O | Ready to Test | CUSNWD0O.carcgl.com | 10.177.6.212 | 0 | Newington | 2 | 6 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Satyam Bendapudi | Yes | No |  | 60.00 GB | 1,020.00 GB | 20.00 GB | 10.00 GB |  |  |  | 913828333602 | HVAC_Com_Prod | m5.large | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.36 | N/A | AWSCloudWatchAgentRole | CENTRAL Research & Development | db | Production | Shared | aPriori - Prod | CUSNWD0O | NA | Satyam Bendapudi | HVAC_Com_Prod | 9230 | 109230 | Database | NA | NA | Production | Us-east-1 | NA | N/A | y | Bronze
R03 | R03W03 | 06/25/2020 | 07/22/2020 |  | aPriori - Prod | CUSNWW1L | Ready to Test | CUSNWW1L.UTCCGL.COM | 10.177.6.213 | 0 | Newington | 4 | 16 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Satyam Bendapudi | Yes | No | [8 empty] | 913828333602 | HVAC_Com_Prod | m5.xlarge | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.37 | N/A | AWSCloudWatchAgentRole | CENTRAL Research & Development | app | Production | Shared | aPriori - Prod | CUSNWW1L | NA | Satyam Bendapudi | HVAC_Com_Prod | 9230 | 109230 | Application | NA | NA | Production | Us-east-1 | NA | N/A | y | Bronze
R03 | R03W04 | 06/11/2020 | 07/29/2020 |  | SolidEdge Kidde/Edwards | CUSNWA7E | Boot-up Test Complete | CUSNWA7E.utccgl.com | 10.177.6.163 | 0 | Newington | 4 | 16 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Jordan King | Yes | No |  | 72.00 GB | 500.00 GB | [5 empty] | 808538705328 | Fire_And_Security_Prod | m5.xlarge | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.153 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | SolidEdge Kidde/Edwards | CUSNWA7E | 7042 | Jordan King | Fire_And_Security_Prod | FS-00100 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W04 | 06/18/2020 | 07/29/2020 |  | Doku Wiki documentation | CUSNWA7O | Boot-up Test Complete | CUSNWA7O.utccgl.com | 10.177.6.118 | 0 | Newington | 1 | 2 | windows | Windows Server 2012 R2 Standard | Rehost | Julien Dupre, Kristian Tuszynski, Christophe Lecourvreur | Yes |  |  | 60.00 GB | 450.00 GB | [5 empty] | 913828333602 | HVAC_Com_Prod | c5.large | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.30 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | Doku Wiki documentation | CUSNWA7O | N/A | Julien Dupre, Kristian Tuszynski, Christophe Lecourvreur | HVAC_Com_Prod | 9230 | 109230 | Application | N/A | N/A | Production | Us-east-1 | N/A | N/A | y | Bronze
R03 | R03W04 | 06/18/2020 | 07/29/2020 |  | WHQ Engineering Newington (SVN server for Standard Design) | CUSNWA7O | Boot-up Test Complete | CUSNWA7O.utccgl.com | 10.177.6.118 | 0 | Newington | 1 | 2 | windows | Windows Server 2012 R2 Standard | Rehost | Julien Dupre, Kristian Tuszynski, Christophe Lecourvreur | Yes |  |  | 60.00 GB | 450.00 GB | [5 empty] | 913828333602 | HVAC_Com_Prod | c5.large | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.30 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | WHQ Engineering Newington (SVN server for Standard Design) | CUSNWA7O | N/A | Julien Dupre, Kristian Tuszynski, Christophe Lecourvreur | HVAC_Com_Prod | 9230 | 109230 | Application | N/A | N/A | Production | Us-east-1 | N/A | N/A | y | Bronze
R03 | R03W01 | 06/11/2020 | 07/09/2020 |  | Carrier Transicold Athens - IQR - DEV | CUSNWK09 | Complete | CUSNWK09.carcgl.com | 10.177.6.164 | COMPLETE | Newington | 4 | 16 | windows | Windows Server 2016 Standard | Rehost | Mike Brunson | Yes | No |  | 70.67 GB | 300.00 GB | [5 empty] | 707766415800 | Refrigeration_Prod | m5.xlarge | SSD | N/A | YES | subnet-077b7aa26f206e5d1 | sg-0281524ca4012fafb | sg-025b3ec92d0987576 | 10.233.25.140 | N/A | AWSCloudWatchAgentRole | Refrigeration_Prod_707766415800 | app | Production | Shared | Carrier Transicold Athens - IQR - DEV | CUSNWK09 | 9028 | Mike Brunson | Refrigeration_Prod | 8193 | IC990236 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W01 | 06/11/2020 | 07/09/2020 |  | Carrier Transicold Athens - TMS - DEV | CUSNWK09 | Complete | CUSNWK09.carcgl.com | 10.177.6.164 | COMPLETE | Newington | 4 | 16 | windows | Windows Server 2016 Standard | Rehost | Mike Brunson | Yes | No |  | 70.67 GB | 300.00 GB | [5 empty] | 707766415800 | Refrigeration_Prod | m5.xlarge | SSD | N/A | YES | subnet-077b7aa26f206e5d1 | sg-0281524ca4012fafb | sg-025b3ec92d0987576 | 10.233.25.140 | N/A | AWSCloudWatchAgentRole | Refrigeration_Prod_707766415800 | app | Production | Shared | Carrier Transicold Athens - TMS - DEV | CUSNWK09 | 9029 | Mike Brunson | Refrigeration_Prod | 8193 | IC990236 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W03 | 06/25/2020 | 07/22/2020 |  | HPQC ALM12 F&S - Prod | CUSNWA7K | Ready to Test | CUSNWA7K.chubbfsad.com | 10.177.6.201 | 0 | Newington | 4 | 16 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Vinay Chandra | Yes | No |  | 72.00 GB | 900.00 GB | 400.00 GB |  |  |  |  | 913828333602 | HVAC_Com_Prod | m5.xlarge | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.31 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | HPQC ALM12 F&S - Prod | CUSNWA7K | NA | Vinay Chandra | HVAC_Com_Prod | 9230 | 109230 | Application | NA | NA | Production | Us-east-1 | NA | N/A | y | Bronze
R03 | R03W03 | 06/25/2020 | 07/22/2020 |  | HPQC ALM12 F&S - Prod | CUSNWA7V | Ready to Test | CUSNWA7V.chubbfsad.com | 10.177.6.204 | 0 | Newington | 4 | 32 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Vinay Chandra | Yes | No |  | 72.00 GB | 1,300.00 GB | [5 empty] | 913828333602 | HVAC_Com_Prod | r5.xlarge | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.32 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | HPQC ALM12 F&S - Prod | CUSNWA7V | NA | Vinay Chandra | HVAC_Com_Prod | 9230 | 109230 | Application | NA | NA | Production | Us-east-1 | NA | N/A | y | Bronze
R03 | R03W03 | 06/25/2020 | 07/22/2020 |  | HPQC ALM12 F&S - Prod | CUSNWA7W | Ready to Test | CUSNWA7W.chubbfsad.com | 10.177.6.203 | 0 | Newington | 4 | 16 | windows | Microsoft Windows Server 2012 R2 Standard | Rehost | Vinay Chandra | Yes | No |  | 72.00 GB | 400.00 GB | 400.00 GB |  |  |  |  | 913828333602 | HVAC_Com_Prod | m5.xlarge | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.33 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | HPQC ALM12 F&S - Prod | CUSNWA7W | NA | Vinay Chandra | HVAC_Com_Prod | 9230 | 109230 | Application | NA | NA | Production | Us-east-1 | NA | N/A | y | Bronze
R03 | R03W03 | 06/25/2020 | 07/22/2020 |  | FSS Fireye (4777) - HELIX (engeeniring) - Prod | CUSNWA5Y | Ready to Test | CUSNWA5Y.carcgl.com | 10.177.6.195 | COMPLETE | Newington | 2 | 8 | windows | Microsoft Windows Server 2016 Standard | Rehost | Scot Sanborn | Yes | No |  | 58.79 GB | 1,024.00 GB | [5 empty] | 808538705328 | Fire_And_Security_Prod | m5.large | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.157 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | FSS Fireye (4777) - HELIX (engeeniring) - Prod | CUSNWA5Y | NA | Scot Sanborn | Fire_And_Security_Prod | FS-00497 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W03 | 06/25/2020 | 07/22/2020 |  | FSS Fireye (4777) - KRONOS - Prod | CUSNWA77 | Ready to Test | cusnwa77.fs.utc.com | 159.82.100.223 | 0 | Newington | 6 | 8 | windows | Windows Server 2008 R2 Standard | Rehost | Scot Sanborn | Yes | No |  | 278.87 GB | 278.87 GB | [5 empty] | 808538705328 | Fire_And_Security_Prod | c5.2xlarge | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.158 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | FSS Fireye (4777) - KRONOS - Prod | CUSNWA77 | NA | Scot Sanborn | Fire_And_Security_Prod | FS-00497 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W03 | 06/25/2020 | 07/22/2020 |  | FSS Kidde Fenwal DC (0001 9888) Kronos Database - Prod | CUSNWA53 | Ready to Test | cusnwa53.fs.utc.com | 159.82.100.228 | 0 | Newington | 2 | 12 | windows | Microsoft Windows Server 2008 R2 Standard | Rehost | Scot Sanborn | Yes | No |  | 48.00 GB | 200.00 GB | [5 empty] | 808538705328 | Fire_And_Security_Prod | m5.xlarge | SSD | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | sg-03d765951f2e6d249 | 10.233.29.159 | N/A | AWSCloudWatchAgentRole | Fire_And_Security_Prod_808538705328 | app | Production | Shared | FSS Kidde Fenwal DC (0001 9888) Kronos Database - Prod | CUSNWA53 | NA | Scot Sanborn | Fire_And_Security_Prod | FS-00103 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W03 | 06/25/2020 | 07/22/2020 |  | RCD Carrier Newington (0001) - Prod | CUSNWK0W | Ready to Test | CUSNWK0W.carcgl.com | 159.82.100.222 | 0 | Newington | 8 | 8 | windows | Windows Server 2008 R2 Standard | Rehost | David Mannfeld | Yes |  |  | 136.70 GB | 250.00 GB | 125.00 GB |  |  |  |  | 501143608669 | HVAC_Res_Prod | c5.2xlarge | SSD | N/A | YES | subnet-0d2c10f3c6ae2fece | sg-0d09f9d12ffec86b1 | sg-04fe3038a54e44e4d | 10.233.21.141 | N/A | AWSCloudWatchAgentRole | HVAC_Res_Prod_501143608669 | app | Production | Shared | RCD Carrier Newington (0001) - Prod | CUSNWK0W | NA | David Mannfeld | HVAC_Res_Prod | 6220 | 104742 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | y | Bronze
R03 | R03W03 | 06/25/2020 | 07/22/2020 |  | Printer server for SAP cloud - standalone server | CUSNWA3E | Ready to Test | cusnwa3e.carrier.utc.com | 159.82.100.175 | 0 | Newington | 4 | 8 | windows | Windows Server 2008 R2 Standard | Rehost | Tom Greco | Yes |  |  | 36.00 GB | 100.00 GB | [5 empty] | 913828333602 | HVAC_Com_Prod | c5.xlarge | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.34 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | Printer server for SAP cloud - standalone server | CUSNWA3E | NA | Tom Greco | HVAC_Com_Prod | 3899 | 104742 | Application | NA | NA | Production | Us-east-1 | NA | Indefinitely | y | Bronze
R03 | R03W03 | 06/25/2020 | 07/22/2020 |  | JONAS SERVER - PROD | CUSNWA75 | Ready to Test | CUSNWA75.carcgl.com | 10.177.6.128 | 0 | Newington | 4 | 8 | windows | Windows Server 2012 R2 Standard | Rehost | Randy Durocher, Ezhil Nanjappan | Yes |  |  | 60.00 GB | 200.00 GB | [5 empty] | 913828333602 | HVAC_Com_Prod | c5.xlarge | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.38 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | JONAS SERVER - PROD | CUSNWA75 | NA | Randy Durocher, Ezhil Nanjappan | HVAC_Com_Prod | 3899 | 104742 | Application | NA | NA | Production | Us-east-1 | NA | Indefinitely | y | Bronze
R03 | R03W03 | 06/25/2020 | 07/22/2020 |  | JONAS LB VIP SERVER - PROD | CUSNWT0R | Ready to Test | CUSNWT0R.carcgl.com | 10.177.6.89 | 0 | Newington | 2 | 4 | windows | Windows Server 2008 R2 Standard | Rehost | Randy Durocher | Yes |  |  | 70.00 GB | 50.00 GB | [5 empty] | 913828333602 | HVAC_Com_Prod | c5.large | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.39 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | JONAS LB VIP SERVER - PROD | CUSNWT0R | NA | Randy Durocher | HVAC_Com_Prod | 3899 | 104742 | Application | NA | NA | Production | Us-east-1 | NA | Indefinitely | y | Bronze
R03 | R03W03 | 06/25/2020 | 07/22/2020 |  | JONAS LB VIP SERVER - PROD | CUSNWT0S | Ready to Test | CUSNWT0S.carcgl.com | 10.177.6.90 | 0 | Newington | 2 | 4 | windows | Windows Server 2008 R2 Standard | Rehost | Randy Durocher | Yes |  |  | 70.00 GB | 50.00 GB | [5 empty] | 913828333602 | HVAC_Com_Prod | c5.large | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.40 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | JONAS LB VIP SERVER - PROD | CUSNWT0S | NA | Randy Durocher | HVAC_Com_Prod | 3899 | 104742 | Application | NA | NA | Production | Us-east-1 | NA | Indefinitely | y | Bronze
R03 | R03W03 | 06/25/2020 | 07/22/2020 |  | AIR HANDLING ORDERING SYSTEM - PROD | CUSNWA4R | Replication in-progress | cusnwa4r.carrier.utc.com | 159.82.100.57 | 0 | Newington | 32 | 16 | windows | Windows Server 2008 R2 Standard | Rehost | John Boffemmyer | Yes |  |  | 136.12 GB | 480.00 GB | 10.00 GB | 60.00 GB |  |  |  | 913828333602 | HVAC_Com_Prod | c5.9xlarge | SSD | N/A | YES | subnet-0372249a8b0030547 | sg-06e849287c4603b7d | sg-07d38644ed9df7a61 | 10.233.18.35 | N/A | AWSCloudWatchAgentRole | HVAC_Com_Prod_913828333602 | app | Production | Shared | AIR HANDLING ORDERING SYSTEM - PROD | CUSNWA4R | NA | John Boffemmyer | HVAC_Com_Prod | 6203 | 104742 | Application | NA | NA | Production | Us-east-1 | NA | Indefinitely | y | Bronze
R03 | R03W03 | 06/25/2020 | 07/22/2020 |  | Starlite | CUSNWA4K | Ready to Test | cusnwa4k.carrier.utc.com | 159.82.100.192 | 0 | Newington | 1 | 4 | windows | Windows Server 2008 R2 Standard | Rehost | Laura Berndt | Yes |  |  | 36.00 GB | 100.00 GB | [5 empty] | 707766415800 | Refrigeration_Prod | c5.large | SSD | N/A | YES | subnet-077b7aa26f206e5d1 | sg-0281524ca4012fafb | sg-025b3ec92d0987576 | 10.233.25.142 | N/A | AWSCloudWatchAgentRole | Refrigeration_Prod_707766415800 | app | Production | Shared | Starlite | CUSNWA4K | NA | Laura Berndt | Refrigeration_Prod | 1088 | 105675 | Application | SOX COMPLIANCE | NA | Production | Us-east-1 | NA | Indefinitely | y | Bronze
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | Dantimer | CFRRYD0J | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2008 R2 Enterprise | Rehost | Ricardo Font-De-Campos | [11 empty] | Carrier Transicold Italy |  | SSD |  | YES | [7 empty] | db | Production |  | Dantimer | CFRRYD0J |  | Ricardo Font-De-Campos | Carrier Transicold Italy | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | Dantimer | CFRRYT01 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Ricardo Font-De-Campos | [13 empty] | SSD |  | YES | [7 empty] | app | Production |  | Dantimer | CFRRYT01 |  | Ricardo Font-De-Campos | 0 | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | Abel | CFRRYD0J | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2008 R2 Enterprise | Rehost | Ricardo Font-De-Campos | [11 empty] | Carrier Transicold Industrie |  | SSD |  | YES | [7 empty] | db | Production |  | Abel | CFRRYD0J |  | Ricardo Font-De-Campos | Carrier Transicold Industrie | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | Abel | CFRRYT01 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Ricardo Font-De-Campos | [13 empty] | SSD |  | YES | [7 empty] | app | Production |  | Abel | CFRRYT01 |  | Ricardo Font-De-Campos | 0 | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | AltiumDB | CFRRYW0M | Region Build Pending |  |  | 0 | Roissy |  |  | RedHat | Linux Server 7 Red Hat ES 7.5 | Rehost | Marc Springthorpe-Rose | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | db | Production |  | AltiumDB | CFRRYW0M |  | Marc Springthorpe-Rose | Fire and Security | [9 empty] | y
R04 | R04W05 | 2020-09-09 | 2020-10-07 |  | Apriso Environment Montluel - DEV | CFRRYD1R | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | rehost | Giuseppe Larovere, Eric Daniele, Amaury Deroche | [11 empty] | HVAC_Com_Dev | HVAC_Com_Dev_436524867280 | SSD |  | YES | [6 empty] | HVAC_Com_Dev_436524867280 | db | Dev |  | Apriso Environment Montluel - DEV | CFRRYD1R |  | Giuseppe Larovere, Eric Daniele, Amaury Deroche | HVAC_Com_Dev | [9 empty] | y
R04 | R04W05 | 2020-09-09 | 2020-10-07 |  | Apriso Environment Montluel - DEV | CFRRYW0P | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | rehost | Giuseppe Larovere, Eric Daniele, Amaury Deroche | [11 empty] | HVAC_Com_Dev |  | SSD |  | YES | [6 empty] | HVAC_Com_Dev_436524867280 | app | Dev |  | Apriso Environment Montluel - DEV | CFRRYW0P |  | Giuseppe Larovere, Eric Daniele, Amaury Deroche | HVAC_Com_Dev | [9 empty] | y
R04 | R04W05 | 2020-09-09 | 2020-10-07 |  | Apriso Environment Montluel - TEST | CFRRYA5G | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | rehost | Giuseppe Larovere, Eric Daniele, Amaury Deroche | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | app | Test |  | Apriso Environment Montluel - TEST | CFRRYA5G |  | Giuseppe Larovere, Eric Daniele, Amaury Deroche | Commercial HVAC | [9 empty] | y
R04 | R04W05 | 2020-09-09 | 2020-10-07 |  | Apriso Environment Montluel - TEST | CFRRYD1R | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | rehost | Giuseppe Larovere, Eric Daniele, Amaury Deroche | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | db | Test |  | Apriso Environment Montluel - TEST | CFRRYD1R |  | Giuseppe Larovere, Eric Daniele, Amaury Deroche | Commercial HVAC | [9 empty] | y
R04 | R04W05 | 2020-09-09 | 2020-10-07 |  | Apriso Environment Montluel - TEST | CFRRYW0O | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | rehost | Giuseppe Larovere, Eric Daniele, Amaury Deroche | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | app | Test |  | Apriso Environment Montluel - TEST | CFRRYW0O |  | Giuseppe Larovere, Eric Daniele, Amaury Deroche | Commercial HVAC | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | BIS R1: Chubb France iSales | CFRRYA1Z | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Mathieu Bailly, JEAN-CHARLES MOISAN | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Test |  | BIS R1: Chubb France iSales | CFRRYA1Z |  | Mathieu Bailly, JEAN-CHARLES MOISAN | Fire and Security | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | BIS R1: Chubb France iSales | CFRRYD0I | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Mathieu Bailly | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | db | Test |  | BIS R1: Chubb France iSales | CFRRYD0I |  | Mathieu Bailly | Fire and Security | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | BIS R1: Chubb France iSales | CFRRYW08 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Mathieu Bailly | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | web | Test |  | BIS R1: Chubb France iSales | CFRRYW08 |  | Mathieu Bailly | Fire and Security | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | BIS R1: Chubb France JDE Formscape | CFRRYA0U | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | mathieu bailly | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Test |  | BIS R1: Chubb France JDE Formscape | CFRRYA0U |  | mathieu bailly | Fire and Security | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | CCR - ATOSS | CFRRYD1J | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Richard Mohr-Bonome | [11 empty] | Refrigeration |  | SSD |  | YES | [7 empty] | app | Production |  | CCR - ATOSS | CFRRYD1J |  | Richard Mohr-Bonome | Refrigeration | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | CCR - PAISY | CFRRYD1J | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Josef Berger, Sabine Ilg, Jiri Jirsa | [11 empty] | Refrigeration |  | SSD |  | YES | [7 empty] | db | Production |  | CCR - PAISY | CFRRYD1J |  | Josef Berger, Sabine Ilg, Jiri Jirsa | Refrigeration | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | CTD Italy Prezence | CFRRYD0J | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2008 R2 Enterprise | Rehost | Ricardo Font-De-Campos | [11 empty] | Carrier Transicold Italy |  | SSD |  | YES | [7 empty] | db | Production |  | CTD Italy Prezence | CFRRYD0J |  | Ricardo Font-De-Campos | Carrier Transicold Italy | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | CTD Italy Prezence | CFRRYT01 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Ricardo Font-De-Campos | [11 empty] | Carrier Transicold Italy |  | SSD |  | YES | [7 empty] | app | Production |  | CTD Italy Prezence | CFRRYT01 |  | Ricardo Font-De-Campos | Carrier Transicold Italy | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | Custom Develop System - Tracking System | CFRRYA4V | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Gareth Ellson / Marc Springthorpe-Rose | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | db | Production |  | Custom Develop System - Tracking System | CFRRYA4V |  | Gareth Ellson / Marc Springthorpe-Rose | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | DCFlex | CFRRYA1A | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Hakan Erturk | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Production |  | DCFlex | CFRRYA1A |  | Hakan Erturk | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | EFACS - Manufacturing ERP | CFRRYA4I | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Marc Springthorpe-Rose | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | db | Production |  | EFACS - Manufacturing ERP | CFRRYA4I |  | Marc Springthorpe-Rose | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | EMS Tracking System -Manufacturing Quality & Control System | CFRRYW0I | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Marc Springthorpe-Rose | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Production |  | EMS Tracking System -Manufacturing Quality & Control System | CFRRYW0I |  | Marc Springthorpe-Rose | Fire and Security | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | e-procurement 1.2 | CFRRYD0J | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2008 R2 Enterprise | Rehost | Jean-Charles MOISAN, Christine LEMAOU | [11 empty] | Refrigeration |  | SSD |  | YES | [7 empty] | db | Production |  | e-procurement 1.2 | CFRRYD0J |  | Jean-Charles MOISAN, Christine LEMAOU | Refrigeration | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | e-procurement 1.2 | CFRRYD0M | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Jean-Charles MOISAN, Christine LEMAOU | [11 empty] | Refrigeration |  | SSD |  | YES | [7 empty] | db | Test |  | e-procurement 1.2 | CFRRYD0M |  | Jean-Charles MOISAN, Christine LEMAOU | Refrigeration | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | e-procurement 1.2 | CFRRYW01 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Jean-Charles MOISAN, Christine LEMAOU | [11 empty] | Refrigeration |  | SSD |  | YES | [7 empty] | app | Test |  | e-procurement 1.2 | CFRRYW01 |  | Jean-Charles MOISAN, Christine LEMAOU | Refrigeration | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | e-procurement 1.2 | CFRRYW02 | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Jean-Charles MOISAN, Christine LEMAOU | [11 empty] | Refrigeration |  | SSD |  | YES | [7 empty] | app | Production |  | e-procurement 1.2 | CFRRYW02 |  | Jean-Charles MOISAN, Christine LEMAOU | Refrigeration | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | FRD Germany IBM Cognos - PROD | CFRRYA4U | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Sabine Ilg | [11 empty] | Refrigeration |  | SSD |  | YES | [7 empty] | app | Production |  | FRD Germany IBM Cognos - PROD | CFRRYA4U |  | Sabine Ilg | Refrigeration | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | FRD Germany IBM Cognos - PROD | CFRRYD1J | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Sabine Ilg | [11 empty] | Refrigeration |  | SSD |  | YES | [7 empty] | db | Production |  | FRD Germany IBM Cognos - PROD | CFRRYD1J |  | Sabine Ilg | Refrigeration | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | FRD Germany Lenel OnGuard | CFRRYA4L | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Sabine Ilg | [11 empty] | Refrigeration |  | SSD |  | YES | [7 empty] | app | Production |  | FRD Germany Lenel OnGuard | CFRRYA4L |  | Sabine Ilg | Refrigeration | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | FRD Germany Lenel OnGuard | CFRRYA4K | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Sabine Ilg | [11 empty] | Refrigeration |  | SSD |  | YES | [7 empty] | app | Production |  | FRD Germany Lenel OnGuard | CFRRYA4K |  | Sabine Ilg | Refrigeration | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | FRD Switzerland OfficeWings | CFRRYA48 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Sabine Ilg | [11 empty] | Refrigeration |  | SSD |  | YES | [7 empty] | app | Production |  | FRD Switzerland OfficeWings | CFRRYA48 |  | Sabine Ilg | Refrigeration | [9 empty] | y
R04 | R04W01 | 2020-08-12 | 2020-09-09 |  | FSP EMEA - NetPresenter | CFRRYW0F | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Sancho Beerens | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | FSP EMEA - NetPresenter | CFRRYW0F |  | Sancho Beerens | FIRE AND SECURITY | [9 empty] | y
R04 | R04W01 | 2020-08-12 | 2020-09-09 |  | FSP EMEA (Peterconnect) | CFRRYA45 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Sancho Beerens | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | FSP EMEA (Peterconnect) | CFRRYA45 |  | Sancho Beerens | FIRE AND SECURITY | [9 empty] | y
R04 | R04W01 | 2020-08-12 | 2020-09-09 |  | FSP EMEA (Printerlogic) | CFRRYP05 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Sancho Beerens | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | FSP EMEA (Printerlogic) | CFRRYP05 |  | Sancho Beerens | FIRE AND SECURITY | [9 empty] | y
R04 | R04W01 | 2020-08-12 | 2020-09-09 |  | FSP EMEA (Wallboards) IIS - web server | CFRRYW0F | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Sancho Beerens | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | FSP EMEA (Wallboards) IIS - web server | CFRRYW0F |  | Sancho Beerens | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | GitLab 10.7.3 | CFRRYA54 | Region Build Pending |  |  | 0 | Roissy |  |  | RedHat | Linux Server 7 Red Hat ES 7.5 | Rehost | Marc Springthorpe-Rose | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | db | Production |  | GitLab 10.7.3 | CFRRYA54 |  | Marc Springthorpe-Rose | Fire and Security | [9 empty] | y
R04 | R04W02 | 2020-08-19 | 2020-09-16 |  | HVAC BNL - BAAN4 ERP - PROD | CFRRYA4M | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Dirk van der Plas | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | db | Production |  | HVAC BNL - BAAN4 ERP - PROD | CFRRYA4M |  | Dirk van der Plas | Commercial HVAC | [9 empty] | y
R04 | R04W02 | 2020-08-19 | 2020-09-16 |  | HVAC BNL - BAAN4 ERP - PROD | CFRRYD1G | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Dirk van der Plas | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | db | Production |  | HVAC BNL - BAAN4 ERP - PROD | CFRRYD1G |  | Dirk van der Plas | Commercial HVAC | [9 empty] | y
R04 | R04W01 | 2020-08-12 | 2020-09-09 |  | HVAC BNL - BAAN4 ERP - TEST | CFRRYA4R | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Dirk Van Der Plas, Eric Daniele, Amaury Deroche, Sue Davies, Giuseppe Larovere | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | app | Test |  | HVAC BNL - BAAN4 ERP - TEST | CFRRYA4R |  | Dirk Van Der Plas, Eric Daniele, Amaury Deroche, Sue Davies, Giuseppe Larovere | Commercial HVAC | [9 empty] | y
R04 | R04W02 | 2020-08-19 | 2020-09-16 |  | HVAC BNL - Navision ERP - PROD | CFRRYA52 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Dirk van der Plas | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | app | Production |  | HVAC BNL - Navision ERP - PROD | CFRRYA52 |  | Dirk van der Plas | Commercial HVAC | [9 empty] | y
R04 | R04W01 | 2020-08-12 | 2020-09-09 |  | HVAC-BENELUX - TEST | CFRRYA4P | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Dirk van der Plas, Patrick De Bie, Nathaly Werleman | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | app | TEST |  | HVAC-BENELUX - TEST | CFRRYA4P |  | Dirk van der Plas, Patrick De Bie, Nathaly Werleman | Commercial HVAC | [9 empty] | y
R04 | R04W02 | 2020-08-19 | 2020-09-16 |  | HVAC-BENELUX-20/20 Vision - PROD | CFRRYA4N | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Sergi Angelet, Dirk van der Plas, Prasad Mangle | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | db | Production |  | HVAC-BENELUX-20/20 Vision - PROD | CFRRYA4N |  | Sergi Angelet, Dirk van der Plas, Prasad Mangle | Commercial HVAC | [9 empty] | y
R04 | R04W02 | 2020-08-19 | 2020-09-16 |  | HVAC-BENELUX-20/20 Vision - PROD | CFRRYD1G | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Sergi Angelet, Dirk van der Plas, Prasad Mangle | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | db | Production |  | HVAC-BENELUX-20/20 Vision - PROD | CFRRYD1G |  | Sergi Angelet, Dirk van der Plas, Prasad Mangle | Commercial HVAC | [9 empty] | y
R04 | R04W02 | 2020-08-19 | 2020-09-16 |  | HVAC-BENELUX-20/20 Vision - PROD | CFRRYW0J | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Sergi Angelet, Dirk van der Plas, Prasad Mangle | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | db | Production |  | HVAC-BENELUX-20/20 Vision - PROD | CFRRYW0J |  | Sergi Angelet, Dirk van der Plas, Prasad Mangle | Commercial HVAC | [9 empty] | y
R04 | R04W01 | 2020-08-12 | 2020-09-09 |  | HVAC-BENELUX-20/20 Vision - TEST | CFRRYD1H | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Sergi Angelet, Dirk van der Plas, Prasad Mangle | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | app | TEST |  | HVAC-BENELUX-20/20 Vision - TEST | CFRRYD1H |  | Sergi Angelet, Dirk van der Plas, Prasad Mangle | Commercial HVAC | [9 empty] | y
R04 | R04W02 | 2020-08-19 | 2020-09-16 |  | HVAC-BENELUX-EasyArchive - PROD | CFRRYA4Q | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Dirk van der Plas, Nathaly Werleman | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | app | Production |  | HVAC-BENELUX-EasyArchive - PROD | CFRRYA4Q |  | Dirk van der Plas, Nathaly Werleman | Commercial HVAC | [9 empty] | y
R04 | R04W02 | 2020-08-19 | 2020-09-16 |  | HVAC-BENELUX-iMOS - PROD | CFRRYA4O | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Dirk van der Plas, Patrick De Bie, Nathaly Werleman | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | app | Production |  | HVAC-BENELUX-iMOS - PROD | CFRRYA4O |  | Dirk van der Plas, Patrick De Bie, Nathaly Werleman | Commercial HVAC | [9 empty] | y
R04 | R04W01 | 2020-08-12 | 2020-09-09 |  | HVAC-BENELUX-iMOS - TEST | CFRRYA4S | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Dirk Van Der Plas | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | app | Production |  | HVAC-BENELUX-iMOS - TEST | CFRRYA4S |  | Dirk Van Der Plas | Commercial HVAC | [9 empty] | y
R04 | R04W02 | 2020-08-19 | 2020-09-16 |  | HVAC-BENELUX-ORP - PROD | CFRRYD1G | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Dirk van der Plas, Nathaly Werleman | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | db | Production |  | HVAC-BENELUX-ORP - PROD | CFRRYD1G |  | Dirk van der Plas, Nathaly Werleman | Commercial HVAC | [9 empty] | y
R04 | R04W02 | 2020-08-19 | 2020-09-16 |  | HVAC-BENELUX-ORP - PROD | CFRRYT14 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Dirk van der Plas, Nathaly Werleman | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | db | Production |  | HVAC-BENELUX-ORP - PROD | CFRRYT14 |  | Dirk van der Plas, Nathaly Werleman | Commercial HVAC | [9 empty] | y
R04 | R04W02 | 2020-08-19 | 2020-09-16 |  | HVAC-BENELUX-ORP - PROD | CFRRYW0J | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Dirk van der Plas, Nathaly Werleman | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | db | Production |  | HVAC-BENELUX-ORP - PROD | CFRRYW0J |  | Dirk van der Plas, Nathaly Werleman | Commercial HVAC | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | HVAC-UK-GOLDVISION | CFRRYD25 | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows 2016 Standard | Rehost | Rohit Malpekar, Shreyes Bhatnagar, Sergi Angelet, Dave Watson, Carly Booth, Prasad Mangle, Nayan Bane, Nilesh Rane | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | db | Production |  | HVAC-UK-GOLDVISION | CFRRYD25 |  | Rohit Malpekar, Shreyes Bhatnagar, Sergi Angelet, Dave Watson, Carly Booth, Prasad Mangle, Nayan Bane, Nilesh Rane | Commercial HVAC | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | iBank | CNLRDA02 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Patrick Kooderings Clemens | [11 empty] | Refrigeration |  | SSD |  | YES | [7 empty] | app | Production |  | iBank | CNLRDA02 |  | Patrick Kooderings Clemens | Refrigeration | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | IBM Cognos | CFRRYA18 | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Hakan Erturk | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Production |  | IBM Cognos | CFRRYA18 |  | Hakan Erturk | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | IBM Cognos | CFRRYA1B | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Hakan Erturk | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Production |  | IBM Cognos | CFRRYA1B |  | Hakan Erturk | Fire and Security | [9 empty] | y
R04 | R04W02 | 2020-08-19 | 2020-09-16 |  | InspHire Office | CFRRYT15 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Dirk Van Der Plas | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | db | Production |  | InspHire Office | CFRRYT15 |  | Dirk Van Der Plas | Commercial HVAC | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | IPB (Invision) | CFRRYW0M | Region Build Pending |  |  | 0 | Roissy |  |  | RedHat | Linux Server 7 Red Hat ES 7.5 | Rehost | Marc Springthorpe-Rose | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | db | Production |  | IPB (Invision) | CFRRYW0M |  | Marc Springthorpe-Rose | Fire and Security | [9 empty] | y
R04 | R04W01 | 2020-08-12 | 2020-09-09 |  | Mail Attachment DownLoader | CFRRYA44 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Gareth Ellson | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | Mail Attachment DownLoader | CFRRYA44 |  | Gareth Ellson | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | MS Dynamics CRM 2016 | CFRRYA3D | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Primary: Dave Watson, Secondary: Giuseppe Larovere | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | app | Production |  | MS Dynamics CRM 2016 | CFRRYA3D |  | Primary: Dave Watson, Secondary: Giuseppe Larovere | Commercial HVAC | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | MS Dynamics CRM 2016 | CFRRYA3G | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Primary: Dave Watson, Secondary: Giuseppe Larovere | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | app | Production |  | MS Dynamics CRM 2016 | CFRRYA3G |  | Primary: Dave Watson, Secondary: Giuseppe Larovere | Commercial HVAC | [9 empty] | y
R04 | R04W07 | 2020-09-23 | 2020-10-21 |  | MS Dynamics CRM 2016 | CFRRYK09 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Primary: Dave Watson, Secondary: Giuseppe Larovere | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | db | Production |  | MS Dynamics CRM 2016 | CFRRYK09 |  | Primary: Dave Watson, Secondary: Giuseppe Larovere | Commercial HVAC | [9 empty] | y
R04 | R04W07 | 2020-09-23 | 2020-10-21 |  | MS Dynamics CRM 2016 | CFRRYK0A | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Primary: Dave Watson, Secondary: Giuseppe Larovere | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | db | Production |  | MS Dynamics CRM 2016 | CFRRYK0A |  | Primary: Dave Watson, Secondary: Giuseppe Larovere | Commercial HVAC | [9 empty] | y
R04 | R04W07 | 2020-09-23 | 2020-10-21 |  | MS Dynamics CRM 2016 | CFRRYK0B | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Primary: Dave Watson, Secondary: Giuseppe Larovere | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | db | Production |  | MS Dynamics CRM 2016 | CFRRYK0B |  | Primary: Dave Watson, Secondary: Giuseppe Larovere | Commercial HVAC | [9 empty] | y
R04 | R04W02 | 2020-08-19 | 2020-09-16 |  | Multivers (CRM) | CFRRYT16 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Dirk Van Der Plas | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | app | Production |  | Multivers (CRM) | CFRRYT16 |  | Dirk Van Der Plas | Commercial HVAC | [9 empty] | y
R04 | R04W05 | 2020-09-09 | 2020-10-07 |  | Navision Financials - R4 Carrier Poland (Microsoft Dynamics NAV) | CFRRYA3Q | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Dominik Birus, Piotr Bunkowski | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | db | Production |  | Navision Financials - R4 Carrier Poland (Microsoft Dynamics NAV) | CFRRYA3Q |  | Dominik Birus, Piotr Bunkowski | Commercial HVAC | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | Ontime 17 | CFRRYA4Z | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Marc Springthorpe-Rose | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | db | Production |  | Ontime 17 | CFRRYA4Z |  | Marc Springthorpe-Rose | Fire and Security | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | Paisy 4x | CFRRYK0G | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Richard Mohr-Bonome | [11 empty] | Refrigeration |  | SSD |  | YES | [7 empty] | app | Test |  | Paisy 4x | CFRRYK0G |  | Richard Mohr-Bonome | Refrigeration | [9 empty] | y
R04 | R04W01 | 2020-08-12 | 2020-09-09 |  | Perforce | CFRRYA1R | Region Build Pending |  |  | 0 | Roissy |  |  | RedHat | Linux Server 6 Red Hat ES 6 Santiago6.4 | Rehost | Gareth Ellson | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | Perforce | CFRRYA1R |  | Gareth Ellson | FIRE AND SECURITY | [9 empty] | y
R04 | R04W06 | 2020-09-16 | 2020-10-14 |  | PHP+MySQL | CFRRYA4A | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Primary: Dave Watson, Secondary: Jon Pugh | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | app | Test |  | PHP+MySQL | CFRRYA4A |  | Primary: Dave Watson, Secondary: Jon Pugh | Commercial HVAC | [9 empty] | y
R04 | R04W07 | 2020-09-23 | 2020-10-21 |  | PHP+MySQL | CFRRYD12 | Region Build Pending |  |  | 0 | Roissy |  |  | RedHat | Red Hat Enterprise Linux Server 7.4 | Rehost | Primary: Dave Watson, Secondary: Jon Pugh | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | db | Production |  | PHP+MySQL | CFRRYD12 |  | Primary: Dave Watson, Secondary: Jon Pugh | Commercial HVAC | [9 empty] | y
R04 | R04W07 | 2020-09-23 | 2020-10-21 |  | PHP+MySQL | CFRRYD13 | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Primary: Dave Watson, Secondary: Jon Pugh | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | db | Production |  | PHP+MySQL | CFRRYD13 |  | Primary: Dave Watson, Secondary: Jon Pugh | Commercial HVAC | [9 empty] | y
R04 | R04W06 | 2020-09-16 | 2020-10-14 |  | PHP+MySQL | CFRRYD1B | Region Build Pending |  |  | 0 | Roissy |  |  | RedHat | RD HAT ES 7.4 7.4 | Rehost | Primary: Dave Watson, Secondary: Jon Pugh | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | db | Test |  | PHP+MySQL | CFRRYD1B |  | Primary: Dave Watson, Secondary: Jon Pugh | Commercial HVAC | [9 empty] | y
R04 | R04W07 | 2020-09-23 | 2020-10-21 |  | PHP+MySQL | CFRRYW0E | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Primary: Dave Watson, Secondary: Jon Pugh | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | app | Production |  | PHP+MySQL | CFRRYW0E |  | Primary: Dave Watson, Secondary: Jon Pugh | Commercial HVAC | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | Pirana | CFRRYA4Z | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Marc Springthorpe-Rose | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | db | Production |  | Pirana | CFRRYA4Z |  | Marc Springthorpe-Rose | Fire and Security | [9 empty] | y
R04 | R04W02 | 2020-08-19 | 2020-09-16 |  | Power BI - Chubb - DEV | CFRRYK06 | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Nicolas Quentin | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | db | Dev |  | Power BI - Chubb - DEV | CFRRYK06 |  | Nicolas Quentin | Fire and Security | [9 empty] | y
R04 | R04W05 | 2020-09-09 | 2020-10-07 |  | Power BI - Chubb - PROD | CFRRYA2L | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Nicolas Quentin | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | db | Production |  | Power BI - Chubb - PROD | CFRRYA2L |  | Nicolas Quentin | Fire and Security | [9 empty] | y
R04 | R04W02 | 2020-08-19 | 2020-09-16 |  | R1 Carrier France SCS (SAP) - DEV | CFRRYA3J | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Jean-Yves JULLIEN | [11 empty] | HVAC_Com_Dev |  | SSD |  | YES | [6 empty] | HVAC_Com_Dev_436524867280 | db | Dev |  | R1 Carrier France SCS (SAP) - DEV | CFRRYA3J |  | Jean-Yves JULLIEN | HVAC_Com_Dev | [9 empty] | y
R04 | R04W02 | 2020-08-19 | 2020-09-16 |  | R1 Carrier France SCS (SAP) - QA | CFRRYA3H | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Jean-Yves JULLIEN | [11 empty] | HVAC_Com_Dev |  | SSD |  | YES | [6 empty] | HVAC_Com_Dev_436524867280 | db | Dev |  | R1 Carrier France SCS (SAP) - QA | CFRRYA3H |  | Jean-Yves JULLIEN | HVAC_Com_Dev | [9 empty] | y
R04 | R04W05 | 2020-09-09 | 2020-10-07 |  | R1 Chubb France - VDOC | CFRRYA2T | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | nicolas quentin | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | db | Production |  | R1 Chubb France - VDOC | CFRRYA2T |  | nicolas quentin | Fire and Security | [9 empty] | y
R04 | R04W05 | 2020-09-09 | 2020-10-07 |  | R1 Chubb France - VDOC | CFRRYD0V | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | nicolas quentin | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | db | Production |  | R1 Chubb France - VDOC | CFRRYD0V |  | nicolas quentin | Fire and Security | [9 empty] | y
R04 | R04W02 | 2020-08-19 | 2020-09-16 |  | R1 Chubb France Roissy En France (3266) - Power BI | CFRRYA2O | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | nicolas quentin | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | test |  | R1 Chubb France Roissy En France (3266) - Power BI | CFRRYA2O |  | nicolas quentin | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | R4 Carrier Germany Roissy (3266) | CFRRYA4C | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Simon Lehne | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | db | Production |  | R4 Carrier Germany Roissy (3266) | CFRRYA4C |  | Simon Lehne | Commercial HVAC | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | R4 Carrier Germany Roissy (3266) | CFRRYA4D | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 | Rehost | Simon Lehne | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | app | Production |  | R4 Carrier Germany Roissy (3266) | CFRRYA4D |  | Simon Lehne | Commercial HVAC | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | R4 Carrier Germany Roissy (3266) | CFRRYD1A | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Simon Lehne | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | db | Production |  | R4 Carrier Germany Roissy (3266) | CFRRYD1A |  | Simon Lehne | Commercial HVAC | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | R4 Carrier Germany Roissy (3266) | CFRRYT0X | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Simon Lehne | [11 empty] | Commercial HVAC |  | SSD |  | YES | [7 empty] | app | Production |  | R4 Carrier Germany Roissy (3266) | CFRRYT0X |  | Simon Lehne | Commercial HVAC | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | Remote Desktop Server License Manager | CFRRYA1A | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Hakan Erturk | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Production |  | Remote Desktop Server License Manager | CFRRYA1A |  | Hakan Erturk | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | Sage - Finance Package | CFRRYA4G | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2016 | Rehost | Gareth Ellson / Marc Springthorpe-Rose | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Production |  | Sage - Finance Package | CFRRYA4G |  | Gareth Ellson / Marc Springthorpe-Rose | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | Sage RDP Server | CFRRYA4T | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Gareth Ellson / Marc Springthorpe-Rose | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Production |  | Sage RDP Server | CFRRYA4T |  | Gareth Ellson / Marc Springthorpe-Rose | Fire and Security | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | SAVERIF | CFRRYD1M | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Dimitri Raignault | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | db | Production |  | SAVERIF | CFRRYD1M |  | Dimitri Raignault | Fire and Security | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | SAVERIF | CFRRYT18 | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2016 STD | Rehost | Dimitri Raignault | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Production |  | SAVERIF | CFRRYT18 |  | Dimitri Raignault | Fire and Security | [9 empty] | y
R04 | R04W01 | 2020-08-12 | 2020-09-09 |  | Spare Parts Identification - Prod | CFRRYA3E | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Jan Mencl / Heiko Trobisch | [13 empty] | SSD |  | YES | [7 empty] | db | Production |  | Spare Parts Identification - Prod | CFRRYA3E |  | Jan Mencl / Heiko Trobisch | 0 | [9 empty] | y
R04 | R04W01 | 2020-08-12 | 2020-09-09 |  | Spare Parts Identification - Test | CFRRYD0W | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Jan Mencl / Vratislav Vardzik | [13 empty] | SSD |  | YES | [7 empty] | db | Test |  | Spare Parts Identification - Test | CFRRYD0W |  | Jan Mencl / Vratislav Vardzik | 0 | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | SPEX | CFRRYA1A | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Hakan Erturk | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Production |  | SPEX | CFRRYA1A |  | Hakan Erturk | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | SPEX | CFRRYA1B | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Hakan Erturk | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Production |  | SPEX | CFRRYA1B |  | Hakan Erturk | Fire and Security | [9 empty] | y
R04 | R04W01 | 2020-08-12 | 2020-09-09 |  | StoreWizard | CFRRYA2S | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | GABRIEL RUA | [11 empty] | Refrigeration |  | SSD |  | YES | [7 empty] | app | Production |  | StoreWizard | CFRRYA2S |  | GABRIEL RUA | Refrigeration | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | StreamServe | CFRRYD0J | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2008 R2 Enterprise | Rehost | Patrick Kooderings Clemens | [11 empty] | Refrigeration |  | SSD |  | YES | [7 empty] | db | Production |  | StreamServe | CFRRYD0J |  | Patrick Kooderings Clemens | Refrigeration | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | StreamServe | CNLRDA02 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Patrick Kooderings Clemens | [11 empty] | Refrigeration |  | SSD |  | YES | [7 empty] | db | Production |  | StreamServe | CNLRDA02 |  | Patrick Kooderings Clemens | Refrigeration | [9 empty] | y
R04 | R04W01 | 2020-08-12 | 2020-09-09 |  | Subversion | CFRRYA1S | Region Build Pending |  |  | 0 | Roissy |  |  | RedHat | Linux Server 6 Red Hat ES 6 Santiago 6.4 | Rehost | Gareth Ellson | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | Subversion | CFRRYA1S |  | Gareth Ellson | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | Syteline | CFRRYA1A | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Hakan Erturk | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Production |  | Syteline | CFRRYA1A |  | Hakan Erturk | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | Syteline | CFRRYD0C | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Hakan Erturk | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Production |  | Syteline | CFRRYD0C |  | Hakan Erturk | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | Syteline | CFRRYT06 | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Hakan Erturk | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Production |  | Syteline | CFRRYT06 |  | Hakan Erturk | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | Syteline | CFRRYT07 | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Hakan Erturk | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Production |  | Syteline | CFRRYT07 |  | Hakan Erturk | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | Syteline | CFRRYT08 | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Hakan Erturk | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Production |  | Syteline | CFRRYT08 |  | Hakan Erturk | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | TNA Clock | CFRRYA1A | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Hakan Erturk | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Production |  | TNA Clock | CFRRYA1A |  | Hakan Erturk | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | TNA Clock | CFRRYA1B | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Hakan Erturk | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Production |  | TNA Clock | CFRRYA1B |  | Hakan Erturk | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | Track-IT | cfrrya4f | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Armin Leingruber | [13 empty] | SSD |  | YES | [7 empty] | db | Production |  | Track-IT | cfrrya4f |  | Armin Leingruber | 0 | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (Alloc8) | CFRRYD0O | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (Alloc8) | CFRRYD0O |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (Alloc8) | CFRRYW0G | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (Alloc8) | CFRRYW0G |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (CFS UK HR Workflow) | CFRRYA3T | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (CFS UK HR Workflow) | CFRRYA3T |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (CFS UK HR Workflow) | CFRRYK0F | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | non prod |  | UKI Chubb F&S UK (CFS UK HR Workflow) | CFRRYK0F |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (File Storage) | CFRRYA34 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (File Storage) | CFRRYA34 |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (File Storage) | CFRRYA3M | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (File Storage) | CFRRYA3M |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (File Storage) | CFRRYA49 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (File Storage) | CFRRYA49 |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (HR Helpdesk) | CFRRYA3T | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (HR Helpdesk) | CFRRYA3T |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (Invoice Production) | CFRRYA3I | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (Invoice Production) | CFRRYA3I |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (Invoice Production) | CFRRYA3R | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (Invoice Production) | CFRRYA3R |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (Sales Support) | CFRRYA3T | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (Sales Support) | CFRRYA3T |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (Sales Support) | CFRRYK0F | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | db | Staging |  | UKI Chubb F&S UK (Sales Support) | CFRRYK0F |  | David Emmerton | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (SEP) | CFRRYA32 | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton, Shazad Khan | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (SEP) | CFRRYA32 |  | David Emmerton, Shazad Khan | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (SEP) | CFRRYA34 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (SEP) | CFRRYA34 |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (SEP) | CFRRYA3I | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (SEP) | CFRRYA3I |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (SEP) | CFRRYA3R | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (SEP) | CFRRYA3R |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (SEP) | CFRRYA3T | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (SEP) | CFRRYA3T |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (SEP) | CFRRYA3X | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (SEP) | CFRRYA3X |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (SEP) | CFRRYA40 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (SEP) | CFRRYA40 |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (SEP) | CFRRYD0O | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (SEP) | CFRRYD0O |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (SEP) | CFRRYD0X | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (SEP) | CFRRYD0X |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (SEP) | CFRRYD19 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (SEP) | CFRRYD19 |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (SEP) | CFRRYK0F | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | db | Staging |  | UKI Chubb F&S UK (SEP) | CFRRYK0F |  | David Emmerton | Fire and Security | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | UKI Chubb F&S UK (SEP) | CFRRYT0V | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | David Emmerton | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (SEP) | CFRRYT0V |  | David Emmerton | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (TFS) | CFRRYA40 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (TFS) | CFRRYA40 |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (Timesheet Entry) | CFRRYA3T | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (Timesheet Entry) | CFRRYA3T |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (Timesheet Entry) | CFRRYK0F | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | db | Staging |  | UKI Chubb F&S UK (Timesheet Entry) | CFRRYK0F |  | David Emmerton | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (Visitor Express) | CFRRYA3T | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb F&S UK (Visitor Express) | CFRRYA3T |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb F&S UK (Visitor Express) | CFRRYK0F | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | db | Staging |  | UKI Chubb F&S UK (Visitor Express) | CFRRYK0F |  | David Emmerton | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb Systems (DocuWare) | CFRRYA5K | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb Systems (DocuWare) | CFRRYA5K |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb Systems (SEP) | CFRRYA3M | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb Systems (SEP) | CFRRYA3M |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Chubb Systems (SEP) | CFRRYA3R | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | David Emmerton | [11 empty] | FIRE AND SECURITY |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Chubb Systems (SEP) | CFRRYA3R |  | David Emmerton | FIRE AND SECURITY | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Kidde Products (CFRRYF04) | CFRRYF04 | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2008 R2 Standard | Rehost | Hakan Erturk | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Kidde Products (CFRRYF04) | CFRRYF04 |  | Hakan Erturk | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Pyronix | CFRRYA32 | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Shazad Khan | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | app | Production |  | UKI Pyronix | CFRRYA32 |  | Shazad Khan | Fire and Security | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | UKI Pyronix | CFRRYD1X | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2016 Standard | Rehost | Shazad Khan | [11 empty] | Fire and Security |  | SSD |  | YES | [7 empty] | db | Production |  | UKI Pyronix | CFRRYD1X |  | Shazad Khan | Fire and Security | [9 empty] | y
R04 | R04W03 | 2020-08-26 | 2020-09-23 |  | Workflow | CFRRYD0J | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2008 R2 Enterprise | Rehost | Ricardo Font-De-Campos | [11 empty] | Refrigeration |  | SSD |  | YES | [7 empty] | db | Production |  | Workflow | CFRRYD0J |  | Ricardo Font-De-Campos | Refrigeration | [9 empty] | y
R04 | R04W04 | 2020-09-02 | 2020-09-30 |  | Xerox Work Place | CFRRYA3Y | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Anders Hjerpe | [11 empty] | GLOBAL |  | SSD |  | YES | [7 empty] | db | Production |  | Xerox Work Place | CFRRYA3Y |  | Anders Hjerpe | GLOBAL | [9 empty] | y
R04 | R04W01 | 2020-08-12 | 2020-09-09 |  | Xerox Work Place | CFRRYA3Z | Region Build Pending |  |  | 0 | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Anders Hjerpe | [11 empty] | GLOBAL |  | SSD |  | YES | [7 empty] | db | Test |  | Xerox Work Place | CFRRYA3Z |  | Anders Hjerpe | GLOBAL | [9 empty] | y
R04 | R04W06 | 2020-09-16 | 2020-10-14 |  | CARRIER SCS PROFROID - LNPROFROID | CFRRYA37 | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Patrick Dubuisson | [11 empty] | Refrigeration |  | SSD |  | YES | [7 empty] | app | Dev |  | CARRIER SCS PROFROID - LNPROFROID | CFRRYA37 |  | Patrick Dubuisson | Refrigeration | [9 empty] | y
R04 | R04W06 | 2020-09-16 | 2020-10-14 |  | CARRIER SCS PROFROID - MCSTSE | CFRRYT0T | Region Build Pending |  |  | COMPLETE | Roissy |  |  | Windows | Windows Server 2012 R2 Standard | Rehost | Patrick Dubuisson | [11 empty] | Refrigeration |  | SSD |  | YES | [7 empty] | app | Production |  | CARRIER SCS PROFROID - MCSTSE | CFRRYT0T |  | Patrick Dubuisson | Refrigeration | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | 0 | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | 0 |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | 0 | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | 0 | [9 empty] | y
[44 empty] | #REF! | #REF! |  | #REF! |  | #NAME? | #NAME?
Note on D9: Microsoft Office User: Moved to EoM after Pranav's conversation with Liza from DXC around HPC pre-reqs
Note on B10: Microsoft Office User: was R01W01
Note on D10: Microsoft Office User: Moved to EoM after Pranav's conversation with Liza from DXC around HPC pre-reqs
Note on E10: Microsoft Office User: Was 8am (test - 10am)
Note on G10: Microsoft Office User: 7/8 - Pulled the server out from 7/9 after a discussion with Sarah. Follow-up discussion with Liza and the DXC team set for 7/9.
Note on E11: Microsoft Office User: Was 8am (test - 10am) Ram to confirm by 7/17
Note on E12: Microsoft Office User: Was 8am (test - 10am) Ram to confirm by 7/17
Note on D13: Microsoft Office User: Moved to EoM after Pranav's conversation with Liza from DXC around HPC pre-reqs
Note on D14: Microsoft Office User: Moved to EoM after Pranav's conversation with Liza from DXC around HPC pre-reqs
Note on D15: Microsoft Office User: Moved to EoM after Pranav's conversation with Liza from DXC around HPC pre-reqs
Note on D16: Microsoft Office User: Moved to EoM after Pranav's conversation with Liza from DXC around HPC pre-reqs
Note on D17: Microsoft Office User: Moved to EoM after Pranav's conversation with Liza from DXC around HPC pre-reqs
Note on D18: Microsoft Office User: Moved to EoM after Pranav's conversation with Liza from DXC around HPC pre-reqs
Note on D19: Microsoft Office User: Moved to EoM after Pranav's conversation with Liza from DXC around HPC pre-reqs
Note on B21: Microsoft Office User: was R01W01
Note on D21: Microsoft Office User: Moved to EoM after Pranav's conversation with Liza from DXC around HPC pre-reqs
Note on E21: Microsoft Office User: Was 8am (test - 10am)
Note on G21: Microsoft Office User: 7/8 - Pulled the server out from 7/9 after a discussion with Sarah. Follow-up discussion with Liza and the DXC team set for 7/9.
Note on V26: Microsoft Office User: 4 GB remaining
Note on B29: Microsoft Office User: was R01W01
Note on D29: Microsoft Office User: Moved to EoM after Pranav's conversation with Liza from DXC around HPC pre-reqs
Note on E29: Microsoft Office User: Was 6pm (test - 9pm)
Note on G29: Pratik 7/7: to get revised outage window from Sarah S.
Note on B30: Microsoft Office User: was R01W01
Note on D30: Microsoft Office User: Moved to EoM after Pranav's conversation with Liza from DXC around HPC pre-reqs
Note on E30: Microsoft Office User: Was 6pm (test - 9pm)
Note on G30: Pratik - 7/7: to get revised outage window from Sarah S.
Note on B31: Microsoft Office User: was R01W01
Note on D31: Microsoft Office User: Moved to EoM after Pranav's conversation with Liza from DXC around HPC pre-reqs
Note on E31: Microsoft Office User: Was 6pm (test - 9pm)
Note on G31: Pratik 7/7: to get revised outage window from Sarah S.
Note on F49: Pratik: planning to decommission Cusmnd0e and move to a new Doubletake server (VMC7222PA088) so the migration of the server will not be needed. June 30 - mauro.ciccarelli@carrier.com
Note on D50: Microsoft Office User: Pending app owner confirmation
Note on G50: Microsoft Office User: AD migration was not complete as of 6/16
Note on G51: Microsoft Office User: inistalled on Jun 24
Note on D54: Microsoft Office User: Pending app owner confirmation
Note on G54: Microsoft Office User: AD migration was not complete as of 6/16
Note on H57: Microsoft Office User: Was unable to connect via SSMS over default SQL port 1433
Note on H58: Microsoft Office User: Was unable to connect via SSMS over default SQL port 1433
Note on F73: Pratik: Vendor support issue - alejandro.martinez@carrier.com
Note on D75: Microsoft Office User: Moved from 7/9 due to last min email from LTI notifying unavailability of testers
Note on H76: Microsoft Office User: App Owner did not join - Pending app testing
Note on H77: Microsoft Office User: App Owner did not join - Pending app testing
Note on H78: Microsoft Office User: App Owner did not join - Pending app testing
Note on F79: Pratik (7/6): Long replication ETA and may have to be pushed to 7/15 Wave
Note on F80: Pratik (7/6): Long replication ETA and may have to be pushed to 7/15 Wave
Note on F81: Pratik (7/6): Long replication ETA and may have to be pushed to 7/15 Wave
Note on B92: Microsoft Office User: was R03W01
Note on D92: Microsoft Office User: moved from 7/9 per Jeff T.'s request
Note on G92: Microsoft Office User: 7/8 - Andrew Summers termed server not ready for migration. Escalation done
Note on D93: Microsoft Office User: Moved from 7/9
Note on G93: Microsoft Office User: App Owner was unaware and needed FSRs were for different ports
Note on D94: Microsoft Office User: Moved from 7/9
Note on G94: Microsoft Office User: App Owner was unaware and needed FSRs were for different ports
Note on H95: Microsoft Office User: App Owner did not join - Pending app testing
Note on K100: Microsoft Office User: Oran confirmed on 7/8 over email
Note on G103: Microsoft Office User: to be deco - 6/25, John M. confirmed deco - 7/8
Note on H123: Microsoft Office User: App Owner did not join - Pending app testing
Note on H124: Microsoft Office User: App Owner did not join - Pending app testing
Note on AP151: Microsoft Office User: Print Server
Note on B198: Microsoft Office User: Can be merged with R04W05
Note on B199: Microsoft Office User: Can be merged with R04W05
Note on B200: Microsoft Office User: Can be merged with R04W05
Note on B206: Microsoft Office User: Can be merged with R04W05
Note on B207: Microsoft Office User: Can be merged with R04W05
Note on B208: Microsoft Office User: Can be merged with R04W05
Note on B209: Microsoft Office User: Can be merged with R04W05
Note on B210: Microsoft Office User: Can be merged with R04W05
Note on B282: Microsoft Office User: Can be merged with R04W05
Note on B283: Microsoft Office User: Can be merged with R04W05

## RePlatform-Dashboard
[18 empty] | Check-101 (AWS Migration team) |  |  | Disk Size | [22 empty] | EC2-Tagging -(AWS Migration/Carrier team) | [15 empty] | Pre-Migration |  |  |  |  | Build |  |  | Validate |  |  | Boot-up Testing |  |  |  |  | Cutover Validation | [6 empty] | Post Cutover activities/validation (App Owner)
Release | rePlat Group | Start Date | End Date | Cutover Date from App Owner | App | Server_Name | Migration Status | FQDN | On-prem IP | Environment | DC/Site | No of CPU | Total Memory (GB) | Current OS Version | New OS Version (through GAMI) | Server Type | App Owner | AWS Migration Team RDP access validation | Outbound TCP 443,1500 through Proxy | Interview Answer Cross check | C: | D: | E: | F: | G: | R: | X: | Target AWS account | Target AWS Account Name | Target EC2 Instance Type | EBS volume Type (Std, SSD, Provisioned) | EBS IOPS | EBS Encryption (Yes/No) | Target Subnet | Target Security Group | securitygroup_IDs_test | Target Private IP | Target Public IP or EIP | IAM Role | cloudendure project name | server_tier | server_environment | tenancy | ApplicationName | Server Name | Application ID | ApplicationOwner | BusinessUnit | Department | CostCenter | ServerType | ComplianceRequirement | Entity | Environment2 | Region | UsagePattern | MaxLifeTime | backup | AppCat | Confirm Wave Plan with App Owner (AWS, Carrier) | Submit BPAR [status-date] (Carrier) | Submit RFC and Schedule Change window (Carrier) | Complete migration factory intake form (AWS) | Import intake form in to Migration Factory (AWS) | Verify Source Server Pre-requisite (AWS) | Install CloudEndure agent (AWS) | (Optional) Push post-launch script (AWS, Carrier) | Verify CloudEndure replication status (AWS) | (Optional) Troubleshoot CloudEndure issues (AWS) | Validate local admin/sudo user on source machines (AWS, Carrier) | Launch server from migration factory and CloudEndure (AWS, Carrier) | Verify instance boot up status (AWS) | (Optional) Resolve instance boot up issues (AWS) | Validate cutover blueprint for Target instance type, disk IOPS, IP, SG,Subnet (AWS) | Terminate test instances (AWS) | Verify CloudEndure replication status (AWS)4 | Stop Service or shutdown source server for cutover (Carrier) | Launch instances for cutover (AWS) | Verify instance boot up status (AWS)5 | Test RDP/SSH access (AWS, Carrier) | (Optional) Clean up local admin/sudo after cutover (AWS) | Change DNS or other network settings for the application (Carrier) | Application Configuration Change/Network change (Carrier) | Post Cutover activities/ Application validation (App Owner) | Notes | Issues
R01 | 1 | 2020-07-31 | 2020-08-07 |  | CANON CBPS | CUSH0A72 |  |  |  | Production | Tulsa |  |  | Windows Server 2012 R2 Datacenter |  |  | Warren Davis, Kurt Hague, Jason Hinds, Yashovardhan Dixit | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R01 | 1 | 2020-07-31 | 2020-08-07 |  | CANON CBPS | CUSH1AW0 |  |  |  | Production | Alpharetta |  |  | Windows Server 2012 R2 Datacenter |  |  | Warren Davis, Kurt Hague, Jason Hinds, Yashovardhan Dixit | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R01 | 1 | 2020-07-31 | 2020-08-07 |  | CANON CBPS | CUSH1AW3 |  |  |  | Production | Alpharetta |  |  | Windows Server 2012 R2 Datacenter |  |  | Warren Davis, Kurt Hague, Jason Hinds, Yashovardhan Dixit | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R01 | 1 | 2020-07-31 | 2020-08-07 |  | CANON CBPS | CUSH1AX5 |  |  |  | Production | Alpharetta |  |  | Windows Server 2012 R2 Datacenter |  |  | Warren Davis, Kurt Hague, Jason Hinds, Yashovardhan Dixit | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 2 | 2020-07-31 | 2020-08-14 |  | Sage Business Exchange (eBanking) - staging - BaaN | CUSMNA03 |  |  |  | Staging | Meridien |  |  | AIX 5.3 |  |  | Nilesh Chowdhary, Alain Deleval | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 2 | 2020-07-31 | 2020-08-14 |  | Tivoli Workload Scheduler 8.5.1 - staging | CUSMNA03 |  |  |  | Staging | Meridien |  |  | AIX 5.3 |  |  | Jean-Charles MOISAN, Benjamin Levay | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 2 | 2020-07-31 | 2020-08-14 |  | Infor Baan LN 6.1 FP5 | CUSMNA03 |  |  |  | Staging | Meridien |  |  | AIX 5.3 |  |  | Nash Weragama | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 2 | 2020-07-31 | 2020-08-14 |  | BaaN 4C4 - staging | CUSMNA03 |  |  |  | Staging | Meridien |  |  | AIX 5.3 |  |  | Jean-Charles MOISAN, Christine LEMAOU, Benjamin Levay | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 2 | 2020-07-31 | 2020-08-14 |  | BaaN 4C4 - staging | CUSMND05 |  |  |  | Staging | Meridien |  |  | AIX 5.3 |  |  | Jean-Charles MOISAN, Christine LEMAOU, Benjamin Levay | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 2 | 2020-07-31 | 2020-08-14 |  | Baan LN (Singapore) | CUSMNA06 |  |  |  | Production | Meridien |  |  | Linux - Red Hat 5.x |  |  | Boon Swee Chin, Roger See | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 2 | 2020-07-31 | 2020-08-14 |  | Baan LN (Singapore) | CUSMND08 |  |  |  | Production | Meridien |  |  | Linux - Red Hat 5.x |  |  | Boon Swee Chin, Roger See | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 2 | 2020-07-31 | 2020-08-14 |  | BAAN LN FP7 | CUSMNA06 |  |  |  | Production | Meridien |  |  | Linux - Red Hat 5.x |  |  | Eddy Cao | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 1 | 2020-07-31 | 2020-08-07 |  | Employee Self Service - Project Oak - On-Prem Carrier | CUSMNK1C |  |  |  | APM | Meridien |  |  | Database Server (Oracle 12C) |  |  | Tracy Jones, Polly Fabry | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 1 | 2020-07-31 | 2020-08-07 |  | Employee Self Service - Project Oak - On-Prem Carrier | CUSMNK1D |  |  |  | APM | Meridien |  |  | Database Server (Oracle 12C) |  |  | Tracy Jones, Polly Fabry | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 1 | 2020-07-31 | 2020-08-07 |  | Employee Self Service - Project Oak - On-Prem Carrier | CUSMNK1E |  |  |  | Dev, Test | Meridien |  |  | Database Server (Oracle 12C) |  |  | Tracy Jones, Polly Fabry | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 1 | 2020-07-31 | 2020-08-07 |  | Employee Self Service - Project Oak - On-Prem Carrier | CUSMNK1F |  |  |  | Dev, Test | Meridien |  |  | Database Server (Oracle 12C) |  |  | Tracy Jones, Polly Fabry | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 1 | 2020-07-31 | 2020-08-07 |  | Employee Self Service - Project Oak - On-Prem Carrier | CUSMNK1G |  |  |  | Dev, Test | Meridien |  |  | App Server |  |  | Tracy Jones, Polly Fabry | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 2 | 2020-07-31 | 2020-07-15 | Rehost | MS Dynamics SL - TEST | CUSMNK0R |  |  |  | Test | Meridien |  |  | Windows ServerÂ® 2008 Enterprise |  |  | Renee Brewer | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 2 | 2020-07-31 | 2020-07-15 | Rehost | MS Dynamics SL - TEST | CUSMNK0W |  |  |  | Test | Meridien |  |  | Windows ServerÂ® 2008 Standard |  |  | Renee Brewer | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 1 | 2020-07-31 | 2020-08-07 |  | Employee Self Service - Project Oak - On-Prem Carrier | CUSMNK1H |  |  |  | Dev, Test | Meridien |  |  | App Server |  |  | Tracy Jones, Polly Fabry | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 1 | 2020-07-31 | 2020-08-07 |  | Employee Self Service - Project Oak - On-Prem Carrier | CUSMNK1J |  |  |  | Dev, Test | Meridien |  |  | App Server |  |  | Tracy Jones, Polly Fabry | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 1 | 2020-07-31 | 2020-08-07 |  | Employee Self Service - Project Oak - On-Prem Carrier | XMNT307 |  |  |  | Dev, Test | Meridien |  |  | App Server (Linux) |  |  | Tracy Jones, Polly Fabry | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 1 | 2020-07-31 | 2020-08-07 |  | Employee Self Service - Project Oak - On-Prem Carrier | XMNT308 |  |  |  | Dev, Test | Meridien |  |  | App Server (Linux) |  |  | Tracy Jones, Polly Fabry | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 1 | 2020-07-31 | 2020-08-07 |  | Employee Self Service - Project Oak - On-Prem Carrier | XMNT309 |  |  |  | Test | Meridien |  |  | App Server (Windows) |  |  | Tracy Jones, Polly Fabry | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 1 | 2020-07-31 | 2020-08-07 |  | Employee Self Service - Project Oak - On-Prem Carrier | XMNT310 |  |  |  | Test | Meridien |  |  | App Server (Windows) |  |  | Tracy Jones, Polly Fabry | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 2 | 2020-07-31 | 2020-08-14 |  | Global IdM (OIM) | QUSMND0ZVIP |  |  |  | 0 | Meridien |  |  | Linux 3.2 |  |  | Bruce Lindstrom | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 2 | 2020-07-31 | 2020-08-14 |  | Infor Baan LN 6.1 FP5 | CUSMND05 |  |  |  | Staging | Meridien |  |  | AIX 5.3 |  |  | Nash Weragama | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 2 | 2020-07-31 | 2020-08-14 |  | Infor ION | CUSMNK0N |  |  |  | Production | Meridien |  |  | Microsoft Windows Server 2012 R2 Standard |  |  | Nash Weragama | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 2 | 2020-07-31 | 2020-08-14 |  | Infor ION 10X | CUSMNK0N |  |  |  | Production | Meridien |  |  | Microsoft Windows Server 2012 R2 Standard |  |  | Nash Weragama | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 2 | 2020-07-31 | 2020-08-14 |  | RCS Newington (BI 4) - QA | CUSMNK17 |  |  |  | Production | Meridien |  |  | Linux - OEL 6.x |  |  | Phillip Pascoe, Craig Tiroff | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R02 | 2 | 2020-07-31 | 2020-08-14 |  | RCS Newington (SAP DW) - QA | CUSMNK17 |  |  |  | Production | Meridien |  |  | Linux - OEL 6.x |  |  | Phillip Pascoe, Craig Tiroff | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | BaaN 4C4 - Production | CUSNWA25 |  |  |  | Production | Newington |  |  | AIX 5.3 |  |  | Jean-Charles MOISAN, Christine LEMAOU, Benjamin Levay | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | BaaN 4C4 - Production | CUSNWA26 |  |  |  | Production | Newington |  |  | AIX 5.3 |  |  | Jean-Charles MOISAN, Christine LEMAOU, Benjamin Levay | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | Baan ln Shanghai Carrier transicold | CUSNWA30 |  |  |  | Production | Newington |  |  | Linux - Red Hat 5.x |  |  | Eddy Cao | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | Baan LN (Singapore) | CUSNWA30 |  |  |  | Production | Newington |  |  | Linux - Red Hat 5.x |  |  | Boon Swee Chin, Roger See | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | Baan LN (Singapore) | CUSNWB02 |  |  |  | Production | Newington |  |  | Linux - Red Hat 5.x |  |  | Boon Swee Chin, Roger See | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | Baan LN (Singapore) | CUSNWD15 |  |  |  | Production | Newington |  |  | Linux - Red Hat 5.x |  |  | Boon Swee Chin, Roger See | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | BAAN LN FP7 | CUSNWA30 |  |  |  | Production | Newington |  |  | Linux - Red Hat 5.x |  |  | Eddy Cao | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | BAAN LN FP7 | CUSNWB02 |  |  |  | Production | Newington |  |  | Linux - Red Hat 5.x |  |  | Eddy Cao | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | BAAN LN FP7 | CUSNWD15 |  |  |  | Production | Newington |  |  | Linux - Red Hat 5.x |  |  | Eddy Cao | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 2 | 2020-08-07 | 2020-08-14 |  | Employee Self Service - Project Oak - On-Prem Carrier | CUSNWA5W |  |  |  | Production | Newington |  |  | App Server |  |  | Tracy Jones, Polly Fabry | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 2 | 2020-08-07 | 2020-08-14 |  | Employee Self Service - Project Oak - On-Prem Carrier | CUSNWA7N |  |  |  | Production | Newington |  |  | App Server |  |  | Tracy Jones, Polly Fabry | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 2 | 2020-08-07 | 2020-08-14 |  | Employee Self Service - Project Oak - On-Prem Carrier | CUSNWD1D |  |  |  | Production | Newington |  |  | Database Server (Oracle 12C) |  |  | Tracy Jones, Polly Fabry | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 2 | 2020-08-07 | 2020-08-14 |  | Employee Self Service - Project Oak - On-Prem Carrier | CUSNWD1E |  |  |  | Production | Newington |  |  | Database Server (Oracle 12C) |  |  | Tracy Jones, Polly Fabry | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 2 | 2020-08-07 | 2020-08-14 |  | Employee Self Service - Project Oak - On-Prem Carrier | CUSNWW19 |  |  |  | Production | Newington |  |  | App Server (Linux) |  |  | Tracy Jones, Polly Fabry | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 2 | 2020-08-07 | 2020-08-14 |  | Employee Self Service - Project Oak - On-Prem Carrier | XNWP953 |  |  |  | Production | Newington |  |  | App Server (Linux) |  |  | Tracy Jones, Polly Fabry | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 2 | 2020-08-07 | 2020-08-14 |  | Employee Self Service - Project Oak - On-Prem Carrier | XNWP954 |  |  |  | Production | Newington |  |  | App Server (Linux) |  |  | Tracy Jones, Polly Fabry | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 2 | 2020-08-07 | 2020-08-14 |  | Employee Self Service - Project Oak - On-Prem Carrier | XNWP955 |  |  |  | Production | Newington |  |  | App Server (Windows) |  |  | Tracy Jones, Polly Fabry | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 2 | 2020-08-07 | 2020-08-14 |  | Employee Self Service - Project Oak - On-Prem Carrier | XNWP956 |  |  |  | Production | Newington |  |  | App Server (Windows) |  |  | Tracy Jones, Polly Fabry | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 2 | 2020-08-07 | 2020-08-14 |  | Employee Self Service (ESS) | QUSNWACI |  |  |  | Production | Newington |  |  | Red Hat Enterprise Linux Server release 7.7 (Maipo) - 375 GB is currently used. |  |  | gpsbsitdba@sbs.utc.com Tracy Jones | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 2 | 2020-08-07 | 2020-08-14 |  | HVACNA Shared Platform for CCS Operational DW | CUSNWD2N |  |  |  | Production | Newington |  |  | Linux - OEL 6.x |  |  | Phillip Pascoe, Craig Tiroff | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 2 | 2020-08-07 | 2020-08-14 |  | HVACNA-Exec Analytics & Self Service Reporting | CUSNWD2N |  |  |  | Production | Newington |  |  | Linux - OEL 6.x |  |  | Phillip Pascoe, Craig Tiroff | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 2 | 2020-08-07 | 2020-08-14 |  | HVACNA-External Customer Reporting & Analytics | CUSNWD2N |  |  |  | Production | Newington |  |  | Linux - OEL 6.x |  |  | Phillip Pascoe, Craig Tiroff | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 2 | 2020-08-07 | 2020-08-14 |  | HVACNA-HVACBUSINESSOBJECTS-BI-US-RCS | CUSNWD2N |  |  |  | Production | Newington |  |  | Linux - OEL 6.x |  |  | Phillip Pascoe, Craig Tiroff | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | Infor - ION | CUSNWD1B |  |  |  | Production | Newington |  |  | Microsoft Windows Server 2012 R2 Standard |  |  | Nash Weragama | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | Infor Baan LN 6.1 FP5 | CUSNWA25 |  |  |  | Production | Newington |  |  | AIX 5.3 |  |  | Nash Weragama | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | Infor Baan LN 6.1 FP5 | CUSNWA26 |  |  |  | Production | Newington |  |  | AIX 5.3 |  |  | Nash Weragama | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | Infor ION 10X | CUSNWD1B |  |  |  | Production | Newington |  |  | Microsoft Windows Server 2012 R2 Standard |  |  | Nash Weragama | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 1 | 2020-07-31 | 2020-08-28 |  | NOR Newforma - Prod | CMUSSWHNWFRWB1.UTCWH.COM |  |  |  | Production | Newington |  |  | Windows Server 2012 R2 Standard |  |  | Ferdinand Schmid, Trish Cratty, Tesfa Taitt, Felix Baxter, Frehiwot Zerom | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 1 | 2020-07-31 | 2020-08-28 |  | NOR Newforma - Prod | CUSNWA38 |  |  |  | Production | Newington |  |  | Windows Server 2012 R2 Standard |  |  | Ferdinand Schmid | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 2 | 2020-08-07 | 2020-08-14 |  | MS Dynamics SL - PROD | CUSNWW1K |  |  |  | DR / Production | Newington |  |  | Windows ServerÂ® 2008 Enterprise |  |  | Renee Brewer | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 1 | 2020-07-31 | 2020-08-28 |  | NOR Talon FastEdge - PROD | CUSNWA7P |  |  |  | Production | Newington |  |  | Windows Server 2012 R2 Standard |  |  | Ferdinand Schmid, Trish Cratty | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 2 | 2020-08-07 | 2020-08-14 |  | RCS Newington (BI 4) | CUSNWD2N |  |  |  | Production | Newington |  |  | Linux - OEL 6.x |  |  | Phillip Pascoe, Craig Tiroff | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 2 | 2020-08-07 | 2020-08-14 |  | RCS Newington (SAP DW) | CUSNWD2N |  |  |  | Production | Newington |  |  | Linux - OEL 6.x |  |  | Phillip Pascoe, Craig Tiroff | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | Sage Business Exchange (eBanking) BaaN | CUSNWA26 |  |  |  | Production | Newington |  |  | AIX 5.3 |  |  | Nilesh Chowdhary, Alain Deleval | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | Tivoli Workload Scheduler 8.5.1 - Production | CUSNWA26 |  |  |  | Production | Newington |  |  | AIX 5.3 |  |  | Jean-Charles MOISAN, Benjamin Levay | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | WHQ Engineering (Windchill) | CUSNWA2Z |  |  |  | production | Newington |  |  | Windows Server 2012 R2 Standard |  |  | John Macpherson | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | WHQ Engineering (Windchill) | CUSNWA3M |  |  |  | production | Newington |  |  | Linux - Red Hat 6.x |  |  | John Macpherson | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | WHQ Engineering (Windchill) | CUSNWA3N |  |  |  | production | Newington |  |  | Linux - Red Hat 6.x |  |  | John Macpherson | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | WHQ Engineering (Windchill) | CUSNWA3O |  |  |  | production | Newington |  |  | Linux - Red Hat 6.x |  |  | John Macpherson | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | WHQ Engineering (Windchill) | CUSNWA3P |  |  |  | production | Newington |  |  | Linux - Red Hat 6.x |  |  | John Macpherson | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | WHQ Engineering (Windchill) | CUSNWA3R |  |  |  | Production | Newington |  |  | Windows Server 2008 R2 Enterprise |  |  | Rich Becher | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | WHQ Engineering (Windchill) | CUSNWA3Q |  |  |  | production | Newington |  |  | Windows Server 2008 R2 Enterprise |  |  | John Macpherson | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | WHQ Engineering (Windchill) | CUSNWA44 |  |  |  | production | Newington |  |  | Windows Server 2008 R2 Standard |  |  | John Macpherson | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | WHQ Engineering (Windchill) | CUSNWA4V |  |  |  | production | Newington |  |  | Windows Server 2008 R2 Standard |  |  | John Macpherson | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R03 | 3 | 2020-08-14 | 2020-08-28 |  | WHQ Engineering (Windchill) | CUSNWA7Y |  |  |  | Production | Newington |  |  | Microsoft Windows Server 2012 R2 Standard |  |  | Sandra Trainer, John Macpherson | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R04 | 1 | 2020-08-20 | 2020-09-03 | Retain - TBC | BIS R1: Chubb France ECLAIRFDV | ECLAIRFDV |  |  |  |  | Roissy |  |  | Windows 2000 Server |  |  | Nicolas Quentin | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R04 | 1 | 2020-08-20 | 2020-09-03 | Retain - TBC | BIS R1: Chubb France ECLAIRFDV | ECLAIRFDVTEST |  |  |  |  | Roissy |  |  | Windows 2000 Server |  |  | Nicolas Quentin | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R04 | 1 | 2020-08-20 | 2020-09-03 | Retain - TBC | BIS R1: Chubb France ECLAIRFDV | ECLAIRSQL |  |  |  |  | Roissy |  |  | Windows Server 2003 |  |  | Nicolas Quentin | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R04 | 1 | 2020-08-20 | 2020-09-03 | Retain - TBC | BIS R1: Chubb France ECLAIRSAV | CFRRYA0T |  |  |  |  | Roissy |  |  | Windows Server 2008 R2 Standard |  |  | Nicolas Quentin | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R04 | 1 | 2020-08-20 | 2020-09-03 | Retain - TBC | BIS R1: Chubb France ECLAIRSAV | KFRCEESXDC01 |  |  |  |  | Roissy |  |  | ESXi 4.0 VMWARE ESX Host 4.0 |  |  | Nicolas Quentin | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R04 | 1 | 2020-08-20 | 2020-09-03 | Retain - TBC | BIS R1: Chubb France ECLAIRSAV | KFRCEESXDC02 |  |  |  |  | Roissy |  |  | ESXi 4.0 VMWARE ESX Host 4.0 |  |  | Nicolas Quentin | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R04 | 1 | 2020-08-20 | 2020-09-03 | Retain - TBC | BIS R1: Chubb France ECLAIRSAV | ECLAIRIIS1 |  |  |  |  | Roissy |  |  | Windows Server 2003 Windows Server 2003 Std SP2 |  |  | Nicolas Quentin | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R04 | 1 | 2020-08-20 | 2020-09-03 | Retain - TBC | BIS R1: Chubb France ECLAIRSAV | ECLAIRIIS2 |  |  |  |  | Roissy |  |  | Windows Server 2003 Windows Server 2003 Std SP2 |  |  | Nicolas Quentin | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R04 | 1 | 2020-08-20 | 2020-09-03 | Retain - TBC | BIS R1: Chubb France ECLAIRSAV | KFRCPA01 |  |  |  |  | Roissy |  |  | Windows Server 2003 |  |  | Nicolas Quentin | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R04 | 1 | 2020-08-20 | 2020-09-03 | Retain - TBC | BIS R1: Chubb France ECLAIRSAV | SICLISQL |  |  |  |  | Roissy |  |  | Windows Server 2003 |  |  | Nicolas Quentin | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R04 | 1 | 2020-08-20 | 2020-09-03 | Retain - TBC | BIS R1: Chubb France ECLAIRSAV | SICLISQLTEST |  |  |  |  | Roissy |  |  | Windows Server 2003 |  |  | Nicolas Quentin | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R04 | 1 | 2020-08-20 | 2020-09-03 |  | FRO France (QAD Enterprise) | CFRRMF01 |  |  |  |  | Roissy |  |  | RED HAT 5 |  |  | Jakub Pokorny | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R04 | 1 | 2020-08-20 | 2020-09-03 |  | Diapason - Business | CFRRYA47 |  |  |  | Production | Roissy |  |  | AIX 7.1 7100-04-01-1543 |  |  | Fotini Drimoni | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R04 | 1 | 2020-08-20 | 2020-09-03 |  | R2 HVAC Italy (7879 3266) | CFRRYA31 |  |  |  | Production | Roissy |  |  | AIX 7.1 7100-04-01-1543 |  |  | Giuseppe Larovere | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R04 | 1 | 2020-08-20 | 2020-09-03 |  | SAP 4,6B - PROD | CFRRYA0J |  |  |  | Production | Roissy |  |  | Windows Server 2003 |  |  | Maria Erba, Eric Daniele, Amaury Deroche, Giuseppe Larovere | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
R04 | 1 | 2020-08-20 | 2020-09-03 |  | SAP 4,6B - TEST | CFRRYA0H |  |  |  | TEST | Roissy |  |  | Windows Server 2003 |  |  | Maria Erba, Eric Daniele, Amaury Deroche, Giuseppe Larovere | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
Chubb CN | 1 | 2020-08-20 | 2020-09-24 |  | ADP Payroll / Timesheet | CCAMOA09 |  |  |  |  | Canada |  |  | Windows Server 2008 R2 - 64bit |  |  | Matthew.Fernandez@chubbfs.ca | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
Chubb CN | 1 | 2020-08-20 | 2020-09-24 |  | eBanking Server | CCAMOF07 |  |  |  |  | Canada |  |  | Windows Server 2012 R2 64 bit |  |  | Matthew.Fernandez@chubbfs.ca | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
Chubb CN | 1 | 2020-08-20 | 2020-09-24 |  | Finance File Share | KCAMOW099 |  |  |  |  | Canada |  |  | Windows 7, 64bit |  |  | Matthew.Fernandez@chubbfs.ca | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
Chubb CN | 1 | 2020-08-20 | 2020-09-24 |  | FTP Server | CAMICS09 |  |  |  |  | Canada |  |  | Windows Server 2008 – 32bit |  |  | Matthew.Fernandez@chubbfs.ca | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
Chubb CN | 1 | 2020-08-20 | 2020-09-24 |  | Global Payroll Environment | CCAMOA0W |  |  |  |  | Canada |  |  | Windows Server 2008 R2 - 64bit |  |  | Matthew.Fernandez@chubbfs.ca | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
Chubb CN | 1 | 2020-08-20 | 2020-09-24 |  | Group File Server / User Home Drive | KCAMOF01 |  |  |  |  | Canada |  |  | Windows Server 2008 R2 - 64bit |  |  | Matthew.Fernandez@chubbfs.ca | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
Chubb CN | 1 | 2020-08-20 | 2020-09-24 |  | Group File Server / User Home Drive | KCAMOF03 |  |  |  |  | Canada |  |  | Windows Server 2008 R2 - 64bit |  |  | Matthew.Fernandez@chubbfs.ca | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
Chubb CN | 1 | 2020-08-20 | 2020-09-24 |  | Group File Server / User Home Drive | CSG_MIS_FS1 |  |  |  |  | Canada |  |  | Windows Server 2008 R2 - 64bit |  |  | Matthew.Fernandez@chubbfs.ca | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
Chubb CN | 1 | 2020-08-20 | 2020-09-24 |  | Group File Server / User Home Drive | CHBMISFS1 |  |  |  |  | Canada |  |  | Windows Server 2008 R2 - 64bit |  |  | Matthew.Fernandez@chubbfs.ca | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
Chubb CN | 1 | 2020-08-20 | 2020-09-24 |  | Group File Server / User Home Drive | CCAAJF01 |  |  |  |  | Canada |  |  | Windows Server 2008 R2 - 64bit |  |  | Matthew.Fernandez@chubbfs.ca | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
Chubb CN | 1 | 2020-08-20 | 2020-09-24 |  | Group File Server / User Home Drive | CCAOSF01 |  |  |  |  | Canada |  |  | Windows Server 2008 Standard |  |  | Matthew.Fernandez@chubbfs.ca | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
Chubb CN | 1 | 2020-08-20 | 2020-09-24 |  | JDE Staging Server | CCAMOK0C |  |  |  |  | Canada |  |  | Windows Server 2012 R2 – 64bit |  |  | Matthew.Fernandez@chubbfs.ca | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
Chubb CN | 1 | 2020-08-20 | 2020-09-24 |  | User Home Drive | CCAMOF04 |  |  |  |  | Canada |  |  | Windows Server 2012 R2 - 64bit |  |  | Matthew.Fernandez@chubbfs.ca | [13 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[31 empty] | SSD |  | YES | [10 empty] | #REF! | #REF! |  | #REF! | [10 empty] | y
[44 empty] | #REF! | #REF! |  | #REF! |  | #NAME? | #NAME?
Note on D3: Microsoft Office User: Last day prior to remediation period from daptive
Note on D4: Microsoft Office User: Last day prior to remediation period from daptive
Note on D5: Microsoft Office User: Last day prior to remediation period from daptive
Note on D6: Microsoft Office User: Last day prior to remediation period from daptive
Note on C61: Microsoft Office User: Headstart because of fileshares and collaboration with UDM streamm
Note on F61: Microsoft Office User: To be merged with UDM stream
Note on C62: Microsoft Office User: Headstart because of fileshares and collaboration with UDM streamm
Note on F62: Microsoft Office User: To be merged with UDM stream
Note on C64: Microsoft Office User: Headstart because of fileshares and collaboration with UDM streamm
Note on F64: Microsoft Office User: To be merged with UDM stream
Note on A95: Microsoft Office User: to be handled with Unstructured Data workstream for File shares and Migrations stream for app server buildout
Note on A96: Microsoft Office User: to be handled with Unstructured Data workstream for File shares and Migrations stream for app server buildout
Note on A97: Microsoft Office User: to be handled with Unstructured Data workstream for File shares and Migrations stream for app server buildout
Note on A98: Microsoft Office User: to be handled with Unstructured Data workstream for File shares and Migrations stream for app server buildout
Note on A99: Microsoft Office User: to be handled with Unstructured Data workstream for File shares and Migrations stream for app server buildout
Note on A100: Microsoft Office User: to be handled with Unstructured Data workstream for File shares and Migrations stream for app server buildout
Note on A101: Microsoft Office User: to be handled with Unstructured Data workstream for File shares and Migrations stream for app server buildout
Note on A102: Microsoft Office User: to be handled with Unstructured Data workstream for File shares and Migrations stream for app server buildout
Note on A103: Microsoft Office User: to be handled with Unstructured Data workstream for File shares and Migrations stream for app server buildout
Note on A104: Microsoft Office User: to be handled with Unstructured Data workstream for File shares and Migrations stream for app server buildout
Note on A105: Microsoft Office User: to be handled with Unstructured Data workstream for File shares and Migrations stream for app server buildout
Note on A106: Microsoft Office User: to be handled with Unstructured Data workstream for File shares and Migrations stream for app server buildout
Note on A107: Microsoft Office User: to be handled with Unstructured Data workstream for File shares and Migrations stream for app server buildout

## aux
Release | Release | Wave | App | Server Name | FQDN | On-prem IP | Migrate to carcgl.com | DC/Site | No of CPU | Total Memory (GB) | OS Version | Server Type | App Owner | AWS Migration Team RDP access validation | Outbound TCP 443,1500 through Proxy | Target AWS account | Target AWS Account | Target EC2 Instance Type | EBS volume Type (Std, SSD, Provisioned) | EBS IOPS | EBS Encryption (Yes/No) | Target Subnet | Target Security Group | Target Private IP | Target Public IP or EIP | IAM Role | wave_id | app_name | cloudendure_projectname | aws_accountid | server_name | server_os | server_os_version | server_fqdn | server_tier | server_environment | subnet_IDs | securitygroup_IDs | subnet_IDs_test | securitygroup_IDs_test | instanceType | tenancy | ApplicationName | Server Name | Application ID | ApplicationOwner | BusinessUnit | Department | CostCenter | ServerType | ComplianceRequirement | Entity | Environment | Region | UsagePattern | MaxLifeTime | AppCat | Confirm Wave Plan with App Owner (AWS, Carrier) | Submit RFC and Schedule Change window (Carrier) | Complete migration factory intake form (AWS) | Import intake form in to Migration Factory (AWS) | Verify Source Server Pre-requisite (AWS) | Install CloudEndure agent (AWS) | (Optional) Push post-launch script (AWS, Carrier) | Verify CloudEndure replication status (AWS) | (Optional) Troubleshoot CloudEndure issues (AWS) | Validate local admin/sudo user on source machines (AWS, Carrier) | Launch server from migration factory and CloudEndure (AWS, Carrier) | Verify instance boot up status (AWS) | (Optional) Resolve instance boot up issues (AWS) | Validate cutover blueprint for Target instance type, disk IOPS, IP, SG,Subnet (AWS) | Terminate test instances (AWS) | Verify CloudEndure replication status (AWS) | Stop Service or shutdown source server for cutover (Carrier) | Launch instances for cutover (AWS) | Verify instance boot up status (AWS) | Test RDP/SSH access (AWS, Carrier) | (Optional) Clean up local admin/sudo after cutover (AWS) | Change DNS or other network settings for the application (Carrier) | Application Configuration Change/Network change (Carrier) | Post Cutover activities/ Application validation (App Owner) | Notes | Issues
R01 | R01 | R01W02 | HVACNA-TIDALQSA-IT-US-HVAC 6.2.1.848 - QA1 | CUSH0A01 | cush0a01.utccgl.com | 10.223.159.254 | Pending | HP MPC - Tulsa,OK |  |  | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger | [12 empty] | AWSCloudWatchAgentRole | [21 empty] | CCS | 104742
R01 | R01 | R01W02 | HVACNA-TIDALQSA-IT-US-HVAC 6.2.1.848 - QA1 | cush0a02 | cush0a02.utccgl.com | 10.223.159.252 | Pending | HP MPC - Tulsa,OK |  |  | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger | [12 empty] | AWSCloudWatchAgentRole | [21 empty] | CCS | 104742
R01 | R01 | R01W01 | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | cush0a03 | cush0a03.utccgl.com | 10.223.207.251 10.223.159.251 | Pending | HP MPC - Tulsa,OK | 2 | 128 | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger | Yes | No | 913828333602 | HAVC_Com_Prod | r5.4xlarge | Standard | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d |  |  | AWSCloudWatchAgentRole | R01W01 | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | HVAC_Com_Prod_913828333602 | 913828333602 | cush0a03 | windows | Microsoft Windows Server 2012 R2 Standard | cush0a03.utccgl.com | app | Production | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | subnet-04a5b0c4eff0b5e65 | sg-07d38644ed9df7a61 | r5.4xlarge | Shared | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | cush0a03 | 6335 | Tim Prueser | Commercial HVAC | CCS | 104742 | Application | NA | NA | PROD | us-east-1 | monthly (Monday after 3rd Sunday) 6 to 9PM (EST) | Indefinitely | Bronze
R01 | R01 | R01W03 | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | CUSH0A05 | CUSH0A05.utccgl.com | 10.223.159.247 | Pending | HP MPC - Tulsa,OK | 2 | 32 | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger | YES | No | 808538705328 | Fire_And_Security_Prod | r5.xlarge | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R01W03 | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 |  |  | CUSH0A05 | windows | Microsoft Windows Server 2012 R2 Standard | CUSH0A05.utccgl.com | App | Production |  |  |  |  | r5.xlarge | Shared | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | CUSH0A05 | 7047 | Jordan King | Fire & Security | CCS | 104742 | Application | NA | NA | PROD | us-east-1 | weekdays | indefinitely | BRONZE
R01 | R01 | R01W02 | HVACNA-TIDALQSA-IT-US-HVAC 6.2.1.848 - QA1 | CUSH0A06 | cush0a06.utccgl.com | 10.223.159.246 | Pending | HP MPC - Tulsa,OK |  |  | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger | [12 empty] | AWSCloudWatchAgentRole | [21 empty] | CCS | 104742
R01 | R01 | R01W01 | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | cush0a07 | cush0a07.utccgl.com | 10.223.207.245 10.223.159.245 | Pending | HP MPC - Tulsa,OK | 2 | 128 | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger | Yes | No | 913828333602 | HAVC_Com_Prod | r5.4xlarge | Standard | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d |  |  | AWSCloudWatchAgentRole | R01W01 | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | HVAC_Com_Prod_913828333602 | 913828333602 | cush0a07 | windows | Microsoft Windows Server 2012 R2 Standard | cush0a07.utccgl.com | app | Production | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | subnet-04a5b0c4eff0b5e65 | sg-07d38644ed9df7a61 | r5.4xlarge | Shared | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | cush0a07 | 6335 | Tim Prueser | Commercial HVAC | CCS | 104742 | Application | NA | NA | PROD | us-east-1 | monthly (Monday after 3rd Sunday) 6 to 9PM (EST) | Indefinitely | Bronze
R01 | R01 | R01W03 | GTS 8.08-Non Production | CUSH0A70 | cush0a70.utccgl.com | 10.223.152.10 | Pending | HP MPC - Tulsa,OK | 8 | 16 | Microsoft Windows Server 2012 R2 Datacenter | Rehost | Sarah Strominger | YES | No | 260780007980 | HVAC_Com_Preprod | c5.2xlarge | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R01W03 | GTS 8.08-Non Production |  |  | CUSH0A70 | windows | Microsoft Windows Server 2012 R2 Datacenter | cush0a70.utccgl.com | App | Stage |  |  |  |  | c5.2xlarge | Shared | GTS 8.08-Non Production | CUSH0A70 | NA | NA | Commercial HVAC | CCS-HPEMPC-15622800-00A-GTSNonProd (Offering: Archived - UTC Prod Windows Virtual- Comm) | 104742 | Application | NA | NA | STG | Us-east-1 | 24 Hous | Indefinitely | BRONZE
R01 | R01 | R01W04 | Development printer server | CUSH0A71 | cush0a71.utccgl.com | 10.223.152.11 | Pending | HP MPC - Tulsa,OK |  |  | Windows Server 2012 R2 Datacenter | Rehost | Sarah Strominger | [12 empty] | AWSCloudWatchAgentRole | R01W04 | [20 empty] | CCS-HPEMPC-16104274-00A-SAPPRINTNONPROD (Offering: Archived - UTC Prod Windows Virtual- Comm) | 104742
R01 | R01 | R01W03 | GTS 8.08-Production Secondary | CUSH0A76 | cush0a76.carcgl.com | 10.223.152.16 | Pending | HP MPC - Tulsa,OK | 8 | 16 | Microsoft Windows Server 2012 R2 Datacenter | Rehost | Sarah Strominger | Yes | No | 913828333602 | HAVC_Com_Prod | c5.2xlarge | Standard | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d |  |  | AWSCloudWatchAgentRole | R01W03 | GTS 8.08-Production Secondary | HVAC_Com_Prod_913828333602 | 913828333602 | CUSH0A76 | windows | Microsoft Windows Server 2012 R2 Datacenter | cush0a76.carcgl.com | App | Production | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | subnet-04a5b0c4eff0b5e65 | sg-07d38644ed9df7a61 | c5.2xlarge | Shared | GTS 8.08-Production Secondary | CUSH0A76 | NA | NA | Commercial HVAC | CCS-HPEMPC-15622784-00A-GTSRFSecondary (Offering: UTC Prod Windows Virtual - Comm) | 104742 | Application | NA | NA | PROD | us-east-1 | 24 Hous | Indefinitely | BRONZE
R01 | R01 | R01W01 | TomCat - dev | CUSH0A78 | cush0a78.utccgl.com | 10.223.152.14 | Pending | HP MPC - Tulsa,OK |  |  | Windows Server 2012 R2 Datacenter | Rehost | Sudesh Kadam | No | No | 436524867280 | HVAC_Com_Dev |  | Standard | N/A | YES | subnet-023516f902c3d8757 | sg-06b51bf12deaa479a |  |  | AWSCloudWatchAgentRole | R01W01 | TomCat - dev |  |  | CUSH0A78 | windows | Windows Server 2012 R2 Datacenter | cush0a78.utccgl.com | [7 empty] | Shared | TomCat - dev | CUSH0A78 | NA | NA | Commercial HVAC | CCS-HPEMPC- | 104742 | Application | NA | NA | DEV | us-east-1 | Weekdays | Indefinitely | Bronze
R01 | R01 | R01W02 | HVACNA-TIDALQSA-IT-US-HVAC 6.2.1.848 - QA1 | CUSH0D01 | cush0d01.utccgl.com | 10.223.159.253 | Pending | HP MPC - Tulsa,OK |  |  | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger | [12 empty] | AWSCloudWatchAgentRole | [21 empty] | CCS | 104742
R01 | R01 | R01W01 | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | CUSH0D02 | cush0d02.utccgl.com | 10.223.207.250 10.223.159.250 | Pending | HP MPC - Tulsa,OK | 2 | 32 | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger | Yes | No | 913828333602 | HAVC_Com_Prod | r5.xlarge | Standard | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d |  |  | AWSCloudWatchAgentRole | R01W01 | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | HVAC_Com_Prod_913828333602 | 913828333602 | CUSH0D02 | windows | Microsoft Windows Server 2012 R2 Standard | cush0d02.utccgl.com | app | Production | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | subnet-04a5b0c4eff0b5e65 | sg-07d38644ed9df7a61 | r5.xlarge | Shared | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | CUSH0D02 | 6335 | Tim Prueser | Commercial HVAC | CCS | 104742 | Application | NA | NA | PROD | us-east-1 | monthly (Monday after 3rd Sunday) 6 to 9PM (EST) | Indefinitely | Bronze
R01 | R01 | R01W04 | Production printer server | CUSH0P01 | cush0p01.utccgl.com | 10.223.152.5 | Pending | HP MPC - Tulsa,OK |  |  | Windows Server 2012 R2 Datacenter | Rehost | Sarah Strominger | [12 empty] | AWSCloudWatchAgentRole | R01W04 | [20 empty] | CCS-DXCMPC-19357990-00A-SAP_PRINTSecondary (Offering: UTC Prod Windows Virtual - Comm) | 104742
R01 | R01 | R01W03 | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | CUSH1A01 | cush1a01.utccgl.com | 10.223.31.254 | Pending | HP MPC - Alpharetta,GA | 2 | 128 | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger | YES | No | 913828333602 | HAVC_Com_Prod | r5.4xlarge | Standard | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d |  |  | AWSCloudWatchAgentRole | R01W03 | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | HVAC_Com_Prod_913828333602 | 913828333602 | CUSH1A01 | windows | Microsoft Windows Server 2012 R2 Standard | cush1a01.utccgl.com |  | Production | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | subnet-04a5b0c4eff0b5e65 | sg-07d38644ed9df7a61 | r5.4xlarge | Shared | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | CUSH1A01 | 6335 | Tim Prueser | Commercial HVAC | CCS | 104742 | Application | NA | NA | PROD | us-east-1 | NA | Indefinitely | BRONZE
R01 | R01 | R01W03 | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | CUSH1A02 | CUSH1A02.utccgl.com | 10.223.31.252 | Pending | HP MPC - Alpharetta,GA | 2 | 256 | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger | YES | No | 913828333602 | HAVC_Com_Prod | r5.8xlarge | Standard | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d |  |  | AWSCloudWatchAgentRole | R01W03 | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | HVAC_Com_Prod_913828333602 | 913828333602 | CUSH1A02 | windows | Microsoft Windows Server 2012 R2 Standard | CUSH1A02.utccgl.com |  | Production | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | subnet-04a5b0c4eff0b5e65 | sg-07d38644ed9df7a61 | r5.8xlarge | Shared | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | CUSH1A02 | 6335 | Tim Prueser | Commercial HVAC | CCS | 104742 | Application | NA | NA | PROD | us-east-1 | NA | Indefinitely | BRONZE
R01 | R01 | R01W01 | Approva 10.1.6.0007 | CUSH1AT3 | cush1at3.utccgl.com | 10.223.72.4 10.223.24.2 | Pending | HP MPC - Alpharetta,GA | 4 | 8 | Microsoft Windows Server 2012 R2 Datacenter | Rehost | Sarah Strominger | Yes | No | 913828333602 | HAVC_Com_Prod | c5.xlarge | Standard | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d |  |  | AWSCloudWatchAgentRole | R01W01 | Approva 10.1.6.0007 | HVAC_Com_Prod_913828333602 | 913828333602 | CUSH1AT3 | windows | Microsoft Windows Server 2012 R2 Datacenter | cush1at3.utccgl.com | app | Production | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | subnet-04a5b0c4eff0b5e65 | sg-07d38644ed9df7a61 | c5.xlarge | Shared | Approva 10.1.6.0007 | CUSH1AT3 | 5984 | Tim Prueser | Commercial HVAC | CCS-HPEMPC-15071868-00A-Approva (Offering: Archived - UTC Prod Windows Virtual- Comm) | 104742 | Application | NA | NA | PROD | us-east-1 | Weekdays | Indefinitely | Bronze
Pilot | R01 | R01W01 | General Test | CUSH1AV8 | cush1av8.utccgl.com | 10.223.24.7 | complete | HP MPC - Alpharetta,GA | 2 | 4 | Windows Server 2012 R2 Datacenter | Rehost | Jordan King | Yes | Yes | 260780007980 | Fire_And_Security_PreProd | t2.medium/ t3a.medium | standard | N/A | YES | subnet-06de97b914fec4d10 | sg-0ac65d65a7d551733 | 10.233.9.142 | N/A | AWSCloudWatchAgentRole | Pilot | General Test | Fire_And_Security_PreProd_917128996017 | 260780007980 | CUSH1AV8 | windows | Windows Server 2012 R2 Datacenter | cush1av8.utccgl.com | app | test | subnet-06de97b914fec4d10 | sg-0ac65d65a7d551733 | [subnet-0f866e16dd1977655] | sg-06bf1dfeb43c97567 | t2.medium/ t3a.medium | Shared | General Test | CUSH1AV8 | NA | Jordan King | Fire & Security | CCS-HPEMPC-15736948-00A?DevCodeCollab (Offering: Archived - UTC Prod Windows Virtual- Comm) | IC990447 | Application | NA | NA | TST | us-east-1 | Weekdays | Indefinitely | BRONZE | complete -26th May 2020 | 2020-05-18 | complete - 27th May 2020 | complete - 27th May 2020 | In-Progress - 28th May 2020 | Yet to start -27th May 2020 | Yet to Start - 1st June 2020 | Yet to Start - 2nd June 2020 | Yet to Start - 2nd June 2020 | Yet to Start - 3nd June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020
R01 | R01 | R01W03 | GTS 8.08-Production Primary | cush1aw5 | CUSH1AW5.carcgl.com | 10.223.24.16 | Pending | HP MPC - Alpharetta,GA | 8 | 16 | Microsoft Windows Server 2012 R2 Datacenter | Rehost | Sarah Strominger | Yes | No | 913828333602 | HAVC_Com_Prod | c5.2xlarge | Standard | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d |  |  | AWSCloudWatchAgentRole | R01W03 | GTS 8.08-Production Primary | HVAC_Com_Prod_913828333602 | 913828333602 | cush1aw5 | windows | Microsoft Windows Server 2012 R2 Datacenter | CUSH1AW5.carcgl.com | App | Production | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | subnet-04a5b0c4eff0b5e65 | sg-07d38644ed9df7a61 | c5.2xlarge | Shared | GTS 8.08-Production Primary | cush1aw5 | NA | NA | Commercial HVAC | CCS-HPEMPC-15622746-00A-GTSRFPrimary (Offering: UTC Prod Windows Virtual - Comm) | 104742 | Application | NA | NA | PROD | us-east-1 | 24 Hous | Indefinitely | BRONZE
R01 | R01 | R01W01 | Klocworks | cush1ax3 | cush1ax3.utccgl.com | 10.223.72.20 10.223.24.20 | Pending | HP MPC - Alpharetta,GA | 8 | 16 | Microsoft Windows Server 2016 Datacenter | Rehost | Jordan King | Yes |  | 808538705328 | Fire_And_Security_Prod | c5.2xlarge | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R01W01 | Klocworks |  | 808538705328 | cush1ax3 | windows | Microsoft Windows Server 2016 Datacenter | cush1ax3.utccgl.com | app | Production |  |  |  |  | c5.2xlarge | Shared | Klocworks | cush1ax3 | 7047 | Jordan King | Fire & Security | CCS-HPEMPC-16939911-00A?EngineeringDevelopment (Offering: Archived - UTC Prod Windows Virtual - Comm) | IC990447 | Application | NA | NA | PROD | us-east-1 | Weekdays | Indefinitely | Bronze | 43972 | 43973 | 43973 | 43976 | 43977 | 43977 | 43977 | 43979 | 43979 | 43979 | 43990 | 43990 | 43990 | 43990 | 43990 | 43993 | 43993 | 43993 | 43993 | 43993 | 43993 | 43993 | 43993
R01 | R01 | R01W01 | LiveCompare | CUSH1AY3 | cush1ay3.utccgl.com | 10.223.24.29 10.223.72.29 | Pending | HP MPC - Alpharetta,GA | 8 | 32 | Microsoft Windows Server 2016 Datacenter | Rehost | Sarah Strominger | Yes | No | 913828333602 | HAVC_Com_Prod | m5.2xlarge | Standard | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d |  |  | AWSCloudWatchAgentRole | R01W01 | LiveCompare | HVAC_Com_Prod_913828333602 | 913828333602 | CUSH1AY3 | windows | Microsoft Windows Server 2016 Datacenter | cush1ay3.utccgl.com | app | Production | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | subnet-04a5b0c4eff0b5e65 | sg-07d38644ed9df7a61 | m5.2xlarge | Shared | LiveCompare | CUSH1AY3 | 8899 | Tim Prueser, Sarah Strominger | Commercial HVAC | CCS-HPEMPC-17778726-00A-LIVECOMPARE (Offering: Archived - UTC Prod Windows Virtual - Comm) | 104742 | Application | NA | NA | PROD | us-east-1 | Weekdays | Indefinitely | Bronze
R01 | R01 | R01W03 | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | CUSH1AY4 | cush1ay4.utccgl.com | 10.223.24.30 | Pending | HP MPC - Alpharetta,GA | 8 | 128 | Microsoft Windows Server 2012 R2 Datacenter | Rehost | Sarah Strominger | YES | No | 913828333602 | HAVC_Com_Prod | r5.4xlarge | Standard | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d |  |  | AWSCloudWatchAgentRole | R01W03 | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | HVAC_Com_Prod_913828333602 | 913828333602 | CUSH1AY4 | windows | Microsoft Windows Server 2012 R2 Datacenter | cush1ay4.utccgl.com |  | Production | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | subnet-04a5b0c4eff0b5e65 | sg-07d38644ed9df7a61 | r5.4xlarge | Shared | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | CUSH1AY4 | NA | NA | Commercial HVAC | CCS-HPEMPC-17839207-00A-TIDALJUMP (Offering: Archived - UTC Prod Windows Virtual - Comm) | 104742 | Application | NA | NA | PROD | us-east-1 | NA | Indefinitely | BRONZE
R01 | R01 | R01W03 | Uperform 5.20.9 | cush1ay5 | cush1ay5.utccgl.com | 10.223.24.32 | Pending | HP MPC - Alpharetta,GA | 8 | 16 | Microsoft Windows Server 2016 Datacenter | Rehost | Sarah Strominger | YES | No |  |  | c5.2xlarge | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R01W03 | Uperform 5.20.9 |  |  | cush1ay5 | windows | Microsoft Windows Server 2016 Datacenter | cush1ay5.utccgl.com | [6 empty] | c5.2xlarge | Shared | Uperform 5.20.9 | cush1ay5 | NA | NA |  | CCS-DXCMPC-17929643-00A-UPERFORM (Offering: Archived - UTC Prod Windows Virtual - Comm) | 104742 | Application | NA | NA |  | us-east-1 | NA | Indefinitely | BRONZE
R01 | R01 | R01W03 | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | cush1d01 | cush1d01.utccgl.com | 10.223.31.253 | Pending | HP MPC - Alpharetta,GA | 2 | 32 | Microsoft Windows Server 2012 R2 Standard | Rehost | Sarah Strominger | YES | No | 913828333602 | HAVC_Com_Prod | r5.xlarge | Standard | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d |  |  | AWSCloudWatchAgentRole | R01W03 | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | HVAC_Com_Prod_913828333602 | 913828333602 | cush1d01 | windows | Microsoft Windows Server 2012 R2 Standard | cush1d01.utccgl.com |  | Production | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | subnet-04a5b0c4eff0b5e65 | sg-07d38644ed9df7a61 | r5.xlarge | Shared | HVACNA-SAP-ERP-US-HVAC ECC 6 EHP 5 | cush1d01 | NA | NA | Commercial HVAC | CCS | 104742 | Application | NA | NA | PROD | us-east-1 | NA | Indefinitely | BRONZE
R01 | R01 | R01W01 | Approva 10.1.6.0007 | CUSH1D06 | cush1d06.utccgl.com | 10.223.72.5 10.223.24.3 | Pending | HP MPC - Alpharetta,GA | 8 | 16 | Microsoft Windows Server 2012 R2 Datacenter | Rehost | Sarah Strominger | Yes | No | 913828333602 | HAVC_Com_Prod | c5.2xlarge | Standard | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d |  |  | AWSCloudWatchAgentRole | R01W01 | Approva 10.1.6.0007 | HVAC_Com_Prod_913828333602 | 913828333602 | CUSH1D06 | windows | Microsoft Windows Server 2012 R2 Datacenter | cush1d06.utccgl.com | app | Production | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | subnet-04a5b0c4eff0b5e65 | sg-07d38644ed9df7a61 | c5.2xlarge | Shared | Approva 10.1.6.0007 | CUSH1D06 | 5984 | Tim Prueser | Commercial HVAC | CCS-HPEMPC-15071868-01A-ApprovaDB (Offering: Archived - UTC Prod Windows Virtual- Comm) | 104742 | Application | NA | NA | PROD | us-east-1 | Weekdays | Indefinitely | Bronze
R01 | R01 | R01W03 | Uperform 5.20.9 | cush1d17 | cush1d17.utccgl.com | 10.223.24.31 | Pending | HP MPC - Alpharetta,GA | 8 | 16 | Microsoft Windows Server 2016 Datacenter | Rehost | Sarah Strominger | YES | No |  |  | c5.2xlarge | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R01W03 | Uperform 5.20.9 |  |  | cush1d17 | windows | Microsoft Windows Server 2016 Datacenter | cush1d17.utccgl.com | [6 empty] | c5.2xlarge | Shared | Uperform 5.20.9 | cush1d17 | NA | NA |  | CCS-HPEMPC-17929680-00A-UPERFORM (Offering: Archived - UTC Prod Windows Virtual - Comm) | 104742 | Application | NA | NA |  | us-east-1 | NA | Indefinitely | BRONZE
R01 | R01 | R01W04 | Production printer server | CUSH1P01 | cush1p01.utccgl.com | 10.223.24.18 | Pending | HP MPC - Alpharetta,GA |  |  | Windows Server 2012 R2 Datacenter | Rehost | Sarah Strominger | [12 empty] | AWSCloudWatchAgentRole | R01W04 | [20 empty] | CCS-DXCMPC-19356397-00A-SAP_PRINTPrimary (Offering: UTC Prod Windows Virtual - Comm) | 104742
R01 | R01 | R01W03 | Uperform 5.20.9 | cush1w04 | cush1w04.utccgl.com | 10.223.24.27 | Pending | HP MPC - Alpharetta,GA | 8 | 16 | Microsoft Windows Server 2016 Datacenter | Rehost | Sarah Strominger | YES | No |  |  | c5.2xlarge | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R01W03 | Uperform 5.20.9 |  |  | cush1w04 | windows | Microsoft Windows Server 2016 Datacenter | cush1w04.utccgl.com | [6 empty] | c5.2xlarge | Shared | Uperform 5.20.9 | cush1w04 | NA | NA |  | CCS-HPEMPC-17929750-00A-UPERFORM (Offering: Archived - UTC Prod Windows Virtual - Comm) | 104742 | Application | NA | NA |  | us-east-1 | NA | Indefinitely | BRONZE
| R02 | R02W01 | Carrier DEBTS - NonProd | cusmna07 | cusmna07.carcgl.com | 159.82.227.236 | complete | Meriden | 8 | 64 | Microsoft Windows Server 2016 Standard | Rehost | Tracy Jones and Jon Ascher | Yes | TBV | 890585303181 | Fire_And_Security_Dev | r5.2xlarge | Standard | N/A | YES | subnet-0c6533ebaf5f1b1a2 | sg-05d2d8a7449289f9e |  | N/A | AWSCloudWatchAgentRole | R02W01 | Carrier DEBTS - NonProd | Fire_And_Security_Dev_890585303181 | 890585303181 | cusmna07 | windows | Microsoft Windows Server 2016 Standard | cusmna07.carcgl.com | app | dev | subnet-0c6533ebaf5f1b1a2 | sg-05d2d8a7449289f9e | subnet-0c6533ebaf5f1b1a2 | sg-09876514db5a00fb8 | r5.2xlarge | Shared | Carrier DEBTS - NonProd | cusmna07 | 5932 | Michael Derken | Fire_And_Security_Dev |  | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | Bronze
| R02 | R02W01 | Carrier PayCzar - NonProd | cusmna07 | cusmna07.carcgl.com | 159.82.227.236 | complete | Meriden | 8 | 64 | Microsoft Windows Server 2016 Standard | Rehost | Tracy Jones and Jon Ascher | Yes | TBV | 890585303181 | Fire_And_Security_Dev | r5.2xlarge | Standard | N/A | YES | subnet-0c6533ebaf5f1b1a2 | sg-05d2d8a7449289f9e |  | N/A | AWSCloudWatchAgentRole | R02W01 | Carrier PayCzar - NonProd | Fire_And_Security_Dev_890585303181 | 890585303181 | cusmna07 | windows | Microsoft Windows Server 2016 Standard | cusmna07.carcgl.com | app | dev | subnet-0c6533ebaf5f1b1a2 | sg-05d2d8a7449289f9e | subnet-0c6533ebaf5f1b1a2 | sg-09876514db5a00fb8 | r5.2xlarge | Shared | Carrier PayCzar - NonProd | cusmna07 | 6346 | Michael Derken | Fire_And_Security_Dev |  | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | Bronze
| R02 | R02W01 | DoubleTake /Rapid Reconciler Kidde/Edwards | CUSMNA08 | cusmna08.fs.utc.com | 159.82.226.70 | Pending | Meriden | 6 | 32 | Microsoft Windows Server 2008 R2 Standard | Rehost | Chris Marshall, Andrew Warner | Yes | Yes | 808538705328 | Fire_And_Security_Prod | m5.2xlarge | Standard | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 |  | N/A | AWSCloudWatchAgentRole | R02W01 | DoubleTake PD | Fire_And_Security_Prod_808538705328 | 808538705328 | CUSMNA08 | windows | Microsoft Windows Server 2008 R2 Standard | cusmna08.fs.utc.com | app | Production | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | subnet-085227562c4baaf92 | sg-03d765951f2e6d249 | m5.2xlarge | Shared | DoubleTake /Rapid Reconciler Kidde/Edwards | CUSMNA08 | 7033 | Chris Marshall, Andrew Warner | Fire_And_Security_Prod | FS-00100 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | Bronze
| R02 | R02W01 | Subversion Kidde/Edwards,GFP Subversion | CUSMNA0V | cusmna0v.fs.utc.com | 159.82.226.13 | Pending | Meriden | 4 | 16 | Microsoft Windows Server 2008 R2 Standard | Rehost | Jordan King | Yes | Yes | 808538705328 | Fire_And_Security_Prod | m5.xlarge | Standard | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 |  | N/A | AWSCloudWatchAgentRole | R02W01 | Subversion Kidde/Edwards,GFP Subversion | Fire_And_Security_Prod_808538705328 | 808538705328 | CUSMNA0V | windows | Microsoft Windows Server 2008 R2 Standard | cusmna0v.fs.utc.com | app | Production | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | subnet-085227562c4baaf92 | sg-03d765951f2e6d249 | m5.xlarge | Shared | Subversion Kidde/Edwards,GFP Subversion | CUSMNA0V | 7048. 1940 | Jordan King | Fire_And_Security_Prod | CASS-INTLX | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | Bronze
| R02 | R02W01 | KF - Dynamics CRM / FireEye | CUSMNA0W | cusmna0w.fs.utc.com | 159.82.226.28 | Pending | Meriden | 2 | 8 | Microsoft Windows Server 2008 R2 Standard | Rehost | Scot Sanborn | Yes | Yes | 808538705328 | Fire_And_Security_Prod | m5.large | Standard | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 |  | N/A | AWSCloudWatchAgentRole | R02W01 | KF - Dynamics CRM / FireEye | Fire_And_Security_Prod_808538705328 | 808538705328 | CUSMNA0W | windows | Microsoft Windows Server 2008 R2 Standard | cusmna0w.fs.utc.com | app/db | Production | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | subnet-04a5b0c4eff0b5e65 | sg-03d765951f2e6d249 | m5.large | Shared | KF - Dynamics CRM / FireEye | CUSMNA0W | 6167 | Scot Sanborn | Fire_And_Security_Prod | KFEN-14 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | Bronze
R02 | R02 | R02W02 | Production planning system | CUSMNA12 | cusmna12.na.1utcfs.com | 159.82.226.141 | Pending | Meriden | 2 | 8 | Windows Server 2008 R2 Standard | Rehost | Alejandro Martinez Arora Prateek |  |  |  |  | m5.large | [7 empty] | AWSCloudWatchAgentRole | R02W02 | [15 empty] | Production planning system | CUSMNA12 | n/a | ALEJANDRO A MARTINEZ | FIRE AND SECURITY | 3899 | 104742 | Application | n/a | n/a | PROD | n/a | n/a | n/a | n/a
R02 | R02 | R02W02 | Canon Printer Server | CUSMNA12 | cusmna12.na.1utcfs.com | 159.82.226.141 | Pending | Meriden | 2 | 8 | Windows Server 2008 R2 Standard | Rehost | Alejandro Martinez Arora Prateek |  |  |  |  | m5.large | [7 empty] | AWSCloudWatchAgentRole | R02W02 | [15 empty] | Canon Printer Server | CUSMNA12 | n/a | ALEJANDRO A MARTINEZ | FIRE AND SECURITY | 3899 | 104742 | Application | n/a | n/a | PROD | n/a | n/a | n/a | n/a
R02 | R02 | R02W02 | JONAS - DR | CUSMNA1B | cusmna1b.utccgl.com | 159.82.226.66 | Pending | Meriden | 4 | 8 | Windows Server 2008 R2 Standard | Rehost | Randy Durocher |  |  |  |  | c5.xlarge | [7 empty] | AWSCloudWatchAgentRole | R02W02 | [15 empty] | JONAS - DR | CUSMNA1B | 6316 | Randy Durocher | Commercial HVAC | 3899 | 104742 | Application | n/a | n/a | PROD | n/a | n/a | n/a | n/a
| R02 | R02W01 | Mgmt Tools | CUSMNA1I | CUSMNA1I.carcgl.com | 159.82.227.3 | complete | Meriden | 8 | 32 | Microsoft Windows Server 2016 Standard | Rehost | Guy Julian, Ed Amelchenko, Chintan Khambholja, Devon Varner | Yes | TBV | 913828333602 | HAVC_Com_Prod | m5.2xlarge | Standard | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d |  | N/A | AWSCloudWatchAgentRole | R02W01 | Mgmt Tools | HVAC_Com_Prod_913828333602 | 913828333602 | CUSMNA1I | windows | Microsoft Windows Server 2016 Standard | CUSMNA1I.carcgl.com | app | Production | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | subnet-04a5b0c4eff0b5e65 | sg-07d38644ed9df7a61 | m5.2xlarge | shared | Mgmt Tools | CUSMNA1I | 4615 | Guy Julian, Ed Amelchenko, Chintan Khambholja, Devon Varner | HAVC_Com_Prod | 9712 | 109712 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | Bronze
| R02 | R02W01 | So99 | CUSMND01 | cusmnd01.carcgl.com | 159.82.226.23 | complete | Meriden | 8 | 32 | Microsoft Windows Server 2016 Standard | Rehost | Jeff Turner | Yes | Yes | 808538705328 | Fire_And_Security_Prod | m5.2xlarge | Standard | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 |  | N/A | AWSCloudWatchAgentRole | R02W01 | So99 | Fire_And_Security_Prod_808538705328 | 808538705328 | CUSMND01 | windows | Microsoft Windows Server 2016 Standard | cusmnd01.carcgl.com | app/db | Production | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | subnet-085227562c4baaf92 | sg-03d765951f2e6d249 | m5.2xlarge | Shared | So99 | CUSMND01 | 5932 | Jeff Turner | Fire_And_Security_Prod | FS-00100 | IC990447 | Application | NA | NA | Production | us-east-1 | NA | indefinitely | Bronze
| R02 | R02W01 | KF - DoubleTake | CUSMND0E | CUSMND0E.carcgl.com | 159.82.226.87 | complete | Meriden | 2 | 16 | Microsoft Windows Server 2008 R2 Standard | Rehost | Mauro Ciccarelli | Yes | Yes | 808538705328 | Fire_And_Security_Prod | r5.large | Standard | N/A | YES | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 |  | N/A | AWSCloudWatchAgentRole | R02W01 | KF - DoubleTake | Fire_And_Security_Prod_808538705328 | 808538705328 | CUSMND0E or cusmnk17 | windows | Microsoft Windows Server 2008 R2 Standard | CUSMND0E.carcgl.com | app | Production | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | subnet-085227562c4baaf92 | sg-03d765951f2e6d249 | r5.large | Shared | KF - DoubleTake | CUSMND0E or cusmnk17 | 6157 | Mauro Ciccarelli | Fire_And_Security_Prod | FS-00103 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | Bronze
R02 | R02 | R02W02 | Production planning system | CUSMND0L | cusmnd0l.na.1utcfs.com | 159.82.226.140 | Pending | Meriden | 2 | 8 | Windows Server 2008 R2 Standard | Rehost | Alejandro Martinez Zamora Armando |  |  |  |  | m5.large | [7 empty] | AWSCloudWatchAgentRole | R02W02 | [15 empty] | Production planning system | CUSMND0L | n/a | ALEJANDRO A MARTINEZ | FIRE AND SECURITY | 3899 | 104742 | Application | n/a | n/a | PROD | n/a | n/a | n/a | n/a
R02 | R02 | R02W02 | Automated Data ETL (SSIS & Other) | CUSMND0M | cusmnd0m.fs.utc.com | 159.82.226.77 | Pending | Meriden | 4 | 16 | Windows Server 2008 R2 Enterprise | Rehost | Jeff Turner |  |  |  |  | m5.xlarge | [7 empty] | AWSCloudWatchAgentRole | R02W02 | [15 empty] | Automated Data ETL (SSIS & Other) | CUSMND0M | 7018 | Jeff Turner | Fire and Security Prod | IC990260 | IC990447 | Application | n/a | n/a | PROD | n/a | n/a | n/a | n/a
R02 | R02 | R02W02 | Case Manager Web Application | CUSMND0M | cusmnd0m.fs.utc.com | 159.82.226.77 | Pending | Meriden | 4 | 16 | Windows Server 2008 R2 Enterprise | Rehost | Jeff Turner |  |  |  |  | m5.xlarge | [7 empty] | AWSCloudWatchAgentRole | R02W02 | [15 empty] | Case Manager Web Application | CUSMND0M | 7020 | Jeff Turner | Fire and Security Prod | IC990260 | IC990447 | Application | n/a | n/a | PROD | n/a | n/a | n/a | n/a
R02 | R02 | R02W02 | EDI Support Site | CUSMND0M | cusmnd0m.fs.utc.com | 159.82.226.77 | Pending | Meriden | 4 | 16 | Windows Server 2008 R2 Enterprise | Rehost | Jeff Turner |  |  |  |  | m5.xlarge | [7 empty] | AWSCloudWatchAgentRole | R02W02 | [15 empty] | EDI Support Site | CUSMND0M | 7015 | Jeff Turner | Fire and Security Prod | IC990260 | IC990447 | Application | n/a | n/a | PROD | n/a | n/a | n/a | n/a
R02 | R02 | R02W02 | Kidde/Edwards Data Warehouse Reporting | CUSMND0M | cusmnd0m.fs.utc.com | 159.82.226.77 | Pending | Meriden | 4 | 16 | Windows Server 2008 R2 Enterprise | Rehost | Jeff Turner |  |  |  |  | m5.xlarge | [7 empty] | AWSCloudWatchAgentRole | R02W02 | [15 empty] | Kidde/Edwards Data Warehouse Reporting | CUSMND0M | 7034 | Jeff Turner | Fire and Security Prod | IC990260 | IC990447 | Application | n/a | n/a | PROD | n/a | n/a | n/a | n/a
R03 | R03 | R03W01 | Doubletake PY | CUSMND0O |  |  | Pending | Newington |  |  | Microsoft Windows Server 2016 | Rehost | Jeff Turner, Chris Marshall | [12 empty] | AWSCloudWatchAgentRole | R03W01 | [20 empty] | FS-00100 | IC990447
| R02 | R02W01 | HVACNA-WORKSOFT-IT-US-HVACRCS 10.0.0.995 | CUSMNK06 | cusmnk06.utccgl.com | 159.82.227.2 | Pending | Meriden | 2 | 4 | Microsoft Windows Server 2016 Standard | Rehost | Judy Zeman | Yes | TBV | 913828333602 | HAVC_Com_Prod | c5.large | Standard | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d |  | N/A | AWSCloudWatchAgentRole | R02W01 | HVACNA-WORKSOFT-IT-US-HVACRCS 10.0.0.995 | HVAC_Com_Prod_913828333602 | 913828333602 | CUSMNK06 | windows | Microsoft Windows Server 2016 Standard | cusmnk06.utccgl.com | app | Production | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | subnet-04a5b0c4eff0b5e65 | sg-07d38644ed9df7a61 | c5.large | Shared | HVACNA-WORKSOFT-IT-US-HVACRCS 10.0.0.995 | CUSMNK06 | 6346 | Judy Zeman | HAVC_Com_Prod | 4731 | 104742 | Application | NA | NA | Production | us-east-1 | NA | indefinitely | Bronze
R02 | R02 | R02W02 | Case Manager Web Application | CUSMNK0O | cusmnk0o.fs.utc.com | 159.82.226.112 | Pending | Meriden | 1 | 8 | Windows Server 2008 R2 Standard | Rehost | Jeff Turner |  |  |  |  | m5.large | [7 empty] | AWSCloudWatchAgentRole | R02W02 | [15 empty] | Case Manager Web Application | CUSMNK0O | 7020 | Jeff Turner | FIRE AND SECURITY | FS-00100 | IC990447 | Application | n/a | n/a | PROD | n/a | n/a | n/a | n/a
R02 | R02 | R02W02 | EDI Support Site | CUSMNK0O | cusmnk0o.fs.utc.com | 159.82.226.112 | Pending | Meriden | 1 | 8 | Windows Server 2008 R2 Standard | Rehost | Jeff Turner |  |  |  |  | m5.large | [7 empty] | AWSCloudWatchAgentRole | R02W02 | [15 empty] | EDI Support Site | CUSMNK0O | 7015 | Jeff Turner | FIRE AND SECURITY | FS-00100 | IC990447 | Application | n/a | n/a | PROD | n/a | n/a | n/a | n/a
PIlot | Pilot | Pilot | Kidde Safety Meriden (9888) - TEST | CUSMNK0P | cusmnk0p.carcgl.com | 159.82.226.99 | complete | Meriden | 2 | 4 | Windows Server 2008 R2 Standard | Rehost | Chris Marshall | Yes | Yes | 260780007980 | Fire_And_Security_PreProd | t2.medium | standard | N/A | YES | subnet-0dd905d5c0776f8ac | sg-0a08dc8c96199a489 | 10.233.153.141 | N/A | AWSCloudWatchAgentRole | Pilot | General Test | Fire_And_Security_PreProd_917128996017 | 260780007980 | cusmnk0p | Windows | Windows Server 2008 R2 Standard | cusmnk0p.carcgl.com | app | test | subnet-0dd905d5c0776f8ac | sg-0a08dc8c96199a489 | subnet-0dd905d5c0776f8ac | sg-0104099b41897670f | t2.medium | Shared | Kidde Safety Meriden (9888) - TEST | cush1ax3 | NA | Chris Marshall | Fire & Security | FS-00100 | IC990447 | Application | NA | NA | TST | us-east-1 | Weekdays | Indefinitely | BRONZE | complete -26th May 2020 | Optional | complete - 27th May 2020 | complete - 27th May 2020 | In-Progress - 28th May 2020 | Yet to start -27th May 2020 | Yet to Start - 1st June 2020 | Yet to Start - 2nd June 2020 | Yet to Start - 2nd June 2020 | Yet to Start - 3nd June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020
| R02 | R02W01 | RCS Newington (BI 4) - QA | cusmnk17 | cusmnk17.carrier.utc.com | 159.82.226.238 | Pending | Meriden |  |  | Linux - OEL 6.x | Replatform | Phillip Pascoe | No | TBV | 823570924226 | HVAC_Res_Preprod |  | Standard | N/A | YES | subnet-034c5b1f10a32deaf | sg-0eb6d6c9b2ca6e16c |  | N/A | AWSCloudWatchAgentRole | R02W01 | RCS Newington (BI 4) - QA | #ERROR! | 823570924226 | cusmnk17 | linux | Linux - OEL 6.x | cusmnk17.carrier.utc.com | app | pre-prod | subnet-034c5b1f10a32deaf | sg-0eb6d6c9b2ca6e16c | subnet-034c5b1f10a32deaf | sg-044e1966a2ef361df |  | shared | RCS Newington (BI 4) - QA | cusmnk17 |  | Phillip Pascoe, Craig Tiroff | HVAC_Res_Preprod | CASS-INTLX | IC990447 | Application | NA | NA | pre-prod | Us-east-1 | NA | indefinitely | Bronze
| R02 | R02W01 | RCS Newington (SAP DW) - QA | cusmnk17 | cusmnk17.carrier.utc.com | 159.82.226.238 | Pending | Meriden |  |  | Linux - OEL 6.x | Replatform | Phillip Pascoe | No | TBV | 823570924226 | HVAC_Res_Preprod |  | Standard | N/A | YES | subnet-034c5b1f10a32deaf | sg-0eb6d6c9b2ca6e16c |  | N/A | AWSCloudWatchAgentRole | R02W01 | RCS Newington (SAP DW) - QA | #ERROR! | 823570924226 | cusmnk17 | linux | Linux - OEL 6.x | cusmnk17.carrier.utc.com | app | pre-prod | subnet-034c5b1f10a32deaf | sg-0eb6d6c9b2ca6e16c | subnet-034c5b1f10a32deaf | sg-044e1966a2ef361df |  | shared | RCS Newington (SAP DW) - QA | cusmnk17 |  | Phillip Pascoe, Craig Tiroff | HVAC_Res_Preprod | CASS-INTLX | IC990447 | Application | NA | NA | pre-prod | Us-east-1 | NA | indefinitely | Bronze
| R02 | R02W01 | ComfortChoice | CUSMNW0E | cusmnw0e.utccgl.com | 159.82.226.245 | Pending | Meriden | 2 | 4 | Microsoft Windows Server 2012 R2 Standard | Rehost | Mehmood Syed and John Kozlowski | Yes | TBV | 436524867280 | HVAC_Com_Dev | c5.large | Standard | N/A | YES | subnet-00a9966005a386acb | sg-0765e3df2626173e2 |  | N/A | AWSCloudWatchAgentRole | R02W01 | ComfortChoice | HVAC_Com_Dev_436524867280 | 436524867280 | CUSMNW0E | windows | Microsoft Windows Server 2012 R2 Standard | cusmnw0e.utccgl.com | app | dev | subnet-00a9966005a386acb | sg-0765e3df2626173e2 | subnet-00a9966005a386acb | sg-0c55b9769612daba9 | c5.large | Shared | ComfortChoice | CUSMNW0E | 7033 | Syed, Mehmood | HVAC_Com_Dev | 3525 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | Bronze
R03 | R03 | R03W02 | Webtime and HRIS - Prod | CUSNWA2A |  |  | Pending | Newington |  |  | Microsoft Windows Server 2016 Standard | Rehost | Venkatagopi Somaraju, James D McGill | [12 empty] | AWSCloudWatchAgentRole | R03W02 | Webtime and HRIS - Prod |  |  | CUSNWA2A | windows | Microsoft Windows Server 2016 Standard |  |  | Production | [6 empty] | Webtime and HRIS - Prod | CUSNWA2A | NA | Venkatagopi Somaraju, James D McGill | NA | 9755 | 109755 | Application | NA | NA | NA | Us-east-1 | NA | NA | Bronze
R03 | R03 | R03W03 | WHQ Engineering (Windchill) | CUSNWA2Z | CUSNWA2Z.utccgl.com | 10.177.6.218 | Pending | Newington | 8 | 24 | Windows Server 2012 R2 Standard | Rehost | John Macpherson | Yes | No |  |  | m5.2xlarge | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W03 | WHQ Engineering (Windchill) |  |  | CUSNWA2Z | Windows | Windows Server 2012 R2 Standard | CUSNWA2Z.utccgl.com |  | production | [5 empty] | Shared | WHQ Engineering (Windchill) | CUSNWA2Z | N/A | John Macpherson | Commercial HVAC | 9230 | 109230 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
R03 | R03 | R03W01 | HVACNA-DOCUSHARE-DOCH-US-NAFS 6 | CUSNWA33 |  |  | Pending | Newington |  |  | Microsoft Windows Server 2008 R2 Standard | Rehost | Tom Greco | [12 empty] | AWSCloudWatchAgentRole | R03W01 | [20 empty] | 3899 | 104742
R03 | R03 | R03W04 | HVACNA-DOCUSHARE-DOCH-US-NAFS 6 | CUSNWA33 | cusnwa33.carrier.utc.com | 159.82.100.160 | Pending | Newington | 2 | 8 | Microsoft Windows Server 2008 R2 Standard | Rehost | Tom Greco | YES | No |  |  | m5.large | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W04 | HVACNA-DOCUSHARE-DOCH-US-NAFS 6 |  |  | CUSNWA33 | windows |  | cusnwa33.carrier.utc.com | [6 empty] | m5.large | Shared | HVACNA-DOCUSHARE-DOCH-US-NAFS 6 | CUSNWA33 | NA | NA | Commercial HVAC | 3899 | 104742 |  | NA | NA |  | Us-east-1 | NA | N/A | Bronze
R03 | R03 | R03W01 | HVACNA-DOCUSHARE-DOCH-US-NAFS 6 | CUSNWA34 |  |  | Pending | Newington |  |  | Microsoft Windows Server 2008 R2 Standard | Rehost | Tom Greco | [12 empty] | AWSCloudWatchAgentRole | R03W01 | [20 empty] | 3899 | 104742
R03 | R03 | R03W04 | HVACNA-DOCUSHARE-DOCH-US-NAFS 6 | CUSNWA34 | cusnwa34.carrier.utc.com | 159.82.100.159 | Pending | Newington | 2 | 16 | Microsoft Windows Server 2008 R2 Standard | Rehost | Tom Greco | YES | No |  |  | r5.large | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W04 | HVACNA-DOCUSHARE-DOCH-US-NAFS 6 |  |  | CUSNWA34 | windows |  | cusnwa34.carrier.utc.com | [6 empty] | r5.large | Shared | HVACNA-DOCUSHARE-DOCH-US-NAFS 6 | CUSNWA34 | NA | NA | Commercial HVAC | 3899 | 104742 |  | NA | NA |  | Us-east-1 | NA | N/A | Bronze
R03 | R03 | R03W02 | IBM Jazz Continuous Integration Server adapters for PIC software development projects | CUSNWA35 | CUSNWA35.utccgl.com | 10.177.6.143 | Pending | Newington | 2 | 16 | Microsoft Windows Server 2012 R2 Standard | Rehost | McGaughey, Peter Chopra, Puja Victor Yevtukh | YES | No |  |  | r5.large | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W02 | IBM Jazz Continuous Integration Server adapters for PIC software development projects |  |  | CUSNWA35 | windows |  | CUSNWA35.utccgl.com | [6 empty] | r5.large | Shared | IBM Jazz Continuous Integration Server adapters for PIC software development projects | CUSNWA35 | NA | NA | Commercial HVAC | 9230 | 109230 | Application | NA | NA |  | Us-east-1 | NA |  | Bronze
R03 | R03 | R03W06 | Printer server for SAP cloud - standalone server | CUSNWA3E |  |  | Pending | Newington |  |  | Windows Server 2008 R2 Standard | Rehost | Tom Greco |  |  | 913828333602 | HVAC_Com_Prod | [8 empty] | AWSCloudWatchAgentRole | R03W06 | Printer server for SAP cloud - standalone server |  | 913828333602 | CUSNWA3E | Windows | Windows Server 2008 R2 Standard |  | App | Production | [6 empty] | Printer server for SAP cloud - standalone server | CUSNWA3E | NA | Tom Greco | COMMERCIAL HVAC | 3899 | 104742 | Application | NA | NA | Production | Us-east-1 | NA | Indefinitely | Bronze
R03 | R03 | R03W03 | WHQ Engineering (Windchill) | CUSNWA3M | cusnwa3m.carrier.utc.com | 159.82.100.202 | Pending | Newington |  |  | Linux - Red Hat 6.x | Rehost | John Macpherson |  | No |  |  |  | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W03 | WHQ Engineering (Windchill) |  |  | CUSNWA3M | RedHat | Linux - Red Hat 6.x | cusnwa3m.carrier.utc.com |  | production | [5 empty] | Shared | WHQ Engineering (Windchill) | CUSNWA3M | N/A | John Macpherson | Commercial HVAC | 9230 | 109230 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
R03 | R03 | R03W03 | WHQ Engineering (Windchill) | CUSNWA3N | cusnwa3n.carrier.utc.com | 159.82.100.199 | Pending | Newington |  |  | Linux - Red Hat 6.x | Rehost | John Macpherson |  | No |  |  |  | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W03 | WHQ Engineering (Windchill) |  |  | CUSNWA3N | RedHat | Linux - Red Hat 6.x | cusnwa3n.carrier.utc.com |  | production | [5 empty] | Shared | WHQ Engineering (Windchill) | CUSNWA3N | N/A | John Macpherson | Commercial HVAC | 9230 | 109230 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
R03 | R03 | R03W03 | WHQ Engineering (Windchill) | CUSNWA3O | cusnwa3o.carrier.utc.com | 159.82.100.200 | Pending | Newington |  |  | Linux - Red Hat 6.x | Rehost | John Macpherson |  | No |  |  |  | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W03 | WHQ Engineering (Windchill) |  |  | CUSNWA3O | RedHat | Linux - Red Hat 6.x | cusnwa3o.carrier.utc.com |  | production | [5 empty] | Shared | WHQ Engineering (Windchill) | CUSNWA3O | N/A | John Macpherson | Commercial HVAC | 9230 | 109230 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
R03 | R03 | R03W03 | WHQ Engineering (Windchill) | CUSNWA3P | cusnwa3p.carrier.utc.com | 159.82.100.201 | Pending | Newington |  |  | Linux - Red Hat 6.x | Rehost | John Macpherson |  | No |  |  |  | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W03 | WHQ Engineering (Windchill) |  |  | CUSNWA3P | RedHat | Linux - Red Hat 6.x | cusnwa3p.carrier.utc.com |  | production | [5 empty] | Shared | WHQ Engineering (Windchill) | CUSNWA3P | N/A | John Macpherson | Commercial HVAC | 9230 | 109230 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
R03 | R03 | R03W03 | WHQ Engineering (Windchill) | CUSNWA3Q | cusnwa3q.carrier.utc.com | 159.82.100.187 | Pending | Newington | 2 | 64 | Windows Server 2008 R2 Enterprise | Rehost | John Macpherson | Yes | No |  |  | r5.2xlarge | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W03 | WHQ Engineering (Windchill) |  |  | CUSNWA3Q | Windows | Windows Server 2008 R2 Enterprise | cusnwa3q.carrier.utc.com |  | production | [5 empty] | Shared | WHQ Engineering (Windchill) | CUSNWA3Q | N/A | John Macpherson | Commercial HVAC | 9230 | 109230 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
R03 | R03 | R03W03 | WHQ Engineering (Windchill) | CUSNWA3R | cusnwa3r.carrier.utc.com | 159.82.100.189 | Pending | Newington | 2 | 64 | Windows Server 2008 R2 Enterprise | Rehost | Rich Becher | Yes | No |  |  | r5.2xlarge | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W03 | WHQ Engineering (Windchill) |  |  | CUSNWA3R | Windows | Windows Server 2008 R2 Enterprise | cusnwa3r.carrier.utc.com |  | Production | [5 empty] | Shared | WHQ Engineering (Windchill) | CUSNWA3R | N/A | Rich Becher | Commercial HVAC | 9230 | 109230 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
R03 | R03 | R03W03 | WHQ Engineering (Windchill) | CUSNWA44 | cusnwa44.carrier.utc.com | 159.82.102.121 | Pending | Newington | 2 | 32 | Windows Server 2008 R2 Standard | Rehost | John Macpherson | Yes | No |  |  | r5.xlarge | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W03 | WHQ Engineering (Windchill) |  |  | CUSNWA44 | Windows | Windows Server 2008 R2 Standard | cusnwa44.carrier.utc.com |  | production | [5 empty] | Shared | WHQ Engineering (Windchill) | CUSNWA44 | N/A | John Macpherson | Commercial HVAC | 9230 | 109230 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
R03 | R03 | R03W10 | Starlite | CUSNWA4K |  |  | Pending | Newington |  |  | Windows Server 2008 R2 Standard | Rehost | Laura Berndt |  |  | 707766415800 | Refrigeration_Prod | [8 empty] | AWSCloudWatchAgentRole | R03W09 | Starlite |  | 707766415800 | CUSNWA4K | Windows | Windows Server 2008 R2 Standard |  | App | Production | [6 empty] | Starlite | CUSNWA4K | NA | Laura Berndt | RESIDENTIAL AND COMMERCIAL REFRIGERATION | 1088 | 105675 | Application | SOX COMPLIANCE | NA | Production | Us-east-1 | NA | Indefinitely | Bronze
R03 | R03 | R03W09 | AIR HANDLING ORDERING SYSTEM - PROD | CUSNWA4R |  |  | Pending | Newington |  |  | Windows Server 2008 R2 Standard | Rehost | John Boffemmyer |  |  | 913828333602 | HVAC_Com_Prod | [8 empty] | AWSCloudWatchAgentRole | R03W10 | AIR HANDLING ORDERING SYSTEM - PROD |  | 913828333602 | CUSNWA4R | Windows | Windows Server 2008 R2 Standard |  | App | Production | [6 empty] | AIR HANDLING ORDERING SYSTEM - PROD | CUSNWA4R | NA | John Boffemmyer | COMMERCIAL HVAC | 6203 | 104742 | Application | NA | NA | Production | Us-east-1 | NA | Indefinitely | Bronze
R03 | R03 | R03W03 | WHQ Engineering (Windchill) | CUSNWA4V | cusnwa4v.carrier.utc.com | 159.82.94.169 | Pending | Newington | 2 | 16 | Windows Server 2008 R2 Standard | Rehost | John Macpherson | Yes | No |  |  | r5.large | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W03 | WHQ Engineering (Windchill) |  |  | CUSNWA4V | Windows | Windows Server 2008 R2 Standard | cusnwa4v.carrier.utc.com |  | production | [5 empty] | Shared | WHQ Engineering (Windchill) | CUSNWA4V | N/A | John Macpherson | Commercial HVAC | 9230 | 109230 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
R03 | R03 | R03W03 | HVACNA-STARTRAC-US-NAFS | CUSNWA4Y |  |  | Pending | Newington |  |  | Microsoft Windows Server 2008 R2 Standard | Rehost | Tom Greco, Kathy Remillard |  |  | 913828333602 | HVAC_Com_Prod | [8 empty] | AWSCloudWatchAgentRole | R03W03 | HVACNA-STARTRAC-US-NAFS |  | 913828333602 | CUSNWA4Y | Windows | Microsoft Windows Server 2008 R2 Standard |  |  | Production | [6 empty] | HVACNA-STARTRAC-US-NAFS | CUSNWA4Y | N/A | Kathy Remillard | Commercial HVAC | 3899 | 104742 | Application | N/A | N/A | Production | Us-east-1 | N/A | N/A | Bronze
R03 | R03 | R03W01 | Confluence | CUSNWA51 |  |  | Pending | Newington |  |  | Microsoft Windows Server 2008 R2 Standard | Rehost | Jordan King | [12 empty] | AWSCloudWatchAgentRole | R03W01 | [20 empty] | FS-00100 | IC990447
R03 | R03 | R03W05 | FSS Kidde Fenwal DC (0001 9888) Kronos Database - Prod | CUSNWA53 | CUSNWA53.carrier.utc.com | ? | Pending | Newington |  |  | Microsoft Windows Server 2008 R2 Standard | Rehost | Scot Sanborn | no | No |  |  |  | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W05 | FSS Kidde Fenwal DC (0001 9888) Kronos Database - Prod |  |  | CUSNWA53 | windows |  | CUSNWA53.carrier.utc.com | [7 empty] | Shared | FSS Kidde Fenwal DC (0001 9888) Kronos Database - Prod | CUSNWA53 | NA | NA | Fire & Security | FS-00103 | IC990447 |  | NA | NA |  | Us-east-1 | NA | indefinitely | Bronze
R03 | R03 | R03W05 | FSS Fireye (4777) - HELIX (engeeniring) - Prod | CUSNWA5Y | CUSNWA5Y.carcgl.com | 10.177.6.195 | Pending | Newington | 2 | 8 | Microsoft Windows Server 2016 Standard | Rehost | Scot Sanborn | YES | No | 808538705328 | Fire_And_Security_Prod | m5.large | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W05 | FSS Fireye (4777) - HELIX (engeeniring) - Prod |  | 808538705328 | CUSNWA5Y | windows | Microsoft Windows Server 2016 Standard | CUSNWA5Y.carcgl.com | App | Production |  |  |  |  | m5.large | Shared | FSS Fireye (4777) - HELIX (engeeniring) - Prod | CUSNWA5Y | NA | Scot Sanborn | Fire & Security | FS-00497 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | Bronze
R03 | R03 | R03W01 | AutoCAD Edwards | CUSNWA5Z |  |  | Pending | Newington |  |  | Microsoft Windows Server 2012 R2 Standard | Rehost | Jordan King | [12 empty] | AWSCloudWatchAgentRole | R03W01 | [20 empty] | IC990260 | IC990447
R03 | R03 | R03W01 | Code Collaborator | CUSNWA5Z |  |  | Pending | Newington |  |  | Microsoft Windows Server 2012 R2 Standard | Rehost | Jordan King | [12 empty] | AWSCloudWatchAgentRole | R03W01 | [20 empty] | IC990260 | IC990447
R03 | R03 | R03W01 | indysoft Kidde/Edwards | CUSNWA5Z |  |  | Pending | Newington |  |  | Microsoft Windows Server 2012 R2 Standard | Rehost | Jordan King, Chris Marshall | [12 empty] | AWSCloudWatchAgentRole | R03W01 | [20 empty] | IC990260 | IC990447
R03 | R03 | R03W01 | Mentor Graphics Kidde/Edwards | CUSNWA5Z |  |  | Pending | Newington |  |  | Microsoft Windows Server 2012 R2 Standard | Rehost | Jordan King | [12 empty] | AWSCloudWatchAgentRole | R03W01 | [20 empty] | IC990260 | IC990447
R03 | R03 | R03W01 | Subversion Kidde/Edwards | CUSNWA6Q | CUSNWA6Q.carrier.utc.com |  | Pending | Newington |  |  | Microsoft Windows Server 2012 R2 Standard | Rehost | Jordan King | no | No | 808538705328 | Fire_And_Security_Prod |  | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W01 | Subversion Kidde/Edwards |  | 808538705328 | CUSNWA6Q | windows | Microsoft Windows Server 2012 R2 Standard | CUSNWA6Q.carrier.utc.com | App | Production | [5 empty] | Shared | Subversion Kidde/Edwards | CUSNWA6Q | 7048 | Jordan King | Fire & Security | CASS-INTLX | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | Bronze
R03 | R03 | R03W01 | CCS GFP DOORs, DOORs Kidde/Edwards | CUSNWA6R | CUSNWA6R.carrier.utc.com |  | Pending | Newington |  |  | Microsoft Windows Server 2012 R2 Standard | Rehost | Jordan King | no | No | 808538705328 | Fire_And_Security_Prod |  | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W01 | CCS GFP DOORs, DOORs Kidde/Edwards |  | 808538705328 | CUSNWA6R | windows | Microsoft Windows Server 2012 R2 Standard | CUSNWA6R.carrier.utc.com | App | Production | [5 empty] | Shared | CCS GFP DOORs, DOORs Kidde/Edwards | CUSNWA6R | 7044. 1894 | Jordan King | Fire & Security |  | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | Bronze
Pilot | Pilot | Pilot | JONAS - STAGE | CUSNWA74 | cusnwa74.carcgl.com | 10.177.6.127 | complete | Newington | 2 | 4 | Windows 2012 R2 | Rehost | Randy Durocher | Yes | Yes | 260780007980 | HVAC_Com_Preprod | t2.large | Standard | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | 10.233.9.141 | N/A | AWSCloudWatchAgentRole | Pilot | JONAS - STAGE | TSA_EXIT_PILOT | 260780007980 | CUSNWA74 | windows | Windows 2012 R2 | cusnwa74.carcgl.com | app | stage | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | subnet-0fcc346c85fd82ed0 | sg-0cfa6a707d1ff7fe5 | t2.large | shared | JONAS - STAGE | CUSNWA74 | 6316 | Randy Durocher | HVAC_Com_Preprod | 3899 | 104742 | Application | NA | NA | STG | us-east-1 | Weekdays | Indefinitely | BRONZE | complete -26th May 2020 | Optional | complete - 27th May 2020 | complete - 27th May 2020 | In-Progress - 28th May 2020 | Yet to start -27th May 2020 | Yet to Start - 1st June 2020 | Yet to Start - 2nd June 2020 | Yet to Start - 2nd June 2020 | Yet to Start - 3nd June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020
R03 | R03 | R03W07 | JONAS SERVER - PROD | CUSNWA75 |  |  | Pending | Newington |  |  | Windows Server 2012 R2 Standard | Rehost | Randy Durocher, Ezhil Nanjappan | [12 empty] | AWSCloudWatchAgentRole | R03W07 | JONAS SERVER - PROD |  |  | CUSNWA75 | Windows | Windows Server 2012 R2 Standard |  | App | Production | [6 empty] | JONAS SERVER - PROD | CUSNWA75 | NA | Randy Durocher | NA | 3899 | 104742 | Application | NA | NA | Production | Us-east-1 | NA | Indefinitely | Bronze
R03 | R03 | R03W05 | FSS Fireye (4777) - KRONOS - Prod | CUSNWA77 | CUSNWA77.carrier.utc.com | ? | Pending | Newington |  |  | Windows Server 2008 R2 Standard | Rehost | Scot Sanborn | no | No | 808538705328 | Fire_And_Security_Prod |  | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W05 | FSS Fireye (4777) - KRONOS - Prod |  | 808538705328 | CUSNWA77 | windows | Windows Server 2008 R2 Standard | CUSNWA77.carrier.utc.com | App | Production | [5 empty] | Shared | FSS Fireye (4777) - KRONOS - Prod | CUSNWA77 | NA | Scot Sanborn | Fire & Security | FS-00497 | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | Bronze
R03 | R03 | R03W03 | WHQ Engineering Newington (0001) - PART LISTER | CUSNWA79 | cusnwa79.carrier.utc.com | 10.177.6.116 | Pending | Newington |  |  | Linux - Red Hat 6.x | Rehost | John Macpherson |  | No |  |  |  | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W03 | WHQ Engineering Newington (0001) - PART LISTER |  |  | CUSNWA79 | RedHat | Linux - Red Hat 6.x | cusnwa79.carrier.utc.com |  | Production | [5 empty] | Shared | WHQ Engineering Newington (0001) - PART LISTER | CUSNWA79 | N/A | John Macpherson | Commercial HVAC | 9230 | 109230 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
R03 | R03 | R03W01 | Code Collaborator | CUSNWA7E |  |  | Pending | Newington |  |  | Microsoft Windows Server 2012 R2 Standard | Rehost | Jordan King | [12 empty] | AWSCloudWatchAgentRole | R03W01 | [20 empty] | FS-00100 | IC990447
R03 | R03 | R03W01 | Confluence | CUSNWA7E |  |  | Pending | Newington |  |  | Microsoft Windows Server 2012 R2 Standard | Rehost | Jordan King | [12 empty] | AWSCloudWatchAgentRole | R03W01 | [20 empty] | FS-00100 | IC990447
R03 | R03 | R03W01 | SolidEdge Kidde/Edwards | CUSNWA7E |  |  | Pending | Newington |  |  | Microsoft Windows Server 2012 R2 Standard | Rehost | Jordan King | [12 empty] | AWSCloudWatchAgentRole | R03W01 | [20 empty] | FS-00100 | IC990447
R03 | R03 | R03W01 | HVACNA-WORKSOFT-IT-US-HVACRCS 10.0.0.995 | CUSNWA7I | cusnwa7i.utccgl.com | 10.177.6.140 | Pending |  | 4 | 64 | Microsoft Windows Server 2012 R2 Standard | Rehost | [6 empty] | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W01 | HVACNA-WORKSOFT-IT-US-HVACRCS 10.0.0.995 |  |  | CUSNWA7I | windows |  | cusnwa7i.utccgl.com |  |  | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | subnet-04a5b0c4eff0b5e65 | sg-07d38644ed9df7a61 |  | Shared | HVACNA-WORKSOFT-IT-US-HVACRCS 10.0.0.995 | CUSNWA7I |  |  |  | 4731 | 104742 | [5 empty] | NA
R03 | R03 | R03W05 | HPQC ALM12 F&S - Prod | CUSNWA7K | CUSNWA7K.utccgl.com | 10.177.6.201 | Pending | Newington | 4 | 16 | Microsoft Windows Server 2012 R2 Standard | Rehost | Vinay Chandra | YES | No |  |  | m5.xlarge | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W05 | HPQC ALM12 F&S - Prod |  |  | CUSNWA7K | windows |  | CUSNWA7K.utccgl.com | [6 empty] | m5.xlarge | Shared | HPQC ALM12 F&S - Prod | CUSNWA7K | NA | NA |  | 9230 | 109230 |  | NA | NA |  | Us-east-1 | NA | N/A | Bronze
R03 | R03 | R03W03 | Doku Wiki documentation | CUSNWA7O |  |  | Pending | Newington |  |  | Windows Server 2012 R2 Standard | Rehost | Julien Dupre, Kristian Tuszynski, Christophe Lecourvreur |  |  | 913828333602 | HVAC_Com_Prod | [8 empty] | AWSCloudWatchAgentRole | R03W03 | Doku Wiki documentation |  | 913828333602 | CUSNWA7O | windows | Windows Server 2012 R2 Standard |  |  | Production | [6 empty] | Doku Wiki documentation | CUSNWA7O | N/A | Julien Dupre, Kristian Tuszynski, Christophe Lecourvreur | Commercial HVAC | 9230 | 109230 | Application | N/A | N/A | Production | Us-east-1 | N/A | N/A | Bronze
R03 | R03 | R03W03 | WHQ Engineering Newington (SVN server for Standard Design) | CUSNWA7O |  |  | Pending | Newington |  |  | Windows Server 2012 R2 Standard | Rehost | Julien Dupre, Kristian Tuszynski, Christophe Lecourvreur |  |  | 913828333602 | HVAC_Com_Prod | [8 empty] | AWSCloudWatchAgentRole | R03W03 | WHQ Engineering Newington (SVN server for Standard Design) |  | 913828333602 | CUSNWA7O | windows | Windows Server 2012 R2 Standard |  |  | Production | [6 empty] | WHQ Engineering Newington (SVN server for Standard Design) | CUSNWA7O | N/A | Julien Dupre, Kristian Tuszynski, Christophe Lecourvreur | Commercial HVAC | 9230 | 109230 | Application | N/A | N/A | Production | Us-east-1 | N/A | N/A | Bronze
R03 | R03 | R03W05 | HPQC ALM12 F&S - Prod | CUSNWA7V | CUSNWA7V.utccgl.com | 10.177.6.204 | Pending | Newington | 4 | 32 | Microsoft Windows Server 2012 R2 Standard | Rehost | Vinay Chandra | YES | No |  |  | r5.xlarge | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W05 | HPQC ALM12 F&S - Prod |  |  | CUSNWA7V | windows |  | CUSNWA7V.utccgl.com | [6 empty] | r5.xlarge | Shared | HPQC ALM12 F&S - Prod | CUSNWA7V | NA | NA |  | 9230 | 109230 |  | NA | NA |  | Us-east-1 | NA | N/A | Bronze
R03 | R03 | R03W05 | HPQC ALM12 F&S - Prod | CUSNWA7W | CUSNWA7W.utccgl.com | 10.177.6.203 | Pending | Newington | 4 | 16 | Microsoft Windows Server 2012 R2 Standard | Rehost | Vinay Chandra | YES | No |  |  | m5.xlarge | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W05 | HPQC ALM12 F&S - Prod |  |  | CUSNWA7W | windows |  | CUSNWA7W.utccgl.com | [6 empty] | m5.xlarge | Shared | HPQC ALM12 F&S - Prod | CUSNWA7W | NA | NA |  | 9230 | 109230 |  | NA | NA |  | Us-east-1 | NA | N/A | Bronze
R03 | R03 | R03W06 | WHQ Engineering (Windchill) | CUSNWA7Y | cusnwa7y.utccgl.com | 10.177.6.217 | Pending | Newington | 8 | 16 | Microsoft Windows Server 2012 R2 Standard | Rehost | Sandra Trainer, John Macpherson | Yes | No |  |  | c5.2xlarge | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W06 | WHQ Engineering (Windchill) |  |  | CUSNWA7Y | Windows | Microsoft Windows Server 2012 R2 Standard | cusnwa7y.utccgl.com |  | Production | [5 empty] | Shared | WHQ Engineering (Windchill) | CUSNWA7Y | N/A | Sandra Trainer, John Macpherson | Commercial HVAC | 9230 | 109230 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
R03 | R03 | R03W02 | CCS Windchill Product Analytics - Prod | CUSNWA7Z |  |  | Pending | Newington |  |  | Microsoft Windows Server 2012 R2 Standard | Rehost | John Macpherson |  |  | 808538705328 | Fire_And_Security_Prod | [8 empty] | AWSCloudWatchAgentRole | R03W02 | CCS Windchill Product Analytics - Prod |  | 808538705328 | CUSNWA7Z | windows | Microsoft Windows Server 2012 R2 Standard |  |  | Production | [6 empty] | CCS Windchill Product Analytics - Prod | CUSNWA7Z | NA | John Macpherson | Fire & Security | 9230 | 109230 | Application | NA | NA | NA | Us-east-1 | NA | NA | Bronze
R03 | R03 | R03W02 | CCS Windchill Product Analytics - Prod | CUSNWA80 |  |  | Pending | Newington |  |  | Microsoft Windows Server 2012 R2 Standard | Rehost | John Macpherson |  |  | 808538705328 | Fire_And_Security_Prod | [8 empty] | AWSCloudWatchAgentRole | R03W02 | CCS Windchill Product Analytics - Prod |  | 808538705328 | CUSNWA80 | windows | Microsoft Windows Server 2012 R2 Standard |  |  | Production | [6 empty] | CCS Windchill Product Analytics - Prod | CUSNWA80 | NA | John Macpherson | Fire & Security | 9230 | 109230 | Application | NA | n/a | n/a | Us-east-1 | NA | NA | Bronze
R03 | R03 | R03W04 | aPriori - Prod | CUSNWD0O | CUSNWD0O.utccgl.com | 10.177.6.212 | Pending | Newington | 2 | 6 | Microsoft Windows Server 2012 R2 Standard | Rehost | Satyam Bendapudi | YES | No |  |  | m5.large | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W04 | aPriori - Prod |  |  | CUSNWD0O | windows |  | CUSNWD0O.utccgl.com | [6 empty] | m5.large | Shared | aPriori - Prod | CUSNWD0O | NA | NA |  | 9230 | 109230 | Database | NA | NA | Production | Us-east-1 | NA | N/A | Bronze
R03 | R03 | R03W01 | HVACNA-DOCUSHARE-DOCH-US-NAFS 6 | CUSNWD13 |  |  | Pending | Newington |  |  | Microsoft Windows Server 2008 R2 Enterprise | Rehost | Tom Greco | [12 empty] | AWSCloudWatchAgentRole | R03W01 | [20 empty] | 3899 | 104742
R03 | R03 | R03W04 | HVACNA-DOCUSHARE-DOCH-US-NAFS 6 | CUSNWD13 | cusnwd13.carrier.utc.com | 159.82.100.94 | Pending | Newington | 2 | 20 | Microsoft Windows Server 2008 R2 Enterprise | Rehost | Tom Greco | YES | No |  |  | r5.large | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W04 | HVACNA-DOCUSHARE-DOCH-US-NAFS 6 |  |  | CUSNWD13 | windows |  | cusnwd13.carrier.utc.com | [6 empty] | r5.large | Shared | HVACNA-DOCUSHARE-DOCH-US-NAFS 6 | CUSNWD13 | NA | NA | Commercial HVAC | 3899 | 104742 |  | NA | NA |  | Us-east-1 | NA | N/A | Bronze
R03 | R03 | R03W03 | HVACNA-STARTRAC-US-NAFS | CUSNWD1Q |  |  | Pending | Newington |  |  | Microsoft Windows Server 2008 R2 Standard | Rehost | Tom Greco, Kathy Remillard |  |  | 913828333602 | HVAC_Com_Prod | [8 empty] | AWSCloudWatchAgentRole | R03W03 | HVACNA-STARTRAC-US-NAFS |  | 913828333602 | CUSNWD1Q | windows | Microsoft Windows Server 2008 R2 Standard |  |  | Production | [6 empty] | HVACNA-STARTRAC-US-NAFS | CUSNWD1Q | N/A | Kathy Remillard | Commercial HVAC | 3899 | 104742 | Database | N/A | N/A | Production | Us-east-1 | N/A | N/A | Bronze
R03 | R03 | R03W03 | HVACNA-STARTRAC-US-NAFS | CUSNWD1W |  |  | Pending | Newington |  |  | Microsoft Windows Server 2008 R2 Standard | Rehost | Tom Greco, Kathy Remillard |  |  | 913828333602 | HVAC_Com_Prod | [8 empty] | AWSCloudWatchAgentRole | R03W03 | HVACNA-STARTRAC-US-NAFS |  | 913828333602 | CUSNWD1W | windows | Microsoft Windows Server 2008 R2 Standard |  |  | Production | [6 empty] | HVACNA-STARTRAC-US-NAFS | CUSNWD1W | N/A | Kathy Remillard | Commercial HVAC | 3899 | 104742 | Database | N/A | N/A | Production | Us-east-1 | N/A | N/A | Bronze
R03 | R03 | R03W03 | WHQ Engineering (Windchill) | CUSNWD2E | cusnwd2e.carrier.utc.com | 159.82.105.83 | Pending | Newington |  |  | Linux - Red Hat 6.x | Rehost | John Macpherson |  | No |  |  |  | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W03 | WHQ Engineering (Windchill) |  |  | CUSNWD2E | RedHat | Linux - Red Hat 6.x | cusnwd2e.carrier.utc.com |  | production | [5 empty] | Shared | WHQ Engineering (Windchill) | CUSNWD2E | N/A | John Macpherson | Commercial HVAC | 9230 | 109230 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
R03 | R03 | R03W03 | WHQ Engineering (Windchill) | CUSNWD2F | cusnwd2f.carrier.utc.com | 159.82.105.84 | Pending | Newington |  |  | Linux - Red Hat 6.x | Rehost | John Macpherson |  | No |  |  |  | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W03 | WHQ Engineering (Windchill) |  |  | CUSNWD2F | RedHat | Linux - Red Hat 6.x | cusnwd2f.carrier.utc.com |  | production | [5 empty] | Shared | WHQ Engineering (Windchill) | CUSNWD2F | N/A | John Macpherson | Commercial HVAC | 9230 | 109230 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
R03 | R03 | R03W01 | HVACNA-WORKSOFT-IT-US-HVACRCS 10.0.0.995 | CUSNWD2T | cusnwd2t.utccgl.com | 10.177.6.141 | Pending | Newington | 2 | 16 | Microsoft Windows Server 2012 R2 Standard | Rehost | Judy Zeman | Yes | No | 9138283705328 | HAVC_Com_Prod | r5.large | Standard | N/A | YES | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d |  |  | AWSCloudWatchAgentRole | R03W01 | HVACNA-WORKSOFT-IT-US-HVACRCS 10.0.0.995 | HVAC_Com_Prod_913828333602 | 9138283705328 | CUSNWD2T | windows | Microsoft Windows Server 2012 R2 Standard | cusnwd2t.utccgl.com | App | Production | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | subnet-04a5b0c4eff0b5e65 | sg-07d38644ed9df7a61 | r5.large | Shared | HVACNA-WORKSOFT-IT-US-HVACRCS 10.0.0.995 | CUSNWD2T | 6346 | Tim Prueser | Commercial HVAC | 4731 | 104742 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | Bronze
R03 | R03 | R03W01 | Carrier Transicold Athens - IQR - DEV | CUSNWK09 |  |  | Pending | Newington |  |  | Windows Server 2016 Standard | Rehost | Mike Brunson | [12 empty] | AWSCloudWatchAgentRole | R03W01 | [20 empty] | 8193 | IC990236
R03 | R03 | R03W01 | Carrier Transicold Athens - TMS - DEV | CUSNWK09 |  |  | Pending | Newington |  |  | Windows Server 2016 Standard | Rehost | Mike Brunson | [12 empty] | AWSCloudWatchAgentRole | R03W01 | [20 empty] | 8193 | IC990236
Pilot | Pilot | Pilot | NWDI-STAGE | CUSNWK0V | CUSNWK0V.carcgl.com | 159.82.100.14 | complete | Newington | 2 | 8 | Windows 2008 R2 | Rehost | Sarah Strominger | Yes | Yes | 260780007980 | HVAC_Com_Preprod | t2.medium | Standard | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | 10.233.9.140 | N/A | AWSCloudWatchAgentRole | Pilot | NWDI-STAGE | TSA_EXIT_PILOT | 260780007980 | CUSNWK0V | windows | Windows 2008 R2 | CUSNWK0V.carcgl.com | app | stage | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | subnet-0fcc346c85fd82ed0 | sg-0cfa6a707d1ff7fe5 | t2.medium | shared | NWDI-STAGE | CUSNWK0V | NA | Sarah Strominger | HVAC_Com_Preprod | 4732 | 104742 | Application | NA | NA | STG | us-east-1 | Weekdays | Indefinitely | BRONZE | complete -26th May 2020 | Optional | complete - 27th May 2020 | complete - 27th May 2020 | In-Progress - 28th May 2020 | Yet to start -27th May 2020 | Yet to Start - 1st June 2020 | Yet to Start - 2nd June 2020 | Yet to Start - 2nd June 2020 | Yet to Start - 3nd June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020
R03 | R03 | R03W06 | RCD Carrier Newington (0001) - Prod | CUSNWK0W |  |  | Pending | Newington |  |  | Windows Server 2008 R2 Standard | Rehost | David Mannfeld |  |  | 501143608669 | HVAC_Res_Prod | [8 empty] | AWSCloudWatchAgentRole | R03W06 | RCD Carrier Newington (0001) - Prod |  | 501143608669 | CUSNWK0W | windows | Windows Server 2008 R2 Standard |  | App | Production | [6 empty] | RCD Carrier Newington (0001) - Prod | CUSNWK0W | NA | David Mannfeld | RESIDENTIAL HVAC | 6220 | 104742 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | Bronze
R03 | R03 | R03W01 | HPQC ALM12 F&S - Stag | CUSNWK1L | CUSNWK1L.utccgl.com | 10.177.6.199 | Pending | Newington | 4 | 16 | Microsoft Windows Server 2012 R2 Standard | Rehost | Vinay Chandra | YES | No |  |  | m5.xlarge | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W01 | HPQC ALM12 F&S - Stag |  |  | CUSNWK1L | windows |  | CUSNWK1L.utccgl.com | [6 empty] | m5.xlarge | Shared | HPQC ALM12 F&S - Stag | CUSNWK1L | NA | NA |  | 9230 | 109230 |  | NA | NA |  | Us-east-1 | NA |  | Bronze
R03 | R03 | R03W01 | HPQC ALM12 F&S - Stag | CUSNWK1M | CUSNWK1M.chubbfsad.com | 10.177.6.202 | Pending | Newington | 4 | 16 | Microsoft Windows Server 2012 R2 Standard | Rehost | Vinay Chandra | YES | No |  |  | m5.xlarge | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W01 | HPQC ALM12 F&S - Stag |  |  | CUSNWK1M | windows |  | CUSNWK1M.chubbfsad.com | [6 empty] | m5.xlarge | Shared | HPQC ALM12 F&S - Stag | CUSNWK1M | NA | NA |  | 9230 | 109230 |  | NA | NA |  | Us-east-1 | NA |  | Bronze
R03 | R03 | R03W01 | HPQC ALM12 F&S - Stag | CUSNWK1N | CUSNWK1N.chubbfsad.com | 10.177.6.200 | Pending | Newington | 4 | 32 | Microsoft Windows Server 2012 R2 Standard | Rehost | Vinay Chandra | YES | No |  |  | r5.xlarge | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W01 | HPQC ALM12 F&S - Stag |  |  | CUSNWK1N | windows |  | CUSNWK1N.chubbfsad.com | [6 empty] | r5.xlarge | Shared | HPQC ALM12 F&S - Stag | CUSNWK1N | NA | NA |  | 9230 | 109230 |  | NA | NA |  | Us-east-1 | NA |  | Bronze
Pilot | Pilot | Pilot | HVACNA-NPC-US-NAFS-TEST | CUSNWT0M | cusnwt0m.carcgl.com | 159.82.100.145 | complete | Newington | 2 | 4 | Microsoft Windows Server 2008 R2 Standard | Rehost | Tom Greco and Venu Reddy | Yes | Yes | 260780007980 | HVAC_Com_Preprod | t2.large | Standard | N/A | YES | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | 10.233.9.142 | N/A | AWSCloudWatchAgentRole | Pilot | HVACNA-NPC-US-NAFS-TEST | TSA_EXIT_PILOT | 917128996017 | CUSNWT0M | windows | Microsoft Windows Server 2008 R2 Standard | cusnwt0m.carcgl.com | app | test | subnet-0fcc346c85fd82ed0 | sg-0590ec68a86588665 | subnet-0fcc346c85fd82ed0 | sg-0cfa6a707d1ff7fe5 | t2.large | shared | HVACNA-NPC-US-NAFS-TEST | CUSNWT0M | 6321 | Tom Greco | Fire & Security | 3899 | 104742 | Application | NA | NA | TST | us-east-1 | Weekdays | Indefinitely | BRONZE | complete -26th May 2020 | Optional | complete - 27th May 2020 | complete - 27th May 2020 | In-Progress - 28th May 2020 | Yet to start -27th May 2020 | Yet to Start - 1st June 2020 | Yet to Start - 2nd June 2020 | Yet to Start - 2nd June 2020 | Yet to Start - 3nd June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020
R03 | R03 | R03W07 | JONAS LB VIP SERVER - PROD | CUSNWT0R |  |  | Pending | Newington |  |  | Windows Server 2008 R2 Standard | Rehost | Randy Durocher | [12 empty] | AWSCloudWatchAgentRole | R03W07 | JONAS LB VIP SERVER - PROD |  |  | CUSNWT0R | Windows | Windows Server 2008 R2 Standard |  | App | Production | [6 empty] | JONAS LB VIP SERVER - PROD | CUSNWT0R | NA | Randy Durocher | HVAC field service | 3899 | 104742 | Application | NA | NA | Production | Us-east-1 | NA | Indefinitely | Bronze
R03 | R03 | R03W07 | JONAS LB VIP SERVER - PROD | CUSNWT0S |  |  | Pending | Newington |  |  | Windows Server 2008 R2 Standard | Rehost | Randy Durocher | [12 empty] | AWSCloudWatchAgentRole | R03W07 | JONAS LB VIP SERVER - PROD |  |  | CUSNWT0S | Windows | Windows Server 2008 R2 Standard |  | App | Production | [6 empty] | JONAS LB VIP SERVER - PROD | CUSNWT0S | NA | Randy Durocher | NA | 3899 | 104742 | Application | NA | NA | Production | Us-east-1 | NA | Indefinitely | Bronze
R03 | R03 | R03W01 | Infrastructure servers | CUSNWW0U |  |  | Pending | Newington |  |  | Windows Server 2008 R2 Standard | Rehost | RICH JOHNSTON | [12 empty] | AWSCloudWatchAgentRole | R03W01 | [20 empty] | 9713 | 109713
R03 | R03 | R03W01 | Infrastructure servers | CUSNWW1C |  |  | Pending | Newington |  |  | Windows Server 2008 R2 Standard | Rehost | RICH JOHNSTON | [12 empty] | AWSCloudWatchAgentRole | R03W01 | [20 empty] | 9713 | 109713
R03 | R03 | R03W04 | aPriori - Prod | CUSNWW1L | CUSNWW1L.utccgl.com | 10.177.6.213 | Pending | Newington | 4 | 16 | Microsoft Windows Server 2012 R2 Standard | Rehost | Satyam Bendapudi | YES | No |  |  | m5.xlarge | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W04 | aPriori - Prod |  |  | CUSNWW1L | windows |  | CUSNWW1L.utccgl.com | [6 empty] | m5.xlarge | Shared | aPriori - Prod | CUSNWW1L | NA | NA |  | 9230 | 109230 | Application | NA | NA | Production | Us-east-1 | NA | N/A | Bronze
Pilot | Pilot | Pilot | MYEDDIE-TEST | KUSMND19 | kusmnd19.carcgl.com | 159.82.226.170 | complete | Meriden | 2 | 4 | Microsoft Windows Server 2008 R2 Enterprise | Rehost | Jeff Turner/Timothy Kennedy | Yes | Yes | 917128996017 | Fire_And_Security_PreProd | t2.large | Standard | N/A | YES | subnet-0dd905d5c0776f8ac | sg-0a08dc8c96199a489 | 10.233.153.140 | N/A | AWSCloudWatchAgentRole | Pilot | MYEDDIE-TEST | Fire_And_Security_PreProd_917128996017 | 917128996017 | KUSMND19 | windows | Microsoft Windows Server 2008 R2 Enterprise | kusmnd19.carcgl.com | db | test | subnet-0dd905d5c0776f8ac | sg-0a08dc8c96199a489 | subnet-0dd905d5c0776f8ac | sg-0104099b41897670f | t2.large | Shared | MYEDDIE-TEST | KUSMND19 | 1856 | Jeff Turner | Fire & Security | CASS-EDWRD | IC990447 | Database | NA | NA | TST | us-east-1 | Weekdays | Indefinitely | BRONZE | complete -26th May 2020 | Optional | complete - 27th May 2020 | complete - 27th May 2020 | In-Progress - 28th May 2020 | Yet to start -27th May 2020 | Yet to Start - 1st June 2020 | Yet to Start - 2nd June 2020 | Yet to Start - 2nd June 2020 | Yet to Start - 3nd June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 4th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020 | Yet to Start - 6th June 2020
R03 | R03 | R03W01 | TRESS - Navojoa | KUSNWD17 | KUSNWD17.carrier.utc.com |  | Pending | Newington |  |  | Microsoft Windows Server 2008 R2 Standard | Rehost | Ismael Villarreal, Shreyes Bhatnagar, Rohit Malpekar, Alejandro Martinez, Oscar Aguilar | no | No |  |  |  | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W01 | TRESS - Navojoa |  | 0 | KUSNWD17 | windows | Microsoft Windows Server 2008 R2 Standard | KUSNWD17.carrier.utc.com | App | Production | [5 empty] | Shared | TRESS - Navojoa | KUSNWD17 | 6805 | Ismael Villarreal, Shreyes Bhatnagar, Rohit Malpekar, Alejandro Martinez, Oscar Aguilar |  | 9713 | 109713 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | Bronze
R03 | R03 | R03W01 | TRESS - Navojoa | KUSNWD17 |  |  | Pending | Newington |  |  | Microsoft Windows Server 2008 R2 Standard | Rehost | Ismael Villarreal, Shreyes Bhatnagar, Rohit Malpekar, Alejandro Martinez, Oscar Aguilar | [12 empty] | AWSCloudWatchAgentRole | R03W01 | [20 empty] | 9713 | 109713
R03 | R03 | R03W01 | MOODLE - Test | KUSNWD1I | KUSNWD1I.carrier.utc.com | 100.64.1.22 | Pending | Newington | 2 | 64 | Microsoft Windows Server 2008 R2 Enterprise | Rehost | Timothy Kennedy | Yes | No | 808538705328 | Fire_And_Security_Prod | r5.2xlarge | Standard | N/A | YES |  |  |  |  | AWSCloudWatchAgentRole | R03W01 | MOODLE - Test |  | 808538705328 | KUSNWD1I | windows | Microsoft Windows Server 2008 R2 Enterprise | KUSNWD1I.carrier.utc.com | App | Production |  |  |  |  | r5.2xlarge | Shared | MOODLE - Test | KUSNWD1I | 1856 | Timothy Kennedy | Fire & Security | CASS-EDWRD | IC990447 | Application | NA | NA | Production | Us-east-1 | NA | indefinitely | Bronze
R02 | R02 | R02DMZ | CCS GSP Supra ADFS for SSO | XMNP175 |  |  |  | Meriden |  |  | Microsoft Windows Server 2012 Standard R2 | Rehost | Kyle Shields, Jan Phillips | [12 empty] | AWSCloudWatchAgentRole | R02DMZ | [20 empty] | CASS-SUPRA | IC990447
| R02 | R02W01-DMZ | ComfortChoice (MyTStat) | XMNT214 | XMNT214.utc.com | 167.17.243.14 | Pending | Meriden |  |  | Microsoft Windows Server 2012 Standard R2 | Rehost | Syed, Mehmood Kozlowski, John E | No | TBV | 890585303181 | Fire_And_Security_Dev |  | Standard | N/A | YES | subnet-0c6533ebaf5f1b1a2 |  |  | N/A | AWSCloudWatchAgentRole | R02W01 | ComfortChoice (MyTStat) | #ERROR! | 890585303181 | XMNT214 | windows | Microsoft Windows Server 2012 Standard R2 | XMNT214.utc.com | app | dev | subnet-0c6533ebaf5f1b1a2 |  |  |  |  | Shared | ComfortChoice (MyTStat) | XMNT214 | NA | Syed, Mehmood Kozlowski, John E | Fire_And_Security_Dev | 3525 | IC990447 | Application | NA | NA | Dev | us-east-1 | NA | indefinitely | Bronze
R02 | R02 | R02DMZ | ComfortChoice (MyTStat) | XMNT214 |  |  |  | Meriden |  |  | Microsoft Windows Server 2012 Standard R2 | Rehost | John Kozlowski, Mehmood Syed, Bryan Yarde | [12 empty] | AWSCloudWatchAgentRole | R02DMZ | [20 empty] | 3525 | IC990447
| R02 | R02W01-DMZ | ComfortChoice (manager) | XMNT215 | XMNT215.utc.com | 167.17.243.53 | Pending | Meriden |  |  | Microsoft Windows Server 2012 Standard R2 | Rehost | Syed, Mehmood Kozlowski, John E | No | TBV | 890585303181 | Fire_And_Security_Dev |  | Standard | N/A | YES | subnet-0c6533ebaf5f1b1a2 |  |  | N/A | AWSCloudWatchAgentRole | R02W01 | ComfortChoice (manager) | #ERROR! | 890585303181 | XMNT215 | windows | Microsoft Windows Server 2012 Standard R2 | XMNT215.utc.com | app | dev | subnet-0c6533ebaf5f1b1a2 |  |  |  |  | Shared | ComfortChoice (manager) | XMNT215 | NA | Syed, Mehmood Kozlowski, John E | Fire_And_Security_Dev | 3525 | IC990447 | Application | NA | NA | Dev | Us-east-1 | NA | indefinitely | Bronze
R02 | R02 | R02DMZ | ComfortChoice (manager) | XMNT215 |  |  |  | Meriden |  |  | Microsoft Windows Server 2012 Standard R2 | Rehost | John Kozlowski, Mehmood Syed, Bryan Yarde | [12 empty] | AWSCloudWatchAgentRole | R02DMZ | [20 empty] | 3525 | IC990447
R02 | R02 | R02DMZ | WHQ (iListen - MFA) - Staging | XMNT232 |  |  |  | Meriden |  |  | Microsoft Windows Server 2012 Standard R2 | Rehost | Sunny Sangha / Ainsworth, Andrew | [12 empty] | AWSCloudWatchAgentRole | R02DMZ | [20 empty] | IC990269 | IC990269-Int
| R02 | R02W01-DMZ | WHQ Engineering Newington (PTC InService) | XMNT245 | XMNT245.carrier.utc.com |  | Pending | Meriden |  |  | Microsoft Windows Server 2012 Standard R2 | Rehost | John Macpherson, Sandra Trainer | No | TBV | 823570924226 | HVAC_Res_Preprod |  | Standard | N/A | YES | subnet-0fcc346c85fd82ed0 |  |  | N/A | AWSCloudWatchAgentRole | R02W01 | WHQ Engineering Newington (PTC InService) | #ERROR! | 823570924226 | XMNT245 | windows | Microsoft Windows Server 2012 Standard R2 | XMNT245.carrier.utc.com | app | Stage | subnet-0fcc346c85fd82ed0 |  |  |  |  | Shared | WHQ Engineering Newington (PTC InService) | XMNT245 | NA | Sandra Trainer | HVAC_Res_Preprod | 9230 | 109230 | Application | NA | NA | Stage | Us-east-1 | NA | indefinitely | Bronze
R02 | R02 | R02DMZ | WHQ Engineering Newington (PTC InService) | XMNT245 |  |  |  | Meriden |  |  | Microsoft Windows Server 2012 Standard R2 | Rehost | John Macpherson, Sandra Trainer | [12 empty] | AWSCloudWatchAgentRole | R02DMZ | [20 empty] | 9230 | 109230
| R02 | R02W01-DMZ | CCS GSP Supra ADFS for SSO-STAGE | xmnt253 | xmnt253.utc.com | 167.17.243.50 | Pending | Meriden |  |  | Microsoft Windows Server 2012 Standard R2 | Rehost | Kyle Shields, Jan Phillips | No | TBV | 917128996017 | Fire_And_Security_PreProd |  | Standard | N/A | YES | subnet-06de97b914fec4d10 | sg-0ac65d65a7d551733 |  | N/A | AWSCloudWatchAgentRole | R02W01 | CCS GSP Supra ADFS for SSO-STAGE | Fire_And_Security_PreProd_917128996017 | 917128996017 | xmnt253 | windows | Microsoft Windows Server 2012 Standard R2 | xmnt253.utc.com | app | Stage | subnet-06de97b914fec4d10 | sg-0ac65d65a7d551733 | [subnet-0f866e16dd1977655] | sg-06bf1dfeb43c97567 |  | Shared | CCS GSP Supra ADFS for SSO-STAGE | xmnt253 | 1958 | Jan Phillips | Fire_And_Security_PreProd | CASS-SUPRA | IC990447 | Application | NA | NA | Stage | Us-east-1 | NA | indefinitely | Bronze
R02 | R02 | R02DMZ | CCS GSP Supra ADFS for SSO - STAGE | xmnt253 |  |  |  | Meriden |  |  | Microsoft Windows Server 2012 Standard R2 | Rehost | Kyle Shields, Jan Phillips | [12 empty] | AWSCloudWatchAgentRole | R02DMZ | [20 empty] | CASS-SUPRA | IC990447
| R02 | R02W01-DMZ | CCS GSP Supra ADFS for SSO-STAGE | XMNT254 | xmnt254.carrier.utc.com |  | Pending | Meriden |  |  | Microsoft Windows Server 2012 Standard R2 | Rehost | Kyle Shields, Jan Phillips | No | TBV | 917128996017 | Fire_And_Security_PreProd |  | Standard | N/A | YES | subnet-06de97b914fec4d10 | sg-0ac65d65a7d551733 |  | N/A | AWSCloudWatchAgentRole | R02W01 | CCS GSP Supra ADFS for SSO-STAGE | Fire_And_Security_PreProd_917128996017 | 917128996017 | XMNT254 | windows | Microsoft Windows Server 2012 Standard R2 | xmnt254.carrier.utc.com | app | Stage | subnet-06de97b914fec4d10 | sg-0ac65d65a7d551733 | [subnet-0f866e16dd1977655] | sg-06bf1dfeb43c97567 |  | Shared | CCS GSP Supra ADFS for SSO-STAGE | XMNT254 | 1958 | Jan Phillips | Fire_And_Security_PreProd | CASS-SUPRA | IC990447 | Application | NA | NA | Stage | Us-east-1 | NA | indefinitely | Bronze
R02 | R02 | R02DMZ | CCS GSP Supra ADFS for SSO - STAGE | XMNT254 |  |  |  | Meriden |  |  | Microsoft Windows Server 2012 Standard R2 | Rehost | Kyle Shields, Jan Phillips | [12 empty] | AWSCloudWatchAgentRole | R02DMZ | [20 empty] | CASS-SUPRA | IC990447
Note on P1: Microsoft Office User: There is no proxy on CUSH0A03, cush1ay3
Note on V1: Microsoft Office User: Default KMS Key
Note on S7: Microsoft Office User: For 128 GB RAM the minimum available cores are 16
Note on AP7: Microsoft Office User: For 128 GB RAM the minimum available cores are 16
Note on F10: Microsoft Office User: From system info, the domain is utccgl.com
Note on E11: Microsoft Office User: qush0a31.utccgl.com Able to ping on IP and telnet 3389. But not able to take RDP
Note on BE18: Microsoft Office User: Apr 1 2023 (default)
Note on BE49: Microsoft Office User: Apr 1 2023 (default)
Note on BE81: Microsoft Office User: Apr 1 2023 (default)
Note on BE107: Microsoft Office User: Apr 1 2023 (default)
Note on BE112: Microsoft Office User: Apr 1 2023 (default)
Note on BE118: Microsoft Office User: Apr 1 2023 (default)
Note on D121: Microsoft Office User: old app name - CCS GSP TE_TestReults

## dropdown
server os | server tier | tenancy
windows | app | Shared
linux | web | Dedicated
| db | Dedicated host

## Pilot-Factory-Input
Migration Factory Input - (AWS Migration team)
wave_id | app_name | cloudendure_projectname | aws_accountid | server_name | server_os | server_os_version | server_fqdn | server_tier | server_environment | subnet_IDs | securitygroup_IDs | subnet_IDs_test | securitygroup_IDs_test | instanceType | tenancy
Pilot | NWDI-STAGE | TSA_EXIT_PILOT | 260780007980 | CUSNWK0V | windows | Windows 2008 R2 | CUSNWK0V.carcgl.com | app | stage | [subnet-0a36a688c9f6caf95] | sg-0371ea9436d9879fa | [subnet-0dac817a917abb034] | sg-0536cbe9e8a352c72 | t2.medium/ t3a.medium | shared
Pilot | JONAS - STAGE | TSA_EXIT_PILOT | 260780007980 | CUSNWA74 | windows | Windows 2012 R2 | cusnwa74.carrier.utc.com | app | stage | [subnet-0a36a688c9f6caf95] | sg-0371ea9436d9879fa | [subnet-0dac817a917abb034] | sg-0536cbe9e8a352c72 | t2.large/t3a.large | shared
Pilot | MYEDDIE-TEST | TSA_EXIT_PILOT | 917128996017 | KUSMND19 | windows | Microsoft Windows Server 2008 R2 Enterprise | kusmnd19.carrier.utc.com | db | test | subnet-06de97b914fec4d10 | sg-0ac65d65a7d551733 | [subnet-0f866e16dd1977655] | sg-06bf1dfeb43c97567 | t2.large/t3a.large | shared
Pilot | HVACNA-NPC-US-NAFS-TEST | TSA_EXIT_PILOT | 917128996017 | CUSNWT0M | windows | Microsoft Windows Server 2008 R2 Standard | cusnwt0m.carrier.utc.com | app | test | [subnet-0a36a688c9f6caf95] | sg-0371ea9436d9879fa | [subnet-0dac817a917abb034] | sg-0536cbe9e8a352c72 | t2.large/t3a.large | shared
Pilot | General Test | TSA_EXIT_PILOT | 260780007980 | CUSH1AV8 | windows | Windows Server 2012 R2 Datacenter | cush1av8.utccgl.com | app | test | [subnet-06de97b914fec4d10] | sg-0ac65d65a7d551733 | [subnet-0f866e16dd1977655] | sg-06bf1dfeb43c97567 | t2.medium/ t3a.medium | shared

## Subnet & SG
wave_id | app_name | cloudendure_projectname | aws_accountid | server_name | server_os | server_os_version | server_fqdn | server_tier | server_environment | subnet_IDs | securitygroup_IDs | subnet_IDs_test | securitygroup_IDs_test
|  | Fire_And_Security_Dev_890585303181 | 890585303181 | [6 empty] | subnet-0c6533ebaf5f1b1a2 | sg-05d2d8a7449289f9e | subnet-04442255f59601142 | sg-09876514db5a00fb8
|  | Fire_And_Security_PreProd_917128996017 | 917128996017 | [6 empty] | subnet-0dd905d5c0776f8ac |  | subnet-0177cd4a69a41399d
|  | Fire_And_Security_Prod_808538705328 | 808538705328 | [6 empty] | subnet-085227562c4baaf92 | sg-0be778a6e7043ca80 | subnet-085227562c4baaf92 | sg-03d765951f2e6d249
|  | Fire_And_Security_Prod_Ext_213337406033 | 213337406033 | [6 empty] | subnet-0cdde536279ae4611,subnet-0666830064416e124,subnet-0eaaa3ff23730120b | sg-02f2c55ccfa7457b4 | subnet-0f1c7ecbe8f3caef2,subnet-0405337ea6fef38c7,subnet-01fb850bfbc6a2fbf | sg-0d1999fe93ca295c6
|  | HVAC_Com_Dev_436524867280 | 436524867280 | [6 empty] | subnet-00a9966005a386acb | sg-0765e3df2626173e2 | subnet-00a9966005a386acb | sg-0c55b9769612daba9
|  | HVAC_Com_PreProd_260780007980 | 260780007980 | [6 empty] | subnet-0a36a688c9f6caf95 | sg-0371ea9436d9879fa | subnet-0dac817a917abb034 | sg-0536cbe9e8a352c72
|  | HVAC_Com_Prod_913828333602 | 913828333602 | [6 empty] | subnet-04a5b0c4eff0b5e65 | sg-06e849287c4603b7d | subnet-04a5b0c4eff0b5e65 | sg-07d38644ed9df7a61
|  | HVAC_Com_Prod_Ext_703675924793 | 703675924793 | [6 empty] | subnet-0512eb413ab3f5df6,subnet-0e7526820c0ebcab8,subnet-0494d1e1102ddb07e | sg-08fdb074428e99ebc | subnet-041bb52de22bfe354,subnet-0aabb8adcd57f80df,subnet-0e3da1d734b5b6b96 | sg-062ef17c8d2d9716a
|  | HVAC_Res_Dev_424277870443 | 424277870443 | [6 empty] | subnet-027c1c1d46d4f4b27 | sg-0d0f0bd000eec7c6f | subnet-0f81630b0b12168e9 | sg-0ebc7f0a0e5cf0ba6
|  | HVAC_Res_PreProd_823570924226 | 823570924226 | [6 empty] | subnet-034c5b1f10a32deaf | sg-0eb6d6c9b2ca6e16c | subnet-034c5b1f10a32deaf | sg-044e1966a2ef361df
|  | HVAC_Res_Prod_501143608669 | 501143608669 | [6 empty] | subnet-0d2c10f3c6ae2fece,subnet-0195bdd3ecf336d5e,subnet-0b82b2b6725d3300f | sg-0d09f9d12ffec86b1 | subnet-01a25b587de2ac578,subnet-03141750165d04203,subnet-0b82b2b6725d3300f | sg-04fe3038a54e44e4d
|  | HVAC_Res_Prod_Ext_326722459790 | 326722459790 | [6 empty] | subnet-09f4b9b0d11a261a9,subnet-07b0a4cf1e7d56cf6,subnet-0e1c71f07d8143edf | sg-0801c70ce42acc9ed | subnet-03485574981a65a20,subnet-0daa2e3ce8b532cd2,subnet-0762a29b2ef2c6ae9 | sg-05ce9e6b0fa3ecf9d
|  | Refrigeration_Dev_760898938529 | 760898938529 | [6 empty] | subnet-0ddd4a95b70d3ce86 | sg-066e24b7bc212b283 | subnet-001065f58cd9392e1 | sg-060fa27b23a554ca8
|  | Refrigeration_PreProd_015623844436 | 015623844436 | [6 empty] | subnet-0d00575edc91f7279 | sg-0083063a33edbdb03 | subnet-04d89a229461d87aa | sg-02fe7d742a1b0548c
|  | Refrigeration_Prod_707766415800 | 707766415800 | [6 empty] | subnet-077b7aa26f206e5d1,subnet-0c5d72fcf985d8231,subnet-0f098edf5b7be72bc | sg-0281524ca4012fafb | subnet-070462d888b803107,subnet-0dfd7451ac81fce23,subnet-081faf8d59d54f02d | sg-025b3ec92d0987576
|  | Refrigeration_Prod_Ext_278620395487 | 278620395487 | [6 empty] | subnet-0ce1c6b4c49db2d20,subnet-09443adeef9a627b7,subnet-0c7d6b0f0063458ac | sg-054045df900bc5a4b | subnet-05e955c32535cdd0e,subnet-0e1ec230f24c926a8,subnet-0a24c2172b4da354e | sg-0eb0968f12c9b67f2
Note:
All Production Servers --> Respective Prod accounts
All Test/Stage/Preprod servers --> Respective Pre-Prod accounts
All the Dev Servers --> Respective Dev accounts
External (DMZ) servers --> Respective EXT accounts
Note: Keep only one Subnet ID MF input form, Rotate the subnet ID per wave to spread the servers acrooss multiple subnets/az's

## Sheet2
Non-Prod AWS Accounts | CloudEndure Replication Status
Fire_And_Security_Dev_890585303181 | Pending
Fire_And_Security_PreProd_917128996017 | Pending
HVAC_Com_Dev_436524867280 | Success
HVAC_Com_PreProd_260780007980 | Success
HVAC_Res_Dev_424277870443 | Success
HVAC_Res_PreProd_823570924226 | Success
Refrigeration_Dev_760898938529 | Success
Refrigeration_PreProd_015623844436 | Success

## Tagging-Description
Name Tag (Key) CamelCase | Value Tag (Source) lowercase
ApplicationName | From CMDB
ApplicationID | From CMDB
ApplicationOwner | Email Address or Dist. (ActiveDirectory)
BusinessUnit | Workflow Request Form
Department | Finance / Marketing / Sales
CostCenter | Financial System or Workflow Form
ServerType | Application, IT, Security, Infrastructure, DB etc.
ComplianceRequirement | HIPAA / GDPR
Entity | Workflow Request Form
Environment | DEV, STG, TST, PRO (only one)
Region | USEast / EUWest / APCentral
UsagePattern | 24 Hours / 7 AM - 7 PM / Weekdays / Weekend
MaxLifeTime | 14 Days / Indefinitely
AppCat | PLATINUM / GOLD / SILVER / BRONZE
Backup | <Value> | TBD

## Path 3 Dashboard (hidden)
|  |  | Discovery |  |  | Design |  |  |  | Build and Valiate | [5 empty] | Cutover | [5 empty] | Post Cutover
Wave | App | Server | Get current application architecture diagram (App Owner) | Get networking req such as firewall, load balances (App Owner) | Denfine test cases (App Owner) | Design target application architecture (AWS) | Design EC2 instance (AWS) | Design networking component as needed (AWS) | Submit AMS Req. (AWS) | Build CloudFormation template for the target infra if needed (AWS) | Submit AMS RFC to build infra in AMS (AWS) | Install new agents or tools on the new infra (AWS) | Submit a AMS Stack admin access RFC to access (App Owner) | Install or deploy application to the new infra (App Owner) | Update change ticket as needed | Replicate data from source to the target infra (App Owner) | Test appliction on the new infrastructure (Application in testing) (App Owner) | Complete final data replication and shutdown the source server (AWS, App Owner) | Change network conn to use the new app endpoint in AMS (Server cutover) (AWS, App Owner) | Test the application after the source server is offline (App Owner) | Post Cutover activities/validation |  | App Owner
1 | CERBERUS | Prod - de08w1429, ny17nt0058 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-06-14 | 2019-06-14 | 2019-06-14 | 2019-06-21 | 2019-06-21 | 2019-06-21 | 2019-06-21 | 2019-06-21 | 2019-06-21 |  | Ryan, Arthur <Arthur.Ryan@resideo.com>
2 | UPC/EAN | Dev - New app | 2019-05-10 | 2019-05-07 | 2019-05-14 | 2019-05-14 | 2019-05-14 | 2019-05-14 | 2019-05-14 | 2019-05-21 | 2019-06-21 | 2019-06-21 | 2019-06-21 | 2019-06-21 |  | 2019-06-27 | 2019-06-27 | 2019-06-27 | 2019-06-27 | 2019-06-27 | 2019-06-27 |  | Jha,Rishi <Rishi.Jha@Honeywell.com>
2 | LOADRUNNER TOOL 1.0 PROD CORP INT | Prod - de08w1219 | 2019-05-07 | 2019-05-07 | 2019-05-14 | 2019-05-14 | 2019-05-14 | 2019-05-14 | 2019-05-14 | 2019-05-21 | 2019-06-21 | 2019-06-21 | 2019-06-21 | 2019-06-21 |  | 2019-06-27 | 2019-06-27 | 2019-06-27 | 2019-06-27 | 2019-06-27
2 | TEST READY 1.0 PROD CORP INT | Missing server | 2019-05-07 | 2019-05-07 | 2019-05-14 | 2019-05-14 | 2019-05-14 | 2019-05-14 | 2019-05-14 | 2019-05-21 | 2019-06-21 | 2019-06-21 | 2019-06-21 | 2019-06-21 |  | 2019-06-27 | 2019-06-27 | 2019-06-27 | 2019-06-27 | 2019-06-27
Target- 4 | LOGISTIC TOOL 1.0 | Prod - hic005789, hic007183 | [20 empty] | Ananda Kumari Chidambaram, Sampada Mathkar
Green = Activity in Progress.
Yellow = Activity in Progress. has a current or potential risk.
Red = Major risk. Requires immediate management involvement
Blue = Activity completed
Gray = Activity Not Started

## Change Ticket (hidden)
Wave | App | Server | Submit change ticket for migration (PMO) | change # | CAB scheduled | Status (scheduled =passed CAB). New, Assses, Authorize, Scheduled | requested Change scheduled
1 | ACCOLADE SOPHEON - PMO | QA - hic007982, hic008009, hic007981 | 2019-04-18 | CHG0104835 | ECAB held | Scheduled | 2019-05-05
1 | ADI PWA | QA - de08w1555, de08w1557 | 2019-04-18 | CHG0105150 | ECAB requested | Authorize | 5/8-9
1 | EACCOUNT RECONCILIATION | Dev - HIC007381, HIC007349 QA - HIC007368, HIC007369, HIC007394 | 2019-04-25 | CHG0104872 | ECAB held | Authorize | 2019-05-05
1 | Hyperion Financial Management | Dev - de08w3394, de08w3393, de08w3400, de08w3392, de08w3397, de08w3398, de08w2571, DE08W3396, DE08W3399, de08u2250, DE08W3404, DE08W3405, de08u2249 | 2019-04-25 | CHG0103053 | issues with conflict | Assses
2 | ACCOLADE SOPHEON - ENG | Dev/QA - ny17w1085, ny17w1087, ny17w1086, ny17w1083 |  | CHG0103054 |  |  | 5/16-20
2 | ACCOLADE SOPHEON - PMO | Prod - hic009400, hic009399, hic009453 | 2019-05-07 | CHG0105728 |  | Assses | 5/16-17
2 | HSG PWA OLAP CUBE | Prod - de08w1553, de08w1554, de08w1556, de08w1558 |  | CHG0105150 | ECAB requested | Authorize | 5/8-9
2 | IC REPORTING OLAP CUBE | Prod - de08w1558 (dup-3), de08w2765 QA - de08w2764 |  | CHG0105150 | ECAB requested | Authorize | 5/8-9
2 | MARKET SIZE REPORTING OLAP CUBE | Prod - az18w9161, az18w9492 QA - de08w9197 (dup-2), de08w9486 | 2019-05-07 | CHG0105731 |  | New | 5/16-17
2 | ACHIEVE OLAP CUBE | Prod - de08w1553(dup-1), de08w1554 (dup-1), de08w1556 (dup-1), de08w1558 (dup-1) |  | CHG0105150 | ECAB requested | Authorize | 5/8-9
2 | ADI PWA | Prod - de08w1553 (dup-2), de08w1554 (dup-2), de08w1556 (dup-2), de08w1558 (dup-2) | 2019-05-07 | CHG0105733 |  | New | 5/16-18
2 | Factory Produtivity Tool (Descoped) | Prod/QA: de08w9197, az18w9492 (dup-1) QA - de08w9197 (dup-1), de08w9486 (dup-1) | 2019-05-07 | CHG0105762 |  | New
2 | Hyperion Financial Management | Prod - HIC005070, HIC005207, HIC006121-HIC006124, HIC006127, HIC006128, HIC005077, hic005178, HIC006125, HIC006126, hic005180
2 | METRIX - TX55 | Dev - de08w3487, de08w3668 | 2019-05-06 | CHG0104102 |  |  | 5/16-17

## Wave Schedule (hidden)
| Apr |  | May |  |  |  | Jun |  |  |  | July |  |  |  |  | Aug
| 2019-04-22 | 2019-04-29 | 2019-05-06 | 2019-05-13 | 2019-05-20 | 2019-05-27 | 2019-06-03 | 2019-06-10 | 2019-06-17 | 2019-06-24 | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26
Project Week | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Application Discovery
Path 2
Wave 1
Wave 2
Wave 3
Wave 4
Wave 5
Wave 6
Path 3
Wave 1
Wave 2
Wave 3
Wave 4
Wave 5
Wave 6
Wave 7
Wave 8
Wave 9
Server On-Prem | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 136 | 106 | 76 | 46 | 16 | 0
Server Replicated | 0 | 0 | 0 | 29 | 30 | 30 | 30 | 30 | 16 | 0 | 0 | 0 | 0 | 0
Server in Testing | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 30 | 30 | 30 | 30 | 16 | 0 | 0
Server Cutover | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 30 | 30 | 30 | 30 | 16
Discovery (remaining 55 apps)
Discovery
Build & Validate
Cutover
Design
Foundation
Foundation
Discovery
Build & Validate
Cutover
Design
Discovery
Build & Validate
Cutover
Design
Discovery
Build & Validate
Cutover
Design
Discovery
Build & Validate
Cutover
Design
Discovery
Build & Validate
Cutover
Design
Discovery
Build & Validate
Cutover
Design
Foundation
Discovery
Build & Validate
Cutover
Design
Foundation
Discovery
Build & Validate
Cutover
Design
Foundation
Discovery
Build & Validate
Cutover
Design
Foundation
Discovery
Build & Validate
Cutover
Design
Foundation
Discovery
Build & Validate
Cutover
Design
Foundation
Discovery
Build & Validate
Cutover
Design
Foundation
Discovery
Build & Validate
Cutover
Design
Foundation
Discovery
Build & Validate
Cutover
Design
Discovery (remaining 55 apps)
Discovery
Build & Validate
Cutover
Design
Foundation
Foundation
Discovery
Build & Validate
Cutover
Design
Discovery
Build & Validate
Cutover
Design
Discovery
Build & Validate
Cutover
Design
Discovery
Build & Validate
Cutover
Design
Discovery
Build & Validate
Cutover
Design
Discovery
Build & Validate
Cutover
Design
Foundation
Discovery
Build & Validate
Cutover
Design
Foundation
Discovery
Build & Validate
Cutover
Design
Foundation
Discovery
Build & Validate
Cutover
Design
Foundation
Discovery
Build & Validate
Cutover
Design
Foundation
Discovery
Build & Validate
Cutover
Design
Foundation
Discovery
Build & Validate
Cutover
Design
Foundation
Discovery
Build & Validate
Cutover
Design
Foundation
Discovery
Build & Validate
Cutover
Design

## Sheet1 (hidden)
Wave |  | Submit change ticket for migration (PMO) | Create Wave and app/server in the migration factory (AWS) | Get and update server attributes (AWS) | Submit AMS Req. (AWS) | Apply correct testing subnet, security groups and tags (AWS) | Create local admin, and Install CloudEndure agent (CapG) | Launch server from migration factory and CloudEndure (AWS, CapG) | Check AMS pre-requisites (CapG) | Cleanup server for ingestion. (WIGs Prep) (CapG) | AMS Workload ingestion RFC (CapG) | Create application users in Resideo domain (Wipro & TCS/app owner?) | Application change and testing. (Servers in testing)(TCS/App Owner) | Launch server from migration factory and CloudEndure (AWS ProServe, CapG) | Check AMS pre-requisites (Cap G) | Cleanup the server for ingestion (Cap G) | AMS Workload ingestion RFC (Cap G) | Application change and testing (TCS/App Owner) | Change DNS or other network settings for the application (Cap G?) | Post Cutover activities/validation (App Owner) | Close down Ports 4 wk after cutover (App Owner) | App Owner
1 | Original | 2019-04-25 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-10 | 2019-05-10 | 2019-05-21 | 2019-05-17 | 2019-05-17 | 2019-05-17 | 2019-06-14 | 2019-06-14 | 2019-06-21 | 2019-06-21 | 2019-06-21 | 2019-06-21 | 2019-06-21 | 2019-06-21 |  | 2019-07-21
1 | Revised | 2019-04-25 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-10 | 2019-05-10 | 2019-05-21 | 2019-05-24 | 2019-05-24 | 2019-05-24 | 5/27 - 6/28 | 5/27 - 6/28 | 7/1 - 7/5 | 7/1 - 7/5 | 7/1 - 7/5 | 7/1 - 7/5 | 7/1 - 7/5 | 7/1 - 7/5 |  | 2019-08-05
2 | Original | 2019-04-25 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-10 | 2019-05-17 | 2019-05-24 | 2019-05-24 | 2019-05-24 | 2019-05-24 | 2019-06-21 | 2019-06-21 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 |  | 2019-07-28
2 | Revised